TOWARDS A GREENER TOMORROW

SEDS ANNUAL REPORT

APRIL 2017 - MARCH 2018

During this financial year the work at SEDS has carried on keeping in line with the mission and vision statement of the organisation.

The programs undertaken are:

- The monitoring and supervision and repairs of units that were constructed.

- Low carbon sustainable Agriculture program

- Child sponsorship

- Tank desilting program

- SEDS Ananda Vidyalayam school year.

All programs as before have been implemented through the total involvement of the beneficiaries and their total participation.

The PIA sponsorship program and the SEDS School continued this year. The school gets support from IKIKI Japan and is able to pay the costs to run the school. Our commitment to provide better education for the children in the villages continues.

The Low Carbon farming project has been supported by PIA this year and funds have run out for further funding.

PIA had started a crowd funding initiative in June of 2017 and has been able to raise an amount of Australian $ 9300. Their accounting year ends in June every year so we have together decided to wait till the end of June for the transfer of the monies.

Reflections………………

37 years ago SEDS was started. Our aim has always been – water, food and basic necessities for the poorest of the poor and working on improving the environment.

10 villages have become 350 today mainly due to the Bio Gas Program which extended to 6 Mandals in Anantapur district

It was the methodology of “do and learn” that has brought us here today. Visions and missions realised with a lot of hard work and perseverance to get there.

We are now in the stage of change and self sustainability and to achieve this stage development has to be looked at from a business angle. Most Organisations started with donor funding but today all NGOs are concentrating on sustainability of the organisation to continue the work.

SEDS can proudly reiterate that as an NGO from the 80s we have been trail blazers or firsts in many fields of development. We wanted change and today looking at the area a change can be seen very clearly with environment, health, children going to school and the community.

All work taken up in the last 37 years was the need of the hour. It involved charity approach/pragmatic approach/community taking responsibility of their lives/community being made aware of their lives along with their rights to be able to demand basic rights and legal rights from the government. Food and environment was a main focus. Hence all SEDS work aimed at a richer sustainable environment and agriculture

From this developed tree nurseries, vegetable gardens, homestead plantations, bund plantations, reforestation, community woodlots, tank bed planting, avenue plantations, horticulture plots, and hectares of Hillocks being greened and Watershed management with Tank de-silting thus became the forte of SEDS. With tank de-silting fish farming became big income additionality for the communities

Since 2010 SEDS has been working on mitigating climate change through a Clean Development Mechanism approach.

We have completed a program for 5000 bio gas plants in 5 Mandals.

The problems faced in implementing such a program have been enormous but it was accomplished with the same doggedness that has been a very positive strength of SEDS and the people on the field.

The problems faced in implementing such a program have been enormous but it was accomplished with the same doggedness that has been a very positive strength of SEDS and the people on the field.

The agreement with the buyer remains the same that is to deliver 105716 CERs of which our delivery has been 33418 CERs. The next verification was from 0.11.15 to 31.12.17. The verification process is over and this time the delivery will be 28700 CERs. The delivery has been submitted to the UNFCCC and we await acceptance. The balance to be delivered is 43598 CERs which will take us past 2020 as we see it now. The rules have become more stringent and we will now have to also monitor fuel usage in the homes annually and according to this CERs will be deducted so the delivery is going to be harder now.

Our registration is still pending as the DOE has been very slow in submitting the papers. From our side we have submitted and had a site visit from the DOE also. According to Sudha Padmanaban the scientist and consultant in charge from the FCN she has reassured us that it is a formality and there should not be a problem.

The drought situation with NO WATER has made the task of keeping the units viable is becoming more and more difficult. People have no drinking water and it is difficult to mix dung with no water available. Our staffs are on a high alert and are sometimes mixing the dung with the beneficiaries themselves.

The detailed report from the computer is added for more details as Annexure 1

The LCF team is now headed by Imran and his committed 5 field workers. A detailed report is added from Imran and team as an annexure 2.

The funding for this program comes to an end in June 2018 and PIA has started a crowd funding process to raise more money for this program. We will know by end June how much has been raised and plan for the next year depending on funding availability. Till then the staff of LCF have been absorbed into the CDM program for monitoring and maintenance.

In this financial year we have completed de silting in another village Kolimipalli taken up in May 2017.

Details with pictures are in annexure 3.

The PIA sponsorship program covered 185 children this year. 18 students have respectively completed their high school graduation and pre-university courses and await their results in June 2017. 3 children left the program for reasons of transfer or migration to other schools not in SEDS area of work. An annexure 4 is added for details of the year activities.

SEDS School

This year the SEDS School has been run by Rashna Joshua and the Education Coordinator Rasool Khan again and they have done a good job of improving the school functioning and upgrading teachers’ skills and regularising the administration of the school.

From 2016 the school as we have been linked in to the government system where we have been registered online as being on the CCE (Continuous Comprehensive Evaluation) program of the government. Internal marks of 20 are a must especially for the 10th STD and all children are registered online with biometrics of each child.

Any student leaving a school has to procure a TC or Record sheet from the previous school before joining another. Earlier students just left and joined up in other schools which resulted in most cases default in payment of fees. The school report is attached as annexure 5 prepared by Rasool Khan

Visitors and volunteers:

Amanda Stone from PIA visited SEDS this year. Ronny Smet from Belgium visited twice in the last year.

Interns from Queensland University – Bethany Morris from Queensland University and Felicity Biggs and Morgan Dowling from Sunshine Coast University spent three months doing their internship.

Finances: SEDS has received support from PIA Australia, Bread for the world/EED Germany, IKIKI Japan and several individual donors.

Income Foreign: Rs 56, 85,968

Income Indian: Rs. 3, 23,570

Annexure I		- CDM April 2017-March 2018

Annexure II	- Low Carbon Farming Report April 2017-March 2018

Annexure III	– Tank Desilting Report April 2017-March 2018

Annexure IV	– PIA Report April 2017-March 2018

Annexure V	– SEDS School Report Ananda Vidyalayam- April 2017-March 2018

Annexure VI – Old People Programme Report Ananda Vidyalayam- April 2017-March 2018

Annexure I	- CDM Super Report April 2017-March 2018

Annexure I	- CDM April 2017-March 2018

Stove & Pipe Repairing to the Bio Gas

Monitoring the Bio Gas Unit

Mixing the Cow Dung for the

CDM – BIO Gas UNIT

Cooking on the Bio Gas Stove

Repairing the Bio Gas Unit

Biogas Trainings & Meetings

Biogas Verification

Annexure II - Low Carbon Farming Report April 2017-March 2018

Mixing the Cow Dung for the

CDM – BIO Gas UNIT

# SEDS PIA LCF - report

April 2017 – March 2018

# Achievements

| Villages Covered | 113 |
| --- | --- |
| Farmer Families | 4187 |
| Acres with GPS readings | 5349 |
| Number of discrete Plots | 2680 |

Monthly wise work Report

April - 2017:-

- New 5 farmer groups data collected,

- Diaries collected – 396, total collected 914,

- Farmer groups name boards prepared in 9 villages, total 27 completed.

- Collected farmer phone numbers in 16 villages for to start sms service( Bulk messaging),

- Conducted regular meetings in 25 villages and given Sustainable Agriculture training,

- Given Sustainable Agriculture training to staff for 2 days,

- Bank accounts opened for farmer groups - 2 out of 20,

- Attended Fair climate network meeting in FCN campus in Bageapalli.

May - 2017:-

- Tank desalting work done in Kolimipalli village, total 30 farmers and 900 loads,

- New 6 farmer groups data collected,

- LCF Diaries rechecked and updated in database 706 out of 914 Diaries balance is 208,

- Farmer groups name boards prepared in 8 total completed 35 villages,

- Given Sustainable Agriculture training to staff for 2 days,

- Conducted regular meetings in 19 villages and given Sustainable Agriculture training

- Collected farmer phone numbers in 20 villages for to start sms service ( Bulk messaging),

June - 2017:-

- Collected farmer phone numbers in 14 villages to start sms service (Bulk messaging), completed 50 villages.

- Bank accounts opened for farmer groups - 6 out of 20,

- Given Sustainable Agriculture training to staff for 2 days,

- LCF balance 208 Diaries rechecked and updated in database completed 914 Diaries,

- Conducted regular meetings in 22 villages and given Sustainable Agriculture training

July - 2017:-

- Collected old 30 Groups data for NABARD(National Bank for Agriculture and Rural Development) for Digitization and submitted,

- LCF GPS Readings done in Suddakuntapalli, 18 farmers, 18 plots,

- Conducted regular meetings in 22 villages and given Sustainable Agriculture training,

- 2 new groups reformed by some other issues,

- Prepared farmer group seals, Letter pads to 9 groups.

August - 2017:-

- LCF Readings done in Bojjireddipalli, 14 farmers, 14 plots,

- LCF Readings done in Guddumnagepalli, 20 farmers, 20 plots,

- Conducted regular meetings in 17 villages and given Sustainable Agriculture training,

- Done PIA LCF Validation,

- Prepared farmer group seals, Letter pads to 6 groups

September - 2017:-

- Bank accounts opened for farmer groups - 8 out of 20,

- Linked 5 New groups to NABARD for financial support to farmer groups, and waiting for another 15 groups to link,

- Conducted Base Level Orientation Training Program (BLOTP) in 5 villages for NABARD,

- Conducted regular meetings in 15 villages and given Sustainable Agriculture training,

- Brought new program “Meet With Expert” for old 30 groups from NABARD (They will help with funding up to Rs.5000/- )

October - 2017:-

- Fish fingerlings – Doddagatta – 1,00,000 distributed,

- Conducted regular monthly meetings in 21 farmer groups,

- Opened 2 bank accounts for new farmer groups  total completed 10 out of 20,

- Updated 20 groups’ data into the NABARD website for digitization.

November - 2017:-

- Fish fingerlings – Nalluru – 2,05,000, Seshapuram – 50,000, Gobbarampalli – 1,50,000 distributed,

- Conducted regular monthly meetings in 18 villages,

- Attended AP Government program – “Mega Pasu Grasa Kshetralu” – MPGK in Anantapur for 2 days,

- GPS plots recheck – Suddakuntapalli – 20 plots

December - 2017:-

- Conducted regular monthly meetings in 11 farmer groups,

- Conducted meeting with Aggarbatti ( Joss sticks) Factory persons and with the farmers in Palasamudram to establish Aggarbatti packing unit through FPO,

- GPS plots recheck – Peddakodipalli – 22 plots, Dandepalli – 21 plots,

January 2018:-

- Conducted awareness meetings for Tank Desilting Work in 13 villages, and  3 villages are ready to participate,

- Collected and paid to office Tank desilting local contribution from Suddakuntapalli – 60 farmers*201=12060.00,

- Prepared and sent proposal for FPO to NABARD

February – 2018:-

- Collected and paid to office Tank desilting local contribution from Guddumnagepalli – 40 farmers*201=8040

- Visited Fish Fingerlings tanks – Doddagatta, Nalluru, Seshapuram, Gobrampalli

- Conducted regular monthly meetings in 9 farmer groups,

March – 2018:-

- Given Sustainable Agriculture trainings to 21 farmer groups,

- LCF plots rechecked in Hussainpuram – 18 plots, Guddumnagepalli – 21 plots,

- Updated all plots data into the data base.

# Agricultural EXTENSION PROVIDED by SEDS:

- Sustainable Agriculture

- Low Carbon Farming

- NABARD

- Producer Company

- Other agro-activities

- Fish Fingerlings

- Tank Desilting Work

# The cultivating season

  - Khareef 2017 - 18 this season  we received a reasonable amount of rain and tanks filled up to 60% capacity and almost 80% of agricultural land was brought under cultivation.

# Sustainable Agriculture

- 50 villages receive monthly meeting trainings on Sustainable Agriculture. With this different activities are also taking place (see table)

- We formed 20 farmer groups in new villages and we have 50 farmer groups now and hope to form more groups in the coming years, totally our target is to form groups in all 113 villages.

# Developments in LCF

- As usual  Labs are still not able to provide carbon numbers, hence no calculations and no carbon credits

- But “Gold Standard” has introduced the “Cool Farm Tool (CFT)” methodology to calculate carbon credits. This is going through a strict verification process and ironing out glitches before it is presented to prospective buyers. As in all new methodologies that are based on the sciences processes are vetted thoroughly before it is passed. We have in spite of labs failing to give us figures and waiting for the Cool Farm Tool continued in our efforts and more and more farmers are changing to Low Carbon Farming. This keeps us convinced that we are on the right path with a commitment that it will be ready to work for the next crop season.

- Agro forestry will be included in the project

  - Agro forestry is a proven methodology; it is a management system that integrates trees on farms and in the agricultural landscape. It leads to a more diversified and sustainable production system than many treeless alternatives and provides increased social, economic, and environmental benefits for land users at all levels

  - All trees planted since the start of the LCF project due to NGO efforts for LCF and Sustainable Agriculture will be taken into account

  - We are confident that we will be able to reach our target of 1500 acres. That is our STRENGTH.

  - Our WEAKNESS is lack or poor funding for a new idea with a risk and not being to employ skilled staff due to low salaries.

  - Our OPPURTUNITY is that we are convinced and need to strike while the iron is hot.

  - Our THREAT is NO FUNDING and Drought.

- Update Season 2012 – 2013

  - SEDS received positive claim validation of the work.

  - “The TUV Rhineland (India) Pvt. Ltd considers necessary to give reasonable assurance that reported data were monitored correctly on the basis of the methodology provided in the MR. the DOE states that the reported monitoring data are free from material errors, omissions and misstatements with a reasonable level of assurance.”

  - In layman terms it means that the information provided by SEDS and the farmers regarding the planted crops and undertaken activities on the plots was correct and this data can now be used for future calculations.

- Update Season 2013 – 2014

  - From the 800 farmers eligible to take up LCF 560 have given diaries back for a 1000 plots covering 2000 acres

- Update Season 2014 – 2015

  - 856 Diaries distributed

  - Proven to be disastrous, not many farmers were able to grow a crop this year and LCF cropping numbers are feared to be very low.

- Update Season 2015 – 2016

- 927 Diaries Distributed

- Given training to LCF Diary monitors and Taken Soil for Redgram crop measurement.

- 927 Diaries updated in data base.

- Update Season 2016 – 2017

- Done GPS Readings in new 6 villages, 194 acres GPS reading done,

- Given Training to LCF Diary monitors, 1140 Diaries distributed for Khareef Season.

- Giving training to LCF staff about Climate Change and SA practices every month 2 days,

- Started SMS service to pass the information to farmer,

- Prepared 18 farmer groups name boards,

- Formed new 15 farmer groups.

- Collected 518 lcf diaries in 17 villages.

- Update Season 2017 – 2018

- Done GPS Readings in new 14 villages, 342 acres GPS reading done,

- 914 Diaries collected and updated in to the database,

- Prepared 29 farmer groups name boards,

- Tank desalting work done in Kolimipalli village, total 30 farmers and 900 loads

- Formed new 5 farmer groups.

- GPS plots recheck done in 20 villages and updated in database,

- Done regular monthly meetings in all 50 villages

- Distributed fish fingerlings  5,05,000 in 4 villages

LCF Photos

# NABARD

- The National Bank for Agricultural and Rural Development has been officially linked up with our original 5 new farmer groups they will support 12,000/- per year for 3 years . We are in the process of linking the remaining 15 farmer groups to NABARD

NABARD Photos

Fish Fingerlings Photos

Annexure III – Tank Desilting Report April 2017-March 2018

TANK DESILTING

- Total 1 villages covered,

- Tank desalting work done in Kolimipalli village, total 30 farmers and 900 loads

Tank Desilting a Note for the reader

Tank Desilting is a program taken up for some of the following reasons:

- To enhance storage capacity in the existing tanks through more efficient catchment which, have been silted from runoff from the hills of soil due to de-forestation.

- To increase water resources through efficient micro catchments based on local knowledge and simple low cost structures.

- To return fertile soils to the farmer lands for higher yields in crops.

- Farmers are able to generate income in balance with their natural environment.

- To ensure that a natural resource is managed efficiently by the community.

- To promote livelihoods for women through kitchen gardens and homestead plantations.

- To promote farmer groups to take up sustainable agricultural practices leading to Low Carbon Farming (mixed cropping, farming with attention for food crops and input cost reduction)

- To promote an ownership of these catchments to the communities.

We try to reach as many farmers as the budget allows.

| No of Farmers | No of Loads | Unit Cost | Paid Payment | Pit size | No of Cubic meters |
| --- | --- | --- | --- | --- | --- |
| 30 | 390 | 130 | 50700.00 | 60*26*2 | 3120 |
|  | 330 | 150 | 49500.00 |  |  |
|  | 120 | 170 | 20400.00 |  |  |
|  | 60 | 180 | 10800.00 |  |  |
| TOTAL | 900 |  | 131400.00 |  |  |
| JCB Hours | 68.5 | 720 | 49320.00 |  |  |
| Grand Total |  |  | 180720.00 |  |  |

Water storage capacity brought to 3,12,0000 gallons.

When the rains come the tank will store 3,12,0000 more gallons of water which will be used for irrigation cattle and for fish rearing as an additional income.

Local Telugu News Paper statement

About tank desilting work: -

Tank Desilting Work Photos

Discussions and planning  						      Marking

Ongoing work 					After completion

Annexure IV – PIA Report April 2017-March 2018

SEDS PIA

Sponsorship program report April to March 2017-18

April:

On April 8th we conduct 2nd Saturday program. On this particular day activities like attendance registration and height & weight measurements were taken. Thereafter we separated the children into two groups. In the first part of activity children participated in the singing competition and the children in group A won. In the second part of activity we had a quiz competition among the children; the question for the quiz is asked by children among themselves and it is related to their subjects and general knowledge. First there was tie between the two groups, later we added 5 questions to each group. Finally group B won the quiz competition. Children enjoyed and had fun; they received bus fare, had a meal and went home happily.

May:

On May 20 2017 we conducted the PIA second Saturday program of the month; on this particular day measurements, heights & weight measurements are taken of sponsored children. As part of the program we started the arts and crafts activities where we provided pencils, eraser, and sharpener & color sketch pens for all the children. In the first part of the activity the children did some sketches & color filling, and then we had a discussion about the 10th class students who got good marks and we congratulated them. After that we had some story-telling and they played Indoor games. The children then collected their bus fare went to lunch and they return to their villages

June:

On June 10 2017 we conducted the PIA second Saturday program of the month; on this particular day measurements, heights & weight measurements are taken of sponsored children. Prepared new list for sponsor children by asking their School name and which class they are in, for updating in our records. We took  foot-measurements for footwear  distribution in July. They played different types of games like cricket, Coco and tennis. After that they receive their bus fare, had lunch and went to their villages.

July:

In the month of July all children’s are very happy because of bags and books distribution. On this day we took children’s Attendance registration, height and weight measurements. Distribution of books, bags, uniform, slippers and stationery was the highlight of the program, Photographs were captured for documentation. At the end of the program children received their bus fare after that child had a healthy lunch and went to their homes with their new bags etc.

August:

In this month 2nd Saturday program was carried out with three interns from Australia: Morgan, Beth and Felicity. In the first part of program Morgan took the attendance registration and Height and weight measurements, thereafter the children joined to make the beautiful paper duck, and then we distributed the required paper. Beth and Felicity helped the children in making the duck after which children had their dance performance and singing. Absentee children on uniform distribution program received their Bags and uniform. At end of the program bus fare distribution were made and children went to have their lunch.

September:

On September-9- 2017 we conducted the PIA second Saturday program of the month; as is standard procedure weights, heights and attendance was registered. On this particular day as part of program we had some story-telling and they watched a movie. After that children received their bus fare, had a healthy lunch and went to their villages happily.

October:

On 14th October we conducted the PIA second Saturday program. On this particular day regular Attendance, height and weight registrations were happen. Program was making Christmas cards for donors. For this purpose we distributed the Christmas cards which had an outline printed and the children had to color these cards for their sponsors. Thereafter we took a group photo of children for printing on Christmas card. At the end of the program children received their bus fare, had a good meal and went to their villages.

November:

On 11th November we conducted 2nd Saturday program. On this day the regular height and weight measurements were taken and registration also done. This particular day we conducted sports for the children. They played kabbadi. We divided them into 2 Groups A and Group B. Group B won the game. Measurements for Christmas were taken. At the end of the program children received their bus fare, had lunch and went to their villages.

Decmeber:

On 9th of December we conducted 2nd Saturday program. On this day the regular height and weight measurements were taken and registration also done. Measurements of absentees were taken, thereafter we conducted a singing competition among the children by dividing them into two groups later we had dumb charades activity.  Children performed well and they enjoyed it a lot. At the end of the program distribution of bus fare is made and children had their meal and went to their villages.

January:

January 1st is a very special day for our children because of clothes distribution. Before starting the program we took height & weight measurements of children then we started the program. New Christmas clothes and footwear were distributed to the children. Before and after photographs were taken for the records. After that they played, had lunch of chicken, bananas and sweets. Thereafter they received their bus fare and went home happily with new clothes and footwear.

Note books were distributed to the Thurakalapatnam primary school students. This was followed by speeches by the headmaster, teachers and SEDS staff.

February:

In the month of February the PIA second Saturday program started with attendance where we took the height & weight measurements of all the children. We then started the arts and crafts activities where we provided pencils & sketches for all the children. In the first part of the activity the lower kindergarten children did some drawings and upper kindergarten had a drawing competition in arts and crafts class. We had some story-telling and they played cricket. The children Received their bus fare and went to lunch happily.

March:

On March-10-2018 we conducted the PIA second Saturday program of the month; as is standard procedure weights, heights and attendance were registered. Music and dance were the main topic of the program. The children participated in the musical chair game for one hour, thereafter children showed their dance performances. Later we collected year 10 student’s hall ticket numbers. Children enjoyed and had fun; they received bus fare, had a meal and went home happily.

Annexure V – School Report April 2017-March 2018

SEDS SCHOOL ANANDA VIDYALAYAM

April 2017 to March 2018 - Report

April:

In the month of April all children were busy with Final exams. The final exams started on the 13th of April finished on 22nd April. Holidays were declared for the children from April 23rd to June 12th. A Parents meeting was conducted and student’s progress cards were issued to their parents. All children went home happily. Teachers cleaned the school together and discussion about school canvassing took place.

May:

In this month we had 3 days of English training classes for the Teachers by a trainer from Bangalore. Syllabus year plan, school time table were prepared and the required stationery, academic books were ordered. This year we included Tie, Belt and School diaries to the students.

June:

June month   began with canvassing our teachers had 5 days of canvassing in surrounding villages. School re-opened on 12thJune, 13 new admissions were taken in the total strength of the school was 38.

July:

In this month students got ready for their 1st unit test which was conducted on 9-14th July. In this year we had Volunteers from Australia and they gave English classes to the students. New Students have also been successfully linked up in the Government online system and the old students data was updated.

August:-

In this month student were busy in participation of Independence Day celebrations. As part of celebration we had an open day event for the first time. Students prepared projects with the help of the teachers. Bethany Morris one of the interns was the chief Guest of the program and we also invited our volunteers Morgan Downing and Felicity Biggs. Later we celebrated Independence Day with cultural activities, dance, drama and singing performance by students. We conducted games for the student and prizes were distributed to the winners and we also had a lucky drip for the students. Distribution of sweets, coffee and biscuits for the children and parents was made. After the successful completion of the celebration students were busy for their upcoming 2nd unit test.

September:-

In the month of September students had their 2nd unit test from 1st –9th September. We have made changes in the Assembly procedure as in the beginning of Assembly a Student has to read a moral story in front of the students and we also have Meditation for 5 Minutes. A new teacher has been appointed for L.K.G. Quarterly exams were conducted on 18 to 23rd September and Dasara Festival holidays were announced from 24th September to 5th October.

October:-

School re-opened on 6th October, classes were started as usual. We did arts and crafts with the children’s. A new teacher has been appointed on resignation of Math’s teachers. At the end of the month children and teachers did gardening at school.

November:

In first week of the November students were busy with their 3rd unit exams.

After successful completion of exams we celebrate children’s day on 14th November, where children performed dances and entertained all. Later we distributed sweets and biscuits to the children. Children prepared arts and crafts. Children also participated in a quiz program. On 28th November we conducted meeting with the parents where the teachers and parents share their view about the students’ performance.

December:

In this month SEDS Anandavidyalayam School and Mekalapalli Govt School children’s conducted an awareness campaign to eliminate open defecation and to stop polluting Environment.

Anandavidyalayam School children’s reached the Mekalapalli School with slogans and show cards, and then both school children’s collectively walked around the village with slogans. Thereafter group photos were taken and videos on sanitation were shown in the Mekalapalli School. Children enjoyed in the rally and they gave a good message to the village. On 12-12-2017 to 21-12-2017 we conducted Half-yearly exams and school closed for Christmas holidays.

January:

January began with classes as usual and some preparations for Republic Day celebrated on the 26thof January. Just before the republic day we conducted a drawing competition with children and the prizes for the winner was announced on Republic day.  26th republic day started with prayers and flag hoisting and singing of the national anthem. This was followed by Speeches, dances and cultural dramas. Prizes were distributed to children who participated in games and drawing competition. Children and parents were given a snack of puffed rice with sweets and biscuits as they were going home.

As classes commenced as normal the following week, the children got back to their studies.

February:-

After the activity filled month of January, February was relatively quiet with classes as usual as children prepared for their 4th unit exams which started on 26-02-2018 till 03-03-2018.

March:

On March 7 we went on a wonderful excursion, which was organized by our teachers. The trip was accompanied by 6 teachers and 32 children. We hired two mini buses. We started at 9.00 am with packs of breakfast and lunch. Children had their breakfast before visiting the places. Our trip began by walking around the Sri Sathya Sai Space Theatre which is a planetarium, which aims to give information about Astronomy, Physics, and Mathematics.We were amazed to find such a wonderful educative place. Thereafter at 11.00 am we reached ChaitanyaJyoti Museum, which houses all stories and incidents of the life of Sai Baba, all the way from his early childhood. Children were amazed and excited to see that place.  Children were thrilled to watch fish in a pond where different types of fish were seen. After that children had a break, where we distributed cool drinks. At 12.00PM we visited Sri Sathya SaiMahasamadi- this is the mausoleum of Sai Baba

After spending a great time while returning, we also visited Shiva Lingam museum about the Lord Shiva. After lunch, we reached Gollapalli reservoir where huge water was stored for catering to drinking water needs and irrigation needs even during a severe drought. Children felt happy and excited to participate in the excursion.  Snack of chips, sweets, mixture and biscuits were distributed to the children on the journey. After the successful visit to the places we reached the SEDS Campus at 5.00 pm, thereafter children returned to their home happily. After that children were busy in preparation for their final exams.

Mini bus

Inside the Mini bus

Planetarium Lobby

Planetarium Entrance

ChaitanyaJyothi Museum Entrance

Fish pond

Shiva lingam Museum Entrance

Sri Sathya Sai Mausoleum

Inside the Shiva lingam Museum

Inside the Shiva lingam Museum

Cool drinks & snacks

Back to SEDS Campus

Gollapalli Reservoir

Children at Gollapalli Reservoir

Shiva lingam Museum Entrance

Annexure VI – Old People Program report 2017-March 2018

SEDS - Old People Program (April 2017 to March 2018)

Old people living on the streets are brought to the farm and bathed, hair cut and shaves for the men, their nails are cut and feet and hands cleaned. They are given new clothes bags pouches medicines and a good chicken meal and sent back. They refuse to stay when asked.

Participants Registration for the Program

Invited old people for the Program

Hair Cutting and Shaving for the old people

Nails Cutting for the old people

Hot Baths for the old people

Distribution of Clothes for the old people

Distribution of other items (Tooth paste & Brush, Comb, Hair Oil, Vaseline, Nail cutters, Shampoo, Towels, Soaps, Medicines etc.)

Distribution of Footwear to the old people

Preparing Food for the old people

Supplying Food for the old people

Going Home