## LivePlan Advisory Checklist
Checklist Summary Details
Checklist Name | LivePlan Method for Advisory Services
Description | Advisory Services
Owner | Advisor
Expected Duration | 1 month
Workflow Status Details |  |  |  |  | Job Role Details
Workflow ID# | Workflow status name |  |  |  | Job role ID# | Job role name
1 | Kick off |  |  |  | 1 | Admin
2 | Plan |  |  |  | 2 | Analyst
3 | Model |  |  |  | 3 | Advisor
4 | Build
5 | Advise
Section 1 | Kick Off (one time per client)
Step # | Step Title | Step Description | Owner | Duration (hours) | Dependent On Step # | Due Date
1 | Set up new LivePlan license | Set up new LP Company with basic info and assign contributors | Admin | 0.25 |  | 2 days after start date
2 | Connect LivePlan to accounting solution | Connect QBO or Xero to LivePlan | Admin | 0.1 | 1 | 2 days after start date
3 | Set up Dashboard tab | Map to preliminary LivePlan data points to pull actuals | Admin | 0.5 | 2 | 2 days after start date
4 | Set up Benchmarks tab | Set up Benchmarks with appropriate variables | Admin | 0.1 | 2 | 2 days after start date
5 | Set up Pitch tab | Enter basic company info: Name, Logo, Headline, Team | Analyst | 0.3 | 1 | 2 days after start date
6 | Schedule Kick Off meeting | Set a date for Kick Off meeting and record in Milestones | Admin | 0.25 | 5 | 2 days after start date
7 | Prepare for Kick Off meeting | See resource document for Kick Off Meeting | Advisor | 0.5 | 5 | 4 days after start date
8 | Host kick-off meeting | See resource document for Kick Off Meeting | Advisor | 1 | 7 | 7 days after start date
9 | Set Plan meeting date | See resource document for Kick Off Meeting | Admin | 0 | 8 | 7 days after start date
Section 2 | Plan (one time per client)
Step # | Step Title | Step Description | Owner | Duration (hours) | Dependent On Step # | Due Date
1 | Prepare for Plan Meeting | Download Plan Meeting Resource doc | Admin | 0 |  | 10 days after start date
2 | Plan Meeting: Problem Worth Solving & Business Solution | Complete LivePlan Pitch Problem Worth Solving and Unique Solution | Advisor | 0.25 | 1 | 14 days after start date
3 | Plan Meeting: Target Market | Complete LivePlan Pitch Target Market | Advisor | 0.25 | 2 | 14 days after start date
4 | Plan Meeting: Sales Channels & Marketing Activities | Complete LivePlan Pitch Sales Channels and Marketing Activities | Advisor | 0.25 | 3 | 14 days after start date
5 | Plan Meeting: Resources: Partners, IP, Patents, long term debt | Complete LivePlan Pitch Team & Resources | Advisor | 0.25 | 4 | 14 days after start date
6 | Plan Meeting: Contractual or other Milestones | Complete LivePlan Pitch Milestones | Advisor | 0.25 | 5 | 14 days after start date
7 | Publish Pitch to secret webpage or PPT for client review | Publish Pitch to secret webpage or PPT for client review | Admin | 0.25 | 6 | 14 days after start date
Section 3 | Model (one time per client)
Step # | Step Title | Step Description | Owner | Duration (hours) | Dependent On Step # | Due Date
1 | Gather historial P&L | 12 - 36 months is ideal, in spreadsheet format | Analyst | 0.25 |  | 21 days after start date
2 | Review historicals looking for trends and ratios | Identify revenue and expense trends and averages over time | Analyst | 0.5 | 1 | 21 days after start date
3 | Compare historical data with Benchmark data | Use Benchmark data to compare company averages to benchmark | Analyst | 0.5 | 2 | 21 days after start date
4 | Establish forecasting categories | Determine LivePlan forecasting categories for Revenue, Expense | Analyst | 0.5 | 3 | 21 days after start date
5 | Determine Revenue & GM growth and Expense ratios | Determine Revenue growth percentages and Expense:Revenue | Analyst | 0.5 | 4 | 21 days after start date
6 | Gather Beginning Balances for start of company plan | Gather beginning balances for start of LivePlan Company plan | Admin | 0.3 |  | 21 days after start date
Section 4 | Build (one time per client)
Step # | Step Title | Step Description | Owner | Duration (hours) | Dependent On Step # | Due Date
1 | Enter Revenue forecast in LivePlan | Enter forecasted revenue in LivePlan | Analyst | 0.3 |  | 28 days after start date
2 | Enter Direct Costs in LivePlan | With eye on GM, enter direct costs | Analyst | 0.3 | 1 | 28 days after start date
3 | Enter Personnel in LivePlan | Use personnel to enter employee labor—or as expense item | Analyst | 0.3 | 2 | 28 days after start date
4 | Enter Expense forecast in LivePlan | Enter expense forecast using established ratios | Analyst | 0.5 | 3 | 28 days after start date
5 | Enter Assets in LivePlan | Enter assets and schedule them out | Analyst | 0.25 | 4 | 28 days after start date
6 | Enter Dividends in LivePlan | Enter dividends and schedule them out | Analyst | 0.25 | 5 | 28 days after start date
7 | Enter Tax Rates in LivePlan | Enter estimated rate for corporate and sales tax | Analyst | 0.25 | 6 | 28 days after start date
8 | Set Cash Assumptions (AR & AP Days) in LivePlan | Set cash assumptions (AR and AP days) | Analyst | 0.25 | 7 | 28 days after start date
9 | Enter Financing Needs in LivePlan | Enter any financing needs based on the forecast | Analyst | 0.25 | 8 | 28 days after start date
10 | Enter Beginning Balances in LivePlan | Enter beginning balances | Admin | 0.25 | 1 | 28 days after start date
11 | Final Mapping with new forecast categories | Final mapping with new forecast categories | Analyst | 0.5 | 10 | 28 days after start date
Section 5 | Advise (monthly per client)
Step # | Step Title | Step Description | Owner | Duration (hours) | Dependent On Step # | Due Date
1 | Confirm advisory meeting date | confirm date with client and obtain Advisory meeting resource doc | Admin | 0 |  | 30 days after start date
2 | Review LivePlan Dashboard for advisory meeting | Review Dashboard and use Advisory meeting resource document | Advisor | 1 | 1 | 30 days after start date
3 | Review Benchmark data for advisory meeting | Review Benchmarks and use Advisory meeting resource document | Advisor | 0.3 | 2 | 30 days after start date
4 | Prepare client notes for meeting | use Advisory meeting resource document for full instruction | Advisor | 0.3 | 3 | 30 days after start date
5 | Host monthly advisory meeting | use Advisory meeting resource document for full instruction | Advisor | 1.5 | 4 | 37 days after start date
6 | Send monthly meeting wrap up message - or full review if lesser package | use Advisory meeting resource document for full instruction | Advisor | 0.3 | 5 | 37 days after start date