## Work Templates
ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW
Name (required) | Description | Work Type | Fee Type | Fixed Fee (If Fixed Fee)
Client Onboarding (United States) | Start date is the date of the first onboarding meeting post-assignment of the Client Manager and the due date is 25 days later. The work assignee is the Salesperson. This is Karbon's best practice process for onboarding clients into the firm. This process is spawned on completion of the related sales process. To learn how to use this template in action, watch the following short video at: https://www.karbonhq.com/template-video/client-onboarding | Client Onboarding | Non Billable

## Work Template Tasks
ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW
Template Name (required) | Item Type (required) | Item Title (required unless automator) | Item Description | Task Assignee (required) | Task Assignee (required) | Task Assignee (required) | Due Date (+/- days after start date) | Email Sender | Email Sender | Initial Email | Initial Email | Initial Email | Reminder Email | Reminder Email | Reminder Email | Reminder Email | Automator Trigger | Automator Trigger | Automator Trigger | Automator Action | Automator Action | Automator Action | Automator Action | Automator Action | Automator Action
|  |  |  | Job Role | Colleague | Task Type |  | Type | Colleague (if type is Colleague) | Auto-send Date (+/- days after work start date) | Subject | Body | Type | Frequency (if type is Custom) | Subject | Body | Trigger Type | Trigger Specific Section (if Automator Trigger Type is Specific Section) | Trigger Status | Automator Type | Action Type | Action Status (if Automator Type is Status) | Action Job Role (if Automator Type is Assignee) | Action Colleague (if Automator Type is Assignee) | Due Date Days After Trigger (if Automator Type is Due Date)
Client Onboarding (United States) | Client Task Group | Onboarding checklist | [5 empty] | Work Assignee |  | -3 | Let's get things going with your upcoming onboarding | Hi <%preferred_name>,<BR/><BR/>Thank you for trusting us with your business. We want to make it easy for you to collaborate with us during your onboarding and throughout our ongoing relationship. As such, from time to time, you will receive emails from myself or our team containing a checklist of items. This checklist is sent to you via Karbon, the system we use to manage our jobs.<BR/><BR/>When you receive an email containing a checklist, you will be able to click the “Manage Checklist” button that will take you to a unique secure view, listing all your items that need to be completed. This view will also enable us to collaborate together to share comments and documents securely. You can also log in which will give you access to all your open and closed requests, including current client requests that haven’t been completed. You’ll also have copies of documents you have uploaded, so you can keep track and easily find what’s been sent.<BR/><BR/>If you don’t have a login, click “Log In” from the portal navigation and then click the “Create Account” button to provide your email and password.<BR/><BR/>Want a quick tutorial on how it works? <a href="https://karbonhq.wistia.com/medias/gu4w66or9u">Click here</a> to learn and watch.<BR/><BR/>With that covered, please complete the following checklist for us to get your onboarding underway. By clicking below, you can get more information, add comments or questions, and upload files. Once you have completed an item please remember to check it off so we know that it has been done. | Custom | 2 | Reminder #<%reminder_number>: Please complete these items to get your onboarding underway | Hi <%preferred_name>,<BR/><BR/>A quick reminder that some of your checklist items still need to be completed.
Client Onboarding (United States) | Client Task Group Automator | [15 empty] | All tasks in this section |  | Client Task Group - Sent to Client | Status | The work | Waiting - Waiting for info
Client Onboarding (United States) | Client Task | Please schedule your kick-off meeting at: www.calendly.com/youraccount | To get you up and running quickly, please schedule your kick-off meeting for some time in the next 2-3 days. |  |  |  | 0
Client Onboarding (United States) | Client Task | Provide the details of your prior accounting professional (if applicable) | Please provide your prior accounting professional's:&nbsp;<div>- Name:&nbsp;</div><div>- Firm Name:&nbsp;</div><div>- Email:&nbsp;</div><div>- Phone:&nbsp;</div> |  |  |  | 0
Client Onboarding (United States) | Client Task | Provide your prior year's tax return | Please provide a copy of your prior year's tax return by uploading to this checklist item. |  |  |  | 2
Client Onboarding (United States) | Section | Client kick-off (step 1)
Client Onboarding (United States) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Assignee | The work |  | Salesperson
Client Onboarding (United States) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Status | The work | In Progress - Kick-off / Setup
Client Onboarding (United States) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Status | All tasks in this section | Ready To Start
Client Onboarding (United States) | Task | Confirm all previous sales activities are complete | <b>Ensure all the following activities have been completed:&nbsp;</b><ul style=""><li style="">Onboarding working team assigned.&nbsp;<br></li><li style="">Client folder in file mgmt system has been created.&nbsp;<br></li><li style="">Engagement letter/contract signed and archived.&nbsp;<br></li><li style="">Payment authorization is complete and archived.&nbsp;<br></li><li style="">First payment has been processed.&nbsp;<br></li><li style="">Details for prior accountant have been obtained.&nbsp;<br></li><li style="">Onboarding checklist has been sent to client.&nbsp;<br></li><li style="">Welcome call has been made.&nbsp;<br></li><li style="">Kick-off meeting with client has been scheduled.&nbsp;</li></ul><div><br></div><div>Change <b><font color="#6c3b8f">work status to "Kick-off"</font></b> and <font color="#6c3b8f"><b>@ mention the Onboarding Specialist</b></font> to begin.</div> | Salesperson |  | Internal Admin | 0
Client Onboarding (United States) | Section | Client kick-off (step 2)
Client Onboarding (United States) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Assignee | The work |  | Onboarding Specialist
Client Onboarding (United States) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Status | All tasks in this section | Ready To Start
Client Onboarding (United States) | Task | Contact prior accountant, perform required client checks, and inform tax authorities (if applicable) | <div><b>If the client has a prior accounting professional, complete the following:&nbsp;</b><br></div>Contact client's prior accountant via client request for access to necessary systems, documentation, and details. Instruct accountant to upload everything needed to the client request or to the instructed client folder in your file management system. Setup auto-reminders (via client requests) to ensure timely delivery. Call prior accountant after email request has been sent to ensure prompt response.&nbsp;&nbsp;<div><div><br></div><div><div><b>If client doesn't have a prior accountant, complete the following:&nbsp;</b></div><div><ul><li>Mark this task complete&nbsp;</li><li>Delete the client request below&nbsp;</li></ul></div></div></div> | Onboarding Specialist |  | Internal Admin | 1
Client Onboarding (United States) | Client Task Group | Details needed in regards to a joint client | [5 empty] | Work Assignee |  |  | Information needed for a joint client | Hi <%preferred_name>,<BR/><BR/>Please complete the following checklist for us. By clicking below, you can get more information, add comments or questions, and upload files. Once you have completed an item please remember to check it off so we know that it has been done. | Urgent |  | Reminder #<%reminder_number>: Please complete these items in regards to <%client_name> | Hi <%preferred_name>,<BR/><BR/>A quick reminder that some of your checklist items still need to be completed.
Client Onboarding (United States) | Client Task Group Automator | [15 empty] | All tasks in this section |  | Client Task Group - Sent to Client | Status | The work | Waiting - Waiting for CPA
Client Onboarding (United States) | Client Task | Documentation / access / clarification needed: ... |  |  |  |  | 3
Client Onboarding (United States) | Section | Kick-off the engagement
Client Onboarding (United States) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Status | All tasks in this section | Ready To Start
Client Onboarding (United States) | Section Automator | [15 empty] | All sections & tasks above this section |  | Completed | Status | The work | In Progress - Kick-off / Setup
Client Onboarding (United States) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Assignee | The work |  | Onboarding Specialist
Client Onboarding (United States) | Task | Remind client of upcoming meeting (and send agenda) | Remind client to complete necessary client onboarding checklist and remind them of the upcoming kick-off meeting. Use the following text for the subject line and body of the email and send to the client. Be sure to update the [ ] sections prior to send and that the appointment is on the associated partner's calendar (plus update the partner if needed).&nbsp;<div>___________</div><div><br></div><div><b>Subject: </b>Reminder: Your kick-off meeting is just around the corner</div><div><b>Body text:</b>&nbsp;</div><div>Hi [First name],</div><div><br></div><div>Thanks for being a new client and partner of [Our firm]. We look forward to serving you now and in the future. Our first meeting to kick things off is [date/time of meeting]. Please be sure to complete the previously sent onboarding checklist. As mentioned, please be sure to either bring / send to us the following:</div><div><ul><li>[List of critical few items to bring/send]</li></ul><div><br></div></div><div>During the meeting, we will be covering the following agenda:</div><div><ul><li>[Agenda items]</li></ul></div><div><br></div><div>Again, thanks for entrusting your accounting needs with us. We look forward to working closely together over the near and long-term future.</div><div><br></div><div>Regards,</div><div>[Onboarding Specialist name]</div> | Onboarding Specialist |  | Internal Admin | 2
Client Onboarding (United States) | Task | Kick-off meeting with client, capture meeting notes below, and send follow-up requests to client | Complete the formal kick-off meeting via video conference or in-person. Review the onboarding process, current progress against the onboarding checklist, what's needed from the client, what we will provide, timing for onboard to be complete, access to systems that needs to be provided, training that will sent/given, professional clearance from prior accountant, rules of engagement, and schedule the meeting series that happens through the onboarding phase. Capture the meeting notes below. MEETING NOTES:&nbsp;<div>..... NEXT STEPS FOR US:</div><div>&nbsp;… NEXT STEPS FOR CLIENT:&nbsp;</div><div>… Use the notes from the prior task to send a client request with the client summary as the email body and to use the client requests themselves to remind them of their next steps and to schedule the next meeting. If needed, resend (or remind client to complete) client onboarding checklist if open items still exist. Remove the request for signature for power of attorney (if not needed). <div><br></div></div> | Onboarding Specialist |  | Internal Admin | 3
Client Onboarding (United States) | Client Task Group | Kickoff meeting follow-up
Client Onboarding (United States) | Client Task Group Automator | [15 empty] | All tasks in this section |  | Client Task Group - Sent to Client | Status | The work | Waiting - Waiting for client
Client Onboarding (United States) | Client Task Group Automator | [15 empty] | All tasks in the section above this section |  | Completed | Due Date | All tasks in this section |  |  |  | 2
Client Onboarding (United States) | Client Task | Please schedule next week's onboarding meeting at: www.calendly.com/youraccount |  |  |  |  | 4
Client Onboarding (United States) | Client Task | Access needed: Provide access to your various financial accounts as discussed | <div class="request-details__description__input request-details__description__input--view-mode" style="font-size: medium;">Includes financial institutions like banks and PayPal, merchant services like Stripe, and POS systems like Square and Clover.</div><div class="request-details__description__settings-icon" data-ember-action="" data-ember-action-7670="7670" style="font-size: medium; white-space: normal;"><span id="ember7671" class="fa-cog fa ember-view"></span></div> |  |  |  | 5
Client Onboarding (United States) | Client Task | Access needed: Provide access to your accounting system |  |  |  |  | 5
Client Onboarding (United States) | Client Task | Signature required: Sign and return the needed power of attorney |  |  |  |  | 5
Client Onboarding (United States) | Section | Chase for missing information
Client Onboarding (United States) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Status | All tasks in this section | Ready To Start
Client Onboarding (United States) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Assignee | The work |  | Onboarding Specialist
Client Onboarding (United States) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Status | The work | In Progress - Kick-off / Setup
Client Onboarding (United States) | Task | Receipt of read-only access to client's banking, merchant services and POS accounts | Includes financial institutions like banks and PayPal, merchant services like Stripe, and POS systems like Square and Clover. | Onboarding Specialist |  | None | 6
Client Onboarding (United States) | Task | Receipt of admin access to client's accounting system |  | Onboarding Specialist |  | None | 6
Client Onboarding (United States) | Nested Task | Receipt of all documentation and systems access from prior accountant (if applicable) |  | Onboarding Specialist |  | None | 6
Client Onboarding (United States) | Task | Weekly meeting & training (2nd week) | <div><b>Complete the following:&nbsp;</b></div><ul><li>Catch client up on current onboarding progress&nbsp;</li><li>Discuss any and all missing items&nbsp;</li><li>Take the opportunity to train the client on the firm's processes and the systems they need to use&nbsp;</li><li>Be sure to schedule the next meeting prior to ending the meeting&nbsp;<br></li><li>Send follow-up email after the meeting with what was discussed and collective next steps&nbsp;</li></ul><div><br></div><div><b>MEETING NOTES</b></div><div><ul><li>...</li></ul><div><br></div></div><div><b>NEXT STEPS:</b></div><div><ul><li>...</li></ul></div> | Onboarding Specialist |  | Internal Admin | 10
Client Onboarding (United States) | Task | Chase missing items from client | Leverage client requests to chase all the missing items needed (e.g. onboarding checklist and systems access). Leverage client requests in Karbon, canned emails in email system, or send periodic reminders to complete as quickly as possible) | Onboarding Specialist |  | None | 13
Client Onboarding (United States) | Task | Chase missing items from authorities (if applicable) | Chase the missing codes until all received. Once received, thank the client. For places like the UK, authorization from the tax authorities is required. | Onboarding Specialist |  | None | 13
Client Onboarding (United States) | Task | Send thank you gift to prior accountant (on confirmed full receipt of docs) | Upon receipt of necessary documentation from client, double-check that everything (including the full details) have been provided and send a thank you gift to build a future relationship. | Onboarding Specialist |  | None | 13
Client Onboarding (United States) | Task | Archive onboarding checklist and legal docs | Upon receipt, save onboarding checklist and legal docs to client folder in file management system and in Karbon. Once everything is complete, <b><font color="#6c3b8f">change work status to "Prep"</font></b> and <b><font color="#6c3b8f">@ mention the Admin</font></b> to complete the system setup.. | Onboarding Specialist |  | Internal Admin | 14
Client Onboarding (United States) | Section | Prep systems
Client Onboarding (United States) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Status | All tasks in this section | Ready To Start
Client Onboarding (United States) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Assignee | The work |  | Admin
Client Onboarding (United States) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Status | The work | In Progress - Prep
Client Onboarding (United States) | Task | Create client profile and fill out client details in Karbon | Using the information collected previously, fully populate the CRM & accounting details for your client in Karbon. | Admin |  | None | 15
Client Onboarding (United States) | Task | Invite client into firm's backend systems | Send client invitations to join the necessary systems for the engagement. This might include collaboration tools, file management,&nbsp;expense app, bookkeeping app, time tracking,&nbsp;accounting/payroll software and more. | Admin |  | None | 15
Client Onboarding (United States) | Task | Access accounting system and conduct necessary prep work |  | Admin |  | None | 15
Client Onboarding (United States) | Task | Setup client invoice schedule & autodraft (if applicable) | Create recurring invoice in accounting system, setup autodraft, and send client autodraft link to complete checkout. | Admin |  | None | 15
Client Onboarding (United States) | Section | Prep (step 1: Financials)
Client Onboarding (United States) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Status | All tasks in this section | Ready To Start
Client Onboarding (United States) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Assignee | The work |  | Onboarding Specialist
Client Onboarding (United States) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Status | The work | In Progress - Prep
Client Onboarding (United States) | Task | Create & review client's financial reports | Review prior year's Profit & Loss and Balance Sheet to get an understanding of where things are at. | Onboarding Specialist |  | None | 16
Client Onboarding (United States) | Task | Reassess scope of project | Review engagement letter in conjunction with the state of affairs of the financials. If a mismatch (e.q. requires major clean-up), complete a change order request with the client. Depending on the change, either continue the process or create a new piece of work for a major clean up and mark this process as complete. | Onboarding Specialist |  | None | 16
Client Onboarding (United States) | Task | Weekly meeting & training (3rd week) | Catch client up on current onboarding progress, missing items, and take the opportunity to train the client on the firm's processes and the systems they need to use.<div><br></div><div><b><font color="#6c3b8f">@ mention the Accountant</font></b> to take next step.</div> | Onboarding Specialist |  | Internal Admin | 17
Client Onboarding (United States) | Section | Prep (step 2: Working GL)
Client Onboarding (United States) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Status | All tasks in this section | Ready To Start
Client Onboarding (United States) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Assignee | The work |  | Accountant
Client Onboarding (United States) | Task | Create working GL file | Reconcile as needed, update Chart of Accounts, perform minor clean up. If a major clean-up is required, create a new piece of work once change order has been signed and returned.&nbsp;<div><br></div><div>On completion, <b><font color="#6c3b8f">@ mention the Onboarding Specialist</font></b>.</div> | Accountant |  | Internal Admin | 20
Client Onboarding (United States) | Section | Prep (step 3: Workflow)
Client Onboarding (United States) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Assignee | The work |  | Onboarding Specialist
Client Onboarding (United States) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Status | All tasks in this section | Ready To Start
Client Onboarding (United States) | Task | Customize workflow(s) to client specific needs | For all client services agreed to, create work from the workflow templates available and customize to fit the client needs. | Onboarding Specialist |  | Internal Admin | 20
Client Onboarding (United States) | Task | Review (and get approval) of financials and workflow processes with Partner | For the financials and workflows prepped, review with the Partner and get sign-off to show and walk-through with the client.<div><br></div><div>Once complete, <b><font color="#6c3b8f">change the work status to "Review &amp; advise"</font></b> and send the following client request to schedule the final onboarding meeting.</div> | Onboarding Specialist |  | Internal Admin | 21
Client Onboarding (United States) | Client Task Group | Schedule review meeting
Client Onboarding (United States) | Client Task Group Automator | [15 empty] | All tasks in this section |  | Client Task Group - Sent to Client | Status | The work | Waiting - Waiting for client 2
Client Onboarding (United States) | Client Task Group Automator | [15 empty] | All tasks in the section above this section |  | Completed | Due Date | All tasks in this section |  |  |  | 0
Client Onboarding (United States) | Client Task | Please schedule your onboarding review meeting at: www.calendly.com/youraccount |  |  |  |  | 21
Client Onboarding (United States) | Section | Review & advise
Client Onboarding (United States) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Assignee | The work |  | Onboarding Specialist
Client Onboarding (United States) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Status | All tasks in this section | Ready To Start
Client Onboarding (United States) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Status | The work | In Progress - Review
Client Onboarding (United States) | Task | Remind of review meeting (and send agenda) | Confirm review meeting and send meeting agenda. | Onboarding Specialist |  | Internal Admin | 23
Client Onboarding (United States) | Task | Conduct final onboarding review meeting | <div><div class="task-details__description__input task-details__description__input--view-mode" style="font-size: medium;">Prepare the presentation, agenda, and talking points for the review meeting.</div></div><div><br></div><div>Present the financials (P&amp;L, Balance Sheet), systems setup, processes to follow and provide training on what it means and where things go from here. Discuss KPIs that will be reviewed each month. Ask questions that still need answers, and answers questions the client might have.<br></div><div><br></div><div><div class="task-details__description__input task-details__description__input--view-mode" style="font-size: medium;">Debrief with team on meeting summary, outcomes and lessons learned. Create or update all ongoing work, workflows, KPIs and engagement details per client discussion. Move Karbon work into recurring status once updated. Fill out all notes on client timeline.</div></div><div><br></div>Once complete, <b><font color="#6c3b8f">change work status to "Follow-up"</font></b> and <b><font color="#6c3b8f">@ mention the Salesperson</font></b> on completion for engagement follow-up. | Onboarding Specialist |  | Internal Admin | 24
Client Onboarding (United States) | Section | Follow-up
Client Onboarding (United States) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Status | All tasks in this section | Ready To Start
Client Onboarding (United States) | Section Automator | [15 empty] | All tasks in this section |  | Completed | Status | The work | Completed
Client Onboarding (United States) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Assignee | The work |  | Salesperson
Client Onboarding (United States) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Status | The work | In Progress - Follow-up
Client Onboarding (United States) | Task | Conduct post-review meeting call | Call client immediately after onboarding is complete to:&nbsp;<div>1) Give thanks&nbsp;</div><div>2) Administer the NPS/satisfaction survey&nbsp;</div><div>3) Get a testimonial / referral / rating / review</div> | Salesperson |  | Internal Admin | 25
Client Onboarding (United States) | Task | Send gift pack out to client | Send the new client thank you gift to client. Once complete, <b><font color="#6c3b8f">change the work status to "Completed"</font></b>. | Salesperson |  | Internal Admin | 25

## Work Template Estimates
ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW
Template Name (not updatable) | Budget Estimate | Budget Estimate | Budget Estimate | Budget Estimate | Budget Estimate
| Job Role (required) | Team Member | Task Type (required) | Hourly Rate (blank for default) | Estimated Time (mins)
Client Onboarding (United States) | Onboarding Specialist |  | Internal Admin |  | 480
Client Onboarding (United States) | Salesperson |  | Internal Admin |  | 60
Client Onboarding (United States) | Accountant |  | Internal Admin |  | 120
Client Onboarding (United States) | Admin |  | Internal Admin |  | 120

## ReferenceData (hidden)
Planned
Ready To Start
In Progress
Waiting
Completed
Public
Private
Hidden
Afghanistan
Albania
Algeria
American Samoa
Andorra
Angola
Anguilla
Antarctica
Antigua and Barbuda
Argentina
Armenia
Aruba
Australia
Austria
Azerbaijan
Bahamas
Bahrain
Bangladesh
Barbados
Belarus
Belgium
Belize
Benin
Bermuda
Bhutan
Bolivia
Bosnia and Herzegovina
Botswana
Bouvet Island
Brazil
British Indian Ocean Territory
Brunei Darussalam
Bulgaria
Burkina Faso
Burundi
Cambodia
Cameroon
Canada
Cape Verde
Cayman Islands
Central African Republic
Chad
Chile
China
Christmas Island
Cocos (Keeling) Islands
Colombia
Comoros
Congo
Congo, the Democratic Republic of the
Cook Islands
Costa Rica
Cote D'Ivoire
Croatia
Cuba
Cyprus
Czech Republic
Denmark
Djibouti
Dominica
Dominican Republic
Ecuador
Egypt
El Salvador
England
Equatorial Guinea
Eritrea
Estonia
Ethiopia
Falkland Islands (Malvinas)
Faroe Islands
Fiji
Finland
France
French Guiana
French Polynesia
French Southern Territories
Gabon
Gambia
Georgia
Germany
Ghana
Gibraltar
Greece
Greenland
Grenada
Guadeloupe
Guam
Guatemala
Guinea
Guinea-Bissau
Guyana
Haiti
Heard Island and Mcdonald Islands
Holy See (Vatican City State)
Honduras
Hong Kong
Hungary
Iceland
India
Indonesia
Iran, Islamic Republic of
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Korea, Democratic People's Republic of
Korea, Republic of
Kuwait
Kyrgyzstan
Lao People's Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Macao
Macedonia, the Former Yugoslav Republic of
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Martinique
Mauritania
Mauritius
Mayotte
Mexico
Micronesia, Federated States of
Moldova, Republic of
Monaco
Mongolia
Montserrat
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
Netherlands Antilles
New Caledonia
New Zealand
Nicaragua
Niger
Nigeria
Niue
Norfolk Island
Northern Ireland
Northern Mariana Islands
Norway
Oman
Pakistan
Palau
Palestinian Territory, Occupied
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Pitcairn
Poland
Portugal
Puerto Rico
Qatar
Reunion
Romania
Russian Federation
Rwanda
Saint Helena
Saint Kitts and Nevis
Saint Lucia
Saint Pierre and Miquelon
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Scotland
Senegal
Serbia and Montenegro
Seychelles
Sierra Leone
Singapore
Skype
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
South Georgia and the South Sandwich Islands
Spain
Sri Lanka
Sudan
Suriname
Svalbard and Jan Mayen
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Taiwan, Province of China
Tajikistan
Tanzania, United Republic of
Thailand
Timor-Leste
Togo
Tokelau
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Turks and Caicos Islands
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom
United States Minor Outlying Islands
Uruguay
USA
Uzbekistan
Vanuatu
Venezuela
Viet Nam
Virgin Islands, British
Virgin Islands, U.s.
Wales
Wallis and Futuna
Western Sahara
Yemen
Zambia
Zimbabwe
Administrator
Restricted User
User
Custom
Gentle
Urgent
Client Owner
Colleague
Work Assignee
Fixed Fee
Non Billable
Time and Materials
Planned
Ready To Start
Ready To Start - Send client requests
Ready To Start - Resend client requests
Ready To Start - Ready for Accounting
Ready To Start - Ready for Tax
In Progress
In Progress - Extension Needed
In Progress - Extension Filed
In Progress - Kick-off / Setup
In Progress - Prep
In Progress - Process
In Progress - Review
In Progress - Revise
In Progress - Final review
In Progress - Advise
In Progress - Assemble
In Progress - File
In Progress - Lodge
In Progress - Follow-up
In Progress - Send payroll to client
In Progress - Finalise payroll process
Waiting
Waiting - Waiting engagement letter
Waiting - Waiting for info
Waiting - Waiting for CPA
Waiting - Waiting for CPA/CA
Waiting - Waiting for client
Waiting - Waiting for client 2
Waiting - Waiting for auditor
Waiting - Waiting for signature
Waiting - Waiting for IRS
Waiting - Waiting for CRA
Waiting - Waiting for ATO
Waiting - Waiting for IRD
Waiting - Waiting for HMRC
Waiting - Waiting for Gov't
Waiting - Waiting for confirmation
Waiting - Extended
Waiting - Wait for payment confirm
Completed
Completed - Not applicable
Completed - Billed
Completed - Not a fit
Completed - Closed lost
Completed - Closed won
Completed - Cancelled
Planned
Ready To Start
Ready To Start - Send client requests
Ready To Start - Resend client requests
Ready To Start - Ready for Accounting
Ready To Start - Ready for Tax
In Progress
In Progress - Extension Needed
In Progress - Extension Filed
In Progress - Kick-off / Setup
In Progress - Prep
In Progress - Process
In Progress - Review
In Progress - Revise
In Progress - Final review
In Progress - Advise
In Progress - Assemble
In Progress - File
In Progress - Lodge
In Progress - Follow-up
In Progress - Send payroll to client
In Progress - Finalise payroll process
Waiting
Waiting - Waiting engagement letter
Waiting - Waiting for info
Waiting - Waiting for CPA
Waiting - Waiting for CPA/CA
Waiting - Waiting for client
Waiting - Waiting for client 2
Waiting - Waiting for auditor
Waiting - Waiting for signature
Waiting - Waiting for IRS
Waiting - Waiting for CRA
Waiting - Waiting for ATO
Waiting - Waiting for IRD
Waiting - Waiting for HMRC
Waiting - Waiting for Gov't
Waiting - Waiting for confirmation
Waiting - Extended
Waiting - Wait for payment confirm
Completed
Completed - Not applicable
Completed - Billed
Completed - Not a fit
Completed - Closed lost
Completed - Closed won
Completed - Cancelled
Client Task Group - Sent to Client
1 | Advertising
1 | Commission
1 | E-Commerce
1 | Fee for Service
1 | Licensing
1 | Markup
1 | Production
1 | Subscription
2 | Advertising
2 | Commission
2 | E-Commerce
2 | Fee for Service
2 | Licensing
2 | Markup
2 | Production
2 | Subscription
3 | Advertising
3 | Commission
3 | E-Commerce
3 | Fee for Service
3 | Licensing
3 | Markup
3 | Production
3 | Subscription
4 | Advertising
4 | Commission
4 | E-Commerce
4 | Fee for Service
4 | Licensing
4 | Markup
4 | Production
4 | Subscription
5 | Advertising
5 | Commission
5 | E-Commerce
5 | Fee for Service
5 | Licensing
5 | Markup
5 | Production
5 | Subscription
6 | Advertising
6 | Commission
6 | E-Commerce
6 | Fee for Service
6 | Licensing
6 | Markup
6 | Production
6 | Subscription
7 | Advertising
7 | Commission
7 | E-Commerce
7 | Fee for Service
7 | Licensing
7 | Markup
7 | Production
7 | Subscription
8 | Advertising
8 | Commission
8 | E-Commerce
8 | Fee for Service
8 | Licensing
8 | Markup
8 | Production
8 | Subscription
9 | Advertising
9 | Commission
9 | E-Commerce
9 | Fee for Service
9 | Licensing
9 | Markup
9 | Production
9 | Subscription
10 | Advertising
10 | Commission
10 | E-Commerce
10 | Fee for Service
10 | Licensing
10 | Markup
10 | Production
10 | Subscription
11 | Advertising
11 | Commission
11 | E-Commerce
11 | Fee for Service
11 | Licensing
11 | Markup
11 | Production
11 | Subscription
12 | Advertising
12 | Commission
12 | E-Commerce
12 | Fee for Service
12 | Licensing
12 | Markup
12 | Production
12 | Subscription
13 | Advertising
13 | Commission
13 | E-Commerce
13 | Fee for Service
13 | Licensing
13 | Markup
13 | Production
13 | Subscription
14 | Advertising
14 | Commission
14 | E-Commerce
14 | Fee for Service
14 | Licensing
14 | Markup
14 | Production
14 | Subscription
15 | Advertising
15 | Commission
15 | E-Commerce
15 | Fee for Service
15 | Licensing
15 | Markup
15 | Production
15 | Subscription
16 | Advertising
16 | Commission
16 | E-Commerce
16 | Fee for Service
16 | Licensing
16 | Markup
16 | Production
16 | Subscription
17 | Advertising
17 | Commission
17 | E-Commerce
17 | Fee for Service
17 | Licensing
17 | Markup
17 | Production
17 | Subscription
18 | Advertising
18 | Commission
18 | E-Commerce
18 | Fee for Service
18 | Licensing
18 | Markup
18 | Production
18 | Subscription
1 | Accruals
1 | Cash
1 | None
2 | Accruals
2 | Cash
2 | None
3 | Accruals
3 | Cash
3 | Flat Rate Accrual
3 | Flat Rate Cash
3 | None
4 | Invoice
4 | None
4 | Payments
5 | Accruals
5 | Cash
5 | None
6 | Accruals
6 | Cash
8 | Débit
8 | Encaissements
10 | Accrual
10 | Cash Receipts
15 | Accruals
15 | Cash
15 | None
16 | Accruals
16 | Cash
16 | None
17 | Accruals
17 | Cash
17 | Flat Rate Accrual
17 | Flat Rate Cash
17 | None
18 | Accruals
18 | Cash
1 | Annually
1 | Monthly
1 | Six Monthly
1 | Three Monthly
1 | Two Monthly
2 | Annually
2 | Monthly
2 | Quarterly (Option 1)
2 | Quarterly (Option 2)
2 | Quarterly (Option 3)
3 | Monthly
3 | Quarterly
3 | Yearly
4 | Monthly
4 | Six Monthly
4 | Two Monthly
5 | Annually
5 | Annually (Quarterly Instalments)
5 | Monthly
5 | None
5 | Quarterly
5 | Six Monthly
6 | Monthly
6 | Three Monthly
6 | Two Monthly
8 | Bi-Annually
8 | Monthly
8 | Quarterly
10 | Bimonthly
10 | Four monthly
10 | Not Registered
10 | Six monthly
10 | Yearly
15 | Monthly
15 | Quarterly
15 | Yearly
16 | Each Semester
16 | Monthly
16 | Quarterly
16 | Yearly
17 | Monthly
17 | Quarterly
17 | Yearly
18 | Monthly
18 | Three Monthly
18 | Two Monthly
1 | Other
1 | Products
1 | Products and Services
1 | Services
2 | Other
2 | Products
2 | Products and Services
2 | Services
3 | Other
3 | Products
3 | Products and Services
3 | Services
4 | Other
4 | Products
4 | Products and Services
4 | Services
5 | Other
5 | Products
5 | Products and Services
5 | Services
6 | Other
6 | Products
6 | Products and Services
6 | Services
7 | Other
7 | Products
7 | Products and Services
7 | Services
8 | Other
8 | Products
8 | Products and Services
8 | Services
9 | Other
9 | Products
9 | Products and Services
9 | Services
10 | Other
10 | Products
10 | Products and Services
10 | Services
11 | Other
11 | Products
11 | Products and Services
11 | Services
12 | Other
12 | Products
12 | Products and Services
12 | Services
13 | Other
13 | Products
13 | Products and Services
13 | Services
14 | Other
14 | Products
14 | Products and Services
14 | Services
15 | Other
15 | Products
15 | Products and Services
15 | Services
16 | Other
16 | Products
16 | Products and Services
16 | Services
17 | Other
17 | Products
17 | Products and Services
17 | Services
18 | Other
18 | Products
18 | Products and Services
18 | Services
1 | Monthly
1 | Quarterly
1 | Yearly
2 | Monthly
2 | Quarterly
2 | Yearly
3 | Monthly
3 | Quarterly
3 | Yearly
4 | Monthly
4 | Quarterly
4 | Yearly
5 | Monthly
5 | Quarterly
5 | Yearly
6 | Monthly
6 | Quarterly
6 | Yearly
7 | Monthly
7 | Quarterly
7 | Yearly
8 | Monthly
8 | Quarterly
8 | Yearly
9 | Monthly
9 | Quarterly
9 | Yearly
10 | Monthly
10 | Quarterly
10 | Yearly
11 | Monthly
11 | Quarterly
11 | Yearly
12 | Monthly
12 | Quarterly
12 | Yearly
13 | Monthly
13 | Quarterly
13 | Yearly
14 | Monthly
14 | Quarterly
14 | Yearly
15 | Monthly
15 | Quarterly
15 | Yearly
16 | Monthly
16 | Quarterly
16 | Yearly
17 | Monthly
17 | Quarterly
17 | Yearly
18 | Monthly
18 | Quarterly
18 | Yearly
1 | Club or Society
1 | Corporation
1 | Estate or Trust
1 | Exempt Organization
1 | Limited Liability
1 | Other/None
1 | Partnership
1 | Person
1 | Private Foundation
1 | S Corporation
1 | Sole Proprietor
2 | Club or Society
2 | Company
2 | Not for Profit
2 | Partnership
2 | Person
2 | Self Managed Superannuation Fund
2 | Sole Proprietor
2 | Superannuation Fund
2 | Trust
3 | Club or Society
3 | Company
3 | Housing Association
3 | Limited Company
3 | Look Through Company
3 | Not for Profit
3 | Partnership
3 | Person
3 | Sole Proprietor
3 | Trust
3 | Unincorporated Charity
4 | Charity
4 | Club or Society
4 | Company
4 | Look-Through Company
4 | Partnership
4 | Person
4 | Sole Proprietor
4 | Trust
5 | Club or Society
5 | Corporation
5 | Not for Profit
5 | Partnership
5 | Person
5 | Sole Proprietorship
5 | Trust
6 | Closed Corporation
6 | Club/Society or Religious Organisation
6 | Company
6 | Individual
6 | Non Profit Company
6 | Non Profit Organisation
6 | Partnership
6 | Sole Proprietor
6 | Trust
7 | Charity Limited Liability Company
7 | Foreign Company Office
7 | General Partnership
7 | Limited Partnership
7 | Private Limited Liability Company
7 | Public Limited Liability Company
7 | Sole Proprietorship
7 | Unlimited Company
8 | Bénéfices Non Commerciaux
8 | Entreprise individuelle
8 | Entreprise individuelle à responsabilité limitée
8 | Entreprise Unipersonnelle à Responsabilité Limitée
8 | Groupement d'Intérêt Economique
8 | Lureur Meublé Non Professionnel
8 | Société à Responsabilité Limitée
8 | Société Civile de Moyens
8 | Société Civile Immobilière
8 | Société d'Exercice Libéral à Responsabilité Limitée
8 | Société d'Exercice Libéral par Actions Simplifiée
8 | Société par Actions Simplifiée Unipersonnelle
8 | Société par Actions Simplifiées
9 | Company
9 | General Partnership
9 | Limited Liability Partnership
9 | Limited Partnership
9 | Private Limited Liability Company
9 | Public Limited Liability Company
9 | Sole Proprietorship
10 | Association
10 | Club Charity
10 | Company Limited by Guarantee
10 | Company Limited by Shares
10 | Designated Activity Company
10 | Dormant
10 | Foundation
10 | Limited Liability Partnership
10 | Partnership
10 | Public Limited
10 | Societas Europaea
10 | Sole Trade
10 | SSAP
10 | Trust
10 | Unlimited Liability Company
11 | Individual
11 | Limited Partnership
11 | Partnership
11 | Private Limited Liability
11 | Public Limited Liability
11 | Sole proprietor
12 | Cooperation Association
12 | Limited Company
12 | Limited Partnership
12 | Partnership
12 | Proprietorship
13 | General Partnership
13 | Limited Partnership
13 | Private Limited Company
13 | Public Limited Company
13 | Sole Proprietorship
14 | Club or Society
14 | Limited Company
14 | Look Through Company
14 | Not for Profit
14 | Partnership
14 | Person
14 | Sole Proprietor
14 | Trust
15 | Association of Persons (AoP)
15 | Bank
15 | Body of Individuals (BoI)
15 | Limited Liability Partnership (LLP)
15 | One Person Company (OPC)
15 | Other
15 | Partnership Firm
15 | Private Limited
15 | Public Limited
15 | Sole Proprietorship
15 | Trust
16 | Independent
16 | Société à Responsabilité Limitée
16 | Société Anonyme
16 | Société Coopérative
17 | Associazione non riconosciuta
17 | Associazione riconosciuta
17 | Fondazione
17 | Impresa individuale
17 | Persona
17 | Professionista
17 | Società a responsabilità limitata semplificata, S.r.l.s.
17 | Società a responsabilità limitata, S.r.l.
17 | Società in Accomandita per Azioni (sapa)
17 | Società In Accomandita Semplice
17 | Società in Nome Collettivo
17 | Società per azioni (S.p.A.)
17 | Società Semplice
17 | Societas Europaea
18 | Association
18 | Church
18 | Closed Company
18 | Individual
18 | Private Company Limited By Guarantee
18 | Private Company Limited By Shares
18 | School
18 | Society
18 | Trust
No Action
Create
No Action
Update
Delete
No Action
Create
No Action
Update
No Action
Create
No Action
Delete
No Action
Create
No Action
Update
Delete
No Action
Create
No Action
Update
Delete
No Action
Create
No Action
Update
No Action
Create
No Action
Delete
No Action
Create
No Action
Update
Delete
No Action
Create
No Action
Update
Delete
No Action
Create
No Action
Delete
No Action
Create
No Action
Update
No Action
Create
No Action
Update
Delete
No Action
Create
No Action
Delete
No Action
Create
No Action
Update
Delete
No Action
Create
No Action
Update
No Action
Create
No Action
Update
Delete
No Action
Create
No Action
Update
Delete
No Action
Create
No Action
Delete
No Action
Create
No Action
Update
Delete
No Action
Create
No Action
Update
Delete
No Action
Create
No Action
Update
Delete

## Composite Statuses (hidden)
Formula
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!