## Sheet1
Checklist Summary Details | [5 empty] | © 2018 Karbon
Checklist Name | Prospect to sale (GoProposal red carpet treatment)
Description | GoProposal + Karbon best practice template for moving a prospect to a sale (red carpet treatment). Learn more on the process at: http://bit.ly/2EoQC1W. This process assumes that marketing activity has been spawned from referral, inbound and outbound marketing activities. Once the lead is received (by Admin or BDM), a new piece of work from this process template is created.
Owner | Salesperson
Expected Duration | 2 weeks
Workflow Status Details (in addition to major categories of Planned, In Progress, Waiting, and Completed) |  |  |  |  | Job Role Details
Workflow ID# | Workflow status name |  |  |  | Job role ID# | Job role name
1 | In Progress (MQL) |  |  |  | 1 | Admin
2 | In Progress (SQL) |  |  |  | 2 | Salesperson
3 | In Progress (Sale) |  |  |  | 3 | Closer
4 | Waiting (Waiting for client) |  |  |  | 4 | Onboarding Specialist
5 | Completed (Not a fit)
6 | Completed (Closed lost)
7 | Completed (Closed won)
8 | Completed (Cancelled)
Section 1 | Marketing qualified lead (MQL)
Step # | Step Title | Step Description | Owner | Duration (hours) | Dependent On Step # | Due Date
0 | Auto-email sent to prospect | Depending on the marketing channel used by the prospect, an automatically generated email from the salesperson is sent thanking them for their interest and directing them to schedule a Discovery video call via a calending app (e.g. Calendly). | Admin | 0 |  | 0 days after start date
1 | Update work status to "MQL" | Whoever is the owner of a new marketing lead, either automatically or manually set work status to "MQL" and @ mention the salesperson. Ensure the proper creation of the contact in Karbon and create/modify work & checklist as needed. | Admin | 0 | 0 | 0 days after start date
2 | Review and qualify lead for size, fit and prioritization | Do background research on the marketing qualified lead (MQL) to get basic contact details and context on the business or individual. Try to determine the firm's size, revenue, industry, maturity plus owner characteristcs. Use those facts to complete your firm's prospect qualification process to prioritize based on opportunity size and fit. This information will also be used in the nurturing process including their name, title, logo, and business details. | Admin | 0.5 | 1 | 0 days after start date
3 | Update sales opportunity, prioritize and take action | If an opportunity worth pursuing, create a sales qualified lead (SQL) by completing your firm's SQL checklist and updating the expected close date, priority, and changing work status to "SQL". Follow-up with the prospect (cc: Salesperson) to either a) book a Discovery call and point them to the online calendar for the assigned Salesperson or b) remind them via email and text of the upcoming meeting. @ mention the assigned Salesperson to ensure the prospect schedules a Discovery meeting. If not an opportunity worth pursuing, send a thank you email, introduce them to a firm that can help and mark this opportunity (piece of work) as "Completed (Not a fit)". | Admin | 0.25 | 2 | 0 days after start date
Section 2 | Sales qualified lead (SQL)
Step # | Step Title | Step Description | Owner | Duration (hours) | Dependent On Step # | Due Date
4 | Prime the prospect (pre-discovery video call) | Send short personalized, automated videos outlining the purpose of the call and what to expect. | Salesperson | 0.25 | 3 | 0 days after start date
5 | Conduct scripted Discovery video call | Conduct the virtual Discovery meeting via video conference to assess the client situation, have the value conversation. Use a script and ensure mutual alignment. At the very least, the Proposal meeting must be booked on the collective calendars (prospect and firm owner) prior to the prospect leaving the meeting. Take notes and @ mention the Closer as an FYI. If not a fit, send a thank you email, introduce them to another firm that can assist, and mark status as "Closed (not a fit)". | Salesperson | 0.5 | 4 | 3 days after start date
6 | Prime the prospect (pre-Proposal meeting) | Send a series of time-spaced emails to prime the prospect including: - Email confirmation on the proposal meeting with intro to the assigned staff handling the close and request to access their accounts ahead of the meeting - Send a short, personalized video from the Closer (firm owner/partner) outlining the agenda for the Proposal meeting, who the firm is, who you've helped, your process and your track record with others. - Send out a sales brochure to the prospect prior to the meeting - Send a short, automated video via email explaining where to come to and confirm the agenda (reminder email) - Send a text message the day/night prior to the Proposal meeting with the meeting time, address and directions | Salesperson | 0.25 | 5 | 6 days after start date
7 | Prepare for prospect (day of Proposal meeting) | Prepare the office location and staff for the prospect's visit: - Brief the entire team on who is visiting (name, business, and remind them to say hi when they are in the office) - Update carpark sign and welcome signs with prospect's name and welcome message - Prepare the meeting room for the meeting and prospect | Salesperson | 0.5 | 6 | 7 days after start date
8 | Conduct the 1:1 Proposal meeting | On entry to the office, have the office team great them when arrive. Take them to the conference room and present a drink menu to choose from. In the meeting and using the fact finding details, discovery meeting notes, and primer materials, listen to the prospects' needs (and top three objections), give them value (education / free advice), have the value conversation, present packages and pricing, AND build/produce a proposal and letter of engagement in the Proposal meeting via GoProposal. Try to get it signed in the meeting if possible. If it is signed, mark the work status as "Sale" and skip to the step after the signed engagement letter within this process. If a signed proposal is not achieved, agree for a follow-up video call and get it booked on the collective calendars prior to the conclusion of the meeting. When appropriate in the meeting, present them with a useful book to thank them for their time. | Closer | 1.5 | 7 | 7 days after start date
9 | Follow-up email (post Proposal meeting) | Immediately after the Proposal meeting, send an email with a screen capture video of the proposal for their review and consideration. | Closer | 0.25 | 8 | 7 days after start date
10 | Remove prospect's objections | After the Proposal meeting, send a series of time-spaced emails (with videos if possible) that address the prospect's three main objectives (typically price, switching accountants, and trusting your firm can deliver) using pre-created client case study videos. This is leading up to the follow-up call. | Closer | 0.5 | 9 | 10 days after start date
11 | Follow-up call with prospect | Conduct the pre-determined follow-up call. If the call was successful, use GoProposal to get the client's signature, trigger on the appropriate workflows in Karbon for the work to be completed, prepare the appropriate engagement letter, mark work status as "Sale", and @ mention the salesperson to close the sale. In Karbon, be sure to assign the right people to right roles for the new work. @ mention the Client Manager to set up and complete the Welcome call. If the meeting was unsuccessful, mark down lessons learned, mark work status as "Completed (Closed Lost)", and @ mention the salesperson as an FYI. Close out the proposal in GoProposal as well. | Closer | 0.5 | 10 | 11 days after start date
Section 3 | Move from sale to pre-onboarding
Step # | Step Title | Step Description | Owner | Duration (hours) | Dependent On Step # | Due Date
12 | Send engagement letter and payment authorization form | Email client their engagement letter and payment authorization form. Change work status to "Waiting for client". If signed engagement letter hasn't been received (or no contact is made), follow-up at least every day (or few days) to keep the process moving. Once received in full, mark the work status as "Sale". If the opportunity goes dark or client objects, mark work status as "Completed (Closed lost)". | Salesperson | 1 | 11 | 11 days after start date
13 | Complete Welcome call | Call the new client to: - Introduce oneself - Introduce the onboarding checklist (send it to them in the meeting) - Gain permission to contact prior accountant (plus details) - Gain permission to make a social media announcement - Gain permission to get a testimonial on successful completion of work - Book onboarding 1:1 meeting | Onboarding Specialist | 0.5 | 12 | 14 days after start date
14 | Send thank you email | Send standard thank you email that outlines the onboarding process, recaps what was said in the Welcome call, and reminds them to complete the onboarding checklist and of the upcoming Onboarding meeting. | Onboarding Specialist | 0.25 | 13 | 14 days after start date
15 | Process payment for services and spawn onboarding work | Create sales receipt and process payment (per agreed fee schedule). Create onboarding work in Karbon, assign owners to key job roles, @ mention salesperson of completion of sale, and mark work status as "Completed (Closed won)". | Onboarding Specialist | 0.25 | 14 | 14 days after start date