## Work Templates
ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW
Name (required) | Description | Work Type | Fee Type | Fixed Fee (If Fixed Fee)
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | The start date is the date the engagement is signed The due date is 28 days later The initial assignee is the Onboarding Specialist This is Karbon's best practice process for onboarding clients into the firm when using integrated apps GoProposal and Xama. The work template will be generated once a proposal is signed for a new client. | Onboarding | Non Billable

## Work Template Tasks
ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW
Template Name (required) | Item Type (required) | Item Title (required unless automator) | Item Description | Task Assignee (required) | Task Assignee (required) | Task Assignee (required) | Due Date (+/- days after start date) | Email Sender | Email Sender | Initial Email | Initial Email | Initial Email | Reminder Email | Reminder Email | Reminder Email | Reminder Email | Automator Trigger | Automator Trigger | Automator Trigger | Automator Action | Automator Action | Automator Action | Automator Action | Automator Action | Automator Action
|  |  |  | Job Role | Colleague | Task Type |  | Type | Colleague (if type is Colleague) | Auto-send Date (+/- days after work start date) | Subject | Body | Type | Frequency (if type is Custom) | Subject | Body | Trigger Type | Trigger Specific Section (if Automator Trigger Type is Specific Section) | Trigger Status | Automator Type | Action Type | Action Status (if Automator Type is Status) | Action Job Role (if Automator Type is Assignee) | Action Colleague (if Automator Type is Assignee) | Due Date Days After Trigger (if Automator Type is Due Date)
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Section | Confirm sales activities completed and setup onboarding and client team
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Section Automator | [15 empty] | The work |  | Ready To Start | Status | All tasks in this section | Ready To Start
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Section Automator | [15 empty] | All tasks in this section |  | Ready To Start | Assignee | The work |  | Partner
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Section Automator | [15 empty] | All tasks in this section |  | Ready To Start | Status | The work | In Progress - Kick-off / Setup
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Task | Confirm all previous sales activities are complete | <b>Ensure all the following activities have been completed:&nbsp;</b><ul style=""><li style="">Engagement letter/contract signed and added to the Contact timeline and pinned for easy reference by any team member.&nbsp;<br></li><li style="">Payment authorisation is complete and the first payment has been processed. If not add this to the kick-off meeting agenda task below.</li><li style="">Kick-off meeting with client has been scheduled. Automatic reminders will be sent on the client task above until this is completed.</li></ul> | Partner |  | Internal Admin | 0
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Task | Setup onboarding and client team | <ul><li>Onboarding work team assigned In the Details tab of this work item under 'Work Team', ensure that the roles are assigned to individuals. &nbsp;<br></li><li>Client team assigned In the Details tab of the contact under 'Client Team', ensure a Client Owner (usually Partner) and Client Manager (if applicable) are assigned.</li></ul>&nbsp; | Partner |  | None | 0
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Task | Ensure the welcome video is added to the relevant client task below. | This video should welcome the client to your firm and outline what will be happening in the onboarding process. | Partner |  | None | 0
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Task | Replace the Calendly link below with an appropriate link for the kick off call |  | Partner |  | None | 0
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Task | Add the onboarding form for completion by the client to the relevant client task below, adjust the email appropriately and send to the client (Sending Settings) |  | Partner |  | None | 0
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Client Task Group | Welcome to our firm | [5 empty] | Work Assignee |  |  | Let's get things going with your upcoming onboarding | Hi <%preferred_name>,<BR/><BR/>Thank you for trusting us with your business. We want to get your onboarding done efficiently and satisfactorily. As such, from time to time, you will receive emails from myself or our team containing a checklist of items. This checklist is sent to you via Karbon, the system we use to manage our jobs.<BR/><BR/>When you receive an email containing a checklist, you will be able to click a link that will take you to a unique secure view, listing all your items that need to be completed. This view will also enable us to collaborate together to share comments and documents securely. <BR/><BR/>With that covered, please complete the following checklist for us to get your onboarding underway. By clicking below, you can get more information, add comments or questions, and upload files. Once you have completed an item please remember to check it off so we know that it has been done. | Custom | 2 | Reminder #<%reminder_number>: Please complete these items to get your onboarding underway | Hi <%preferred_name>,<BR/><BR/>A quick reminder that some of your checklist items still need to be completed. Not sure how to use the task list below. <a href="https://www.karbonhq.com/client-tasks-for-clients">Click here</a> to learn how.
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Client Task | Welcome to our firm! Watch this welcome video: https:// |  |  |  |  | 3
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Client Task | Review our onboarding process | <div>Our typical onboarding process is completed over a 4 week period. During this time your main point of contact will be one of our onboarding specialists. A high level overview of our process is:</div><div><br></div>Week 1: Kick off call, information gathering and systems setup<div>Week 2: Check-in/progress call and systems training part 1</div><div>Week 3: Bookkeeping review (if applicable) and systems training part 2</div><div>Week 4: Finalisation of onboarding and handover to your services delivery team</div> |  |  |  | 3
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Client Task | Please schedule your kick-off meeting at: www.calendly.com/youraccount | To get you up and running quickly, please schedule your kick-off meeting for some time in the next 2-3 days. |  |  |  | 3
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Client Task | Please complete your onboarding information form: |  |  |  |  | 3
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Section | AML & Risk Assessment
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Section Automator | [15 empty] | The work |  | In Progress - Kick-off / Setup | Status | All tasks in this section | Ready To Start
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Section Automator | [15 empty] | All tasks in a specific section | Confirm sales activities completed and setup onboarding and client team | Completed | Assignee | The work |  | Onboarding Specialist
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Task | Create a Risk Assessment in Xama Onboarding | <div>Risk Assessments can be created by clicking into the Risk Assessment tab within a Client in Xama. See this training video for more information -&nbsp;https://vimeo.com/user165977372</div><div><br></div>If configured appropriately within the integration settings, creating a Risk Assessment in Xama will add an integrated Risk Assessment work item in Karbon with instructions to follow.&nbsp;<div><br></div><div>Karbon and Xama have worked together to create a Work Template to support this process. It can be added to your Karbon account here -&nbsp;https://karbonhq.com/templates/risk-assessment-xama/ - and then specified as the template to be generated when the Risk Assessment is created in Xama.</div> | Onboarding Specialist |  | None | 3
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Section | Setup internal systems
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Status | All tasks in this section | Ready To Start
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Task | Confirm activities completed | These can be triggered automatically from the signed proposal:<div><br></div><div><ul><li>Contact and first invoice sent to QuickBooks or Xero (by GoProposal)&nbsp;&nbsp;</li><li>Client Manager notified of new client (by GoProposal)</li><li>Proposal Contacts (Business and Person) updated to correct Contact Type in Karbon (i.e. Client - Onboarding), with client owner and client manager fields added, alongside PDF of the proposal and engagement (by Zapier or manually)</li><li>Work items added to Karbon for the proposal line items selected (by GoProposal). Reference the signed proposal against the listed work items under 'Work' for the client and if any are missing then make sure that they are manually added (<a href="https://help.karbonhq.com/en/articles/5834177-overview-of-work#h_40847d95f8" target="_blank">see how to create work from a template</a>).&nbsp;</li><li>Prefilled onboarding form added to the onboarding work item (by Zapier or manually)</li><li>Contacts added to Xama Hub for AML and Risk Assessment (by Xama Karbon integration)</li><li>Setup client folders in (OneDrive / Google Drive / DropBox) (by Zapier or manually setup in alternative systems)</li><li>Create new client account in Dext (if applicable), or queue this for later (by Zapier or manually)&nbsp;</li><li>Setup professional clearance work item in Karbon (if applicable) (by GoProposal)&nbsp;</li></ul></div><div></div><div><br></div> | Onboarding Specialist |  | None | 3
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Task | Setup the client on all internal systems |  | Onboarding Specialist |  | Internal Admin | 3
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Nested Task | Access accounting system and conduct necessary prep work |  | Onboarding Specialist |  | None | 3
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Nested Task | Create recurring invoices in QuickBooks or Xero (unless using auto-invoicing in GoProposal) | If the client will be using an invoice processing tool like Dext, then set the invoice to automatically send to the email-in address for their account, as well as their actual email address. | Onboarding Specialist |  | None | 3
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Nested Task | Check the direct debit mandate is set up in GoCardless and establish a link between the mandate and the client record in your QuickBooks or Xero account. If not set up, add to the kick off call agenda. |  | Onboarding Specialist |  | None | 3
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Nested Task | Complete setup of work items in Karbon and create appropriate recurring schedules. | <div>Under the 'Details' tab of each Work Item<br></div><div><ul><li>Edit the Key Dates so that the Start and Due Date are reflective of the Key Dates outlined within the engagement letter</li><li>Add the 'Work Team', ensuring that the roles are assigned to individuals.</li></ul><div><br></div></div><div><div>Under the main Header of each Work Item</div><ul><li>Setup Repeating Work schedule (if applicable)</li></ul><div><br></div></div><div><div>Under the 'Time &amp; Budget' tab of each Work Item:<br></div><ul><li>Click 'Fee Settings' and set appropriately. Enter a Fixed Fee amount if applicable.</li><li>Make appropriate budget adjustments.</li></ul></div> | Onboarding Specialist |  | None | 3
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Nested Task | Setup re-engagement (GLOSS Review) work item for the following year. |  | Onboarding Specialist |  | None | 3
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Section | Client systems setup
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Status | All tasks in this section | Ready To Start
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Task | Create a QuickBooks or Xero account for the client, or transfer ownership of billing (assuming access already available from the sales process). If access to their accounting software has already been granted then this can be done immediately. |  | Onboarding Specialist |  | None | 3
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Task | Setup any appropriate software licences and send client invitations as appropriate. |  | Onboarding Specialist |  | None | 3
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Section | Kick-off meeting (week 1)
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Status | All tasks in this section | Ready To Start
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Task | Remind client of upcoming meeting (and send agenda) | Remind client to complete necessary client onboarding checklist and remind them of the upcoming kick-off meeting. Use the following text for the subject line and body of the email and send to the client. Be sure to update the [ ] sections prior to send and that the appointment is on the associated partner's calendar (plus update the partner if needed).&nbsp;<div>___________</div><div><br></div><div><b>Subject: </b>Reminder: Your kick-off meeting is just around the corner</div><div><b>Body text:</b>&nbsp;</div><div>Hi [First name],</div><div><br></div><div>Thanks for becoming a new client and partner of [Our firm]. We look forward to serving you now and in the future. Our first meeting to kick things off is [date/time of meeting]. Please be sure to complete the previously sent onboarding checklist.&nbsp;</div><div><div><br></div></div><div>During the meeting, we will be covering the following agenda:</div><div><ul><li>Introductions</li><li>Review the onboarding process, including expected time to completion, and current progress against tasks.&nbsp;</li><li>Discuss professional clearance (if applicable)</li><li>What you can expect from us, what we expect from you, what’s in scope and how to engage us to provide additional services or amend the scope of existing services.</li><li>Discussion of your goals and preferred style of communication.</li><li>Explain systems for collaboration and outline training to be provided</li><li>Schedule following meetings for systems training and handover</li></ul></div><div><br></div><div>Again, thanks for entrusting your accounting needs with us. We look forward to working closely together over the near and long-term future.</div><div><br></div><div>Regards,</div><div>[Onboarding Specialist name]</div> | Onboarding Specialist |  | Internal Admin | 7
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Task | Kick-off meeting with client | Complete the formal kick-off meeting via video conference or in-person.&nbsp;<div><div><br></div><div>This is typically attended by the partner who made the sale, the client manager, and the person managing the onboarding process.<br></div><div><br></div><div><b>Agenda Items</b></div><div><ul><li>Introductions</li><li>Review the onboarding process, including expected time to completion, and current progress against tasks.&nbsp;Provide a graphical representation of the steps and explain each of them.</li><li>Remind on outstanding items, as applicable: - GoCardless mandate - Identity verification&nbsp;</li><li>Discuss professional clearance (if applicable)</li><li>Outline information request to be received by the client</li><li>Set expectations: Here’s what you can expect from us, what we expect from you, what’s in scope and how we will let you know if you need us to provide additional services or amend the scope of existing services. Explain SLAs on response times.</li><li>Understand the client’s goals and preferred style of communication. Do they prefer phone? Email? A certain day of the week? When's best to contact you? Create a pinned note in Karbon with this information.</li><li>Introduce systems for collaboration, including Karbon, bookkeeping apps etc.</li><li>Ensure client address is up to date on HMRC</li><li>Access to other systems may need to be gained</li><li>Book in system training or notify that a link will be sent out to book it in, or book in a check-in call no more than 1 week later.</li><li>Schedule weekly meetings</li></ul></div><div><br></div></div> | Onboarding Specialist |  | Internal Admin | 7
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Nested Task | Capture meeting notes / recording and add as a pinned note on the client timeline | Template structure:&nbsp;<div>&nbsp;<b><br>MEETING NOTES:<br></b><ul style=""><li style="">...&nbsp;</li></ul><b><br></b><div><b>NEXT STEPS FOR US: </b><ul style=""><li style="">…&nbsp;<br></li></ul><div style="font-weight: bold;"><b><br></b></div><b>NEXT STEPS FOR CLIENT: </b><ul style=""><li style="">…<b><br></b></li></ul><div><br></div></div></div> | Onboarding Specialist |  | None | 7
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Task | Send follow-up client tasks to client post-kickoff meeting | Use the notes from the prior task to send a client task with the client summary as the email body and to use the client tasks themselves to remind them of their next steps and to schedule the next meeting. If needed, resend (or remind client to complete) client onboarding checklist if open items still exist. | Onboarding Specialist |  | None | 7
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Client Task Group | Kickoff meeting follow-up
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Client Task Group Automator | [15 empty] | All tasks in the section above this section |  | Completed | Due Date | All tasks in this section |  |  |  | 3
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Client Task | [Add relevant follow up tasks here and send to the client]
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Section | Confirm information and complete system training meeting (1) (week2)
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Status | All tasks in this section | Ready To Start
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Status | The work | In Progress - Prep
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Task | Confirm completion of client onboarding form | <ul><li>Details for prior accountant have been obtained.&nbsp;</li></ul>&nbsp; | Onboarding Specialist |  | Internal Admin | 14
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Task | Receipt of all documentation and systems access from prior accountant (if applicable) |  | Onboarding Specialist |  | None | 14
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Task | Weekly meeting & training (2nd week) | <div><b>Complete the following:&nbsp;</b></div><ul><li>Catch client up on current onboarding progress&nbsp;</li><li>Discuss any and all missing items</li><li>Complete system training</li><li>Be sure to schedule the next meeting prior to ending the meeting&nbsp;<br></li><li>Send follow-up email after the meeting with what was discussed and collective next steps&nbsp;</li></ul><div><br></div><div><b>MEETING NOTES</b></div><div><ul><li>...</li></ul><div><br></div></div><div><b>NEXT STEPS:</b></div><div><ul><li>...</li></ul></div> | Onboarding Specialist |  | Internal Admin | 14
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Task | Ensure next meeting is scheduled |  | Onboarding Specialist |  | None | 14
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Section | Bookkeeping review
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Section Automator | [15 empty] | All tasks in a specific section | Client systems setup | Completed | Status | All tasks in this section | Ready To Start
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Task | Complete review of bookkeeping and prior information | Familiarise yourself with the client.&nbsp;&nbsp; | Client Manager |  | None | 21
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Task | Consider need for major clean up | Review engagement letter in conjunction with the state of affairs of the financials. If a mismatch (e.q. requires major clean-up), complete a change order request with the client. Depending on the change, either continue the process or create a new piece of work for a major clean up and mark this process as complete. | Client Manager |  | None | 21
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Task | Review (and get approval) of financials and workflow processes with Partner | For the financials and workflows prepped, review with the Partner and get sign-off to show and walk-through with the client. | Client Manager |  | Internal Admin | 21
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Section | System training (2) (week 3)
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Status | All tasks in this section | Ready To Start
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Task | Prep for upcoming client meeting |  | Onboarding Specialist |  | Internal Admin | 21
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Task | Weekly meeting & training (3rd week) | Catch client up on current onboarding progress, missing items, complete further system training, and ensure the final onboarding review and handover meeting is scheduled. | Onboarding Specialist |  | Internal Admin | 21
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Task | Customize workflow(s) to client specific needs | For all work templates consider the need to customise based on training. | Onboarding Specialist |  | Internal Admin | 21
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Client Task Group | Schedule your onboarding review and handover meeting
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Client Task | Please schedule your onboarding review meeting at: www.calendly.com/youraccount |  |  |  |  | 21
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Section | Internal handover (week 4)
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Section Automator | [15 empty] | All sections & tasks above this section |  | Completed | Status | All tasks in this section | Ready To Start
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Task | Confirm all information received and all separate onboarding work items completed |  | Onboarding Specialist |  | None | 28
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Task | Conduct internal handover meeting | Present the financials (P&amp;L, Balance Sheet), systems setup, processes to follow and provide training on what it means and where things go from here. Discuss KPIs that will be reviewed each month. Ask questions that still need answers, and answers questions the client might have. | Onboarding Specialist |  | None | 28
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Section | Conduct final onboarding review and handover meeting (week 4)
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Assignee | The work |  | Onboarding Specialist
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Status | All tasks in this section | Ready To Start
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Status | The work | In Progress - Review
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Task | Remind of review meeting (and send agenda) | Confirm review meeting and send meeting agenda. | Onboarding Specialist |  | Internal Admin | 23
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Task | Prepare for review meeting | Prepare the presentation, agenda, and talking points for the review meeting. | Onboarding Specialist |  | None | 23
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Task | Conduct final onboarding review and handover meeting | Once complete, <b><font color="#6c3b8f">change work status to "Follow-up"</font></b> | Onboarding Specialist |  | Internal Admin | 28
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Task | Post review meeting follow-up activities | Debrief with team on meeting summary, outcomes and lessons learned. Fill out all notes on client timeline. | Onboarding Specialist |  | None | 28
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Section | Follow-up
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Status | All tasks in this section | Ready To Start
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Status | The work | In Progress - Follow-up
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Section Automator | [15 empty] | All tasks in the section above this section |  | Completed | Assignee | The work |  | Admin
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Section Automator | [15 empty] | All tasks in this section |  | Completed | Status | The work | Completed
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Task | Send out onboarding survey | <br> | Admin |  | Internal Admin | 28
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Task | Send gift pack out to client | Send the new client thank you gift to client. Once complete, <b><font color="#6c3b8f">change the work status to "Completed"</font></b>. | Admin |  | Internal Admin | 28

## Work Template Estimates
ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW | ENTER YOUR DATA BELOW
Template Name (not updatable) | Budget Estimate | Budget Estimate | Budget Estimate | Budget Estimate | Budget Estimate
| Job Role (required) | Team Member | Task Type (required) | Hourly Rate (blank for default) | Estimated Time (mins)
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Partner |  | Internal Admin |  | 30
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Client Manager |  | Internal Admin |  | 120
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Onboarding Specialist |  | Internal Admin |  | 300
Client onboarding (Integrated Onboarding System - Businesses) (United Kingdom) | Admin |  | Internal Admin |  | 30

## ReferenceData (hidden)
Planned
Ready To Start
In Progress
Waiting
Completed
Public
Private
Hidden
Afghanistan
Albania
Algeria
American Samoa
Andorra
Angola
Anguilla
Antarctica
Antigua and Barbuda
Argentina
Armenia
Aruba
Australia
Austria
Azerbaijan
Bahamas
Bahrain
Bangladesh
Barbados
Belarus
Belgium
Belize
Benin
Bermuda
Bhutan
Bolivia
Bosnia and Herzegovina
Botswana
Bouvet Island
Brazil
British Indian Ocean Territory
Brunei Darussalam
Bulgaria
Burkina Faso
Burundi
Cambodia
Cameroon
Canada
Cape Verde
Cayman Islands
Central African Republic
Chad
Chile
China
Christmas Island
Cocos (Keeling) Islands
Colombia
Comoros
Congo
Congo, the Democratic Republic of the
Cook Islands
Costa Rica
Cote D'Ivoire
Croatia
Cuba
Cyprus
Czech Republic
Denmark
Djibouti
Dominica
Dominican Republic
Ecuador
Egypt
El Salvador
England
Equatorial Guinea
Eritrea
Estonia
Ethiopia
Falkland Islands (Malvinas)
Faroe Islands
Fiji
Finland
France
French Guiana
French Polynesia
French Southern Territories
Gabon
Gambia
Georgia
Germany
Ghana
Gibraltar
Greece
Greenland
Grenada
Guadeloupe
Guam
Guatemala
Guinea
Guinea-Bissau
Guyana
Haiti
Heard Island and Mcdonald Islands
Holy See (Vatican City State)
Honduras
Hong Kong
Hungary
Iceland
India
Indonesia
Iran, Islamic Republic of
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Korea, Democratic People's Republic of
Korea, Republic of
Kuwait
Kyrgyzstan
Lao People's Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Macao
Macedonia, the Former Yugoslav Republic of
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Martinique
Mauritania
Mauritius
Mayotte
Mexico
Micronesia, Federated States of
Moldova, Republic of
Monaco
Mongolia
Montserrat
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
Netherlands Antilles
New Caledonia
New Zealand
Nicaragua
Niger
Nigeria
Niue
Norfolk Island
Northern Ireland
Northern Mariana Islands
Norway
Oman
Pakistan
Palau
Palestinian Territory, Occupied
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Pitcairn
Poland
Portugal
Puerto Rico
Qatar
Reunion
Romania
Russian Federation
Rwanda
Saint Helena
Saint Kitts and Nevis
Saint Lucia
Saint Pierre and Miquelon
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Scotland
Senegal
Serbia and Montenegro
Seychelles
Sierra Leone
Singapore
Skype
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
South Georgia and the South Sandwich Islands
Spain
Sri Lanka
Sudan
Suriname
Svalbard and Jan Mayen
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Taiwan, Province of China
Tajikistan
Tanzania, United Republic of
Thailand
Timor-Leste
Togo
Tokelau
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Turks and Caicos Islands
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom
United States Minor Outlying Islands
Uruguay
USA
Uzbekistan
Vanuatu
Venezuela
Viet Nam
Virgin Islands, British
Virgin Islands, U.s.
Wales
Wallis and Futuna
Western Sahara
Yemen
Zambia
Zimbabwe
Administrator
Restricted User
User
Custom
Gentle
Urgent
Client Owner
Colleague
Work Assignee
Fixed Fee
Non Billable
Time and Materials
Planned
Ready To Start
Ready To Start - Send client requests
Ready To Start - Resend client requests
Ready To Start - Ready for Accounting
Ready To Start - Ready for Tax
In Progress
In Progress - Kick-off / Setup
In Progress - Prep
In Progress - Process
In Progress - Review
In Progress - Revise
In Progress - Final review
In Progress - Advise
In Progress - Assemble
In Progress - File
In Progress - Lodge
In Progress - Follow-up
In Progress - Send payroll to client
In Progress - Finalise payroll process
Waiting
Waiting - Wait engagement letter
Waiting - Waiting for info
Waiting - Waiting for CPA
Waiting - Waiting for CPA/CA
Waiting - Waiting for client
Waiting - Waiting for client 2
Waiting - Wait for auditor
Waiting - Wait for signature
Waiting - Waiting for IRS
Waiting - Waiting for CRA
Waiting - Waiting for ATO
Waiting - Waiting for IRD
Waiting - Waiting for HMRC
Waiting - Waiting for Gov't
Waiting - Wait for confirmation
Waiting - Extended
Waiting - Wait for payment confirm
Completed
Completed - Not applicable
Completed - Billed
Completed - Not a fit
Completed - Closed lost
Completed - Closed won
Completed - Cancelled
Planned
Ready To Start
Ready To Start - Send client requests
Ready To Start - Resend client requests
Ready To Start - Ready for Accounting
Ready To Start - Ready for Tax
In Progress
In Progress - Kick-off / Setup
In Progress - Prep
In Progress - Process
In Progress - Review
In Progress - Revise
In Progress - Final review
In Progress - Advise
In Progress - Assemble
In Progress - File
In Progress - Lodge
In Progress - Follow-up
In Progress - Send payroll to client
In Progress - Finalise payroll process
Waiting
Waiting - Wait engagement letter
Waiting - Waiting for info
Waiting - Waiting for CPA
Waiting - Waiting for CPA/CA
Waiting - Waiting for client
Waiting - Waiting for client 2
Waiting - Wait for auditor
Waiting - Wait for signature
Waiting - Waiting for IRS
Waiting - Waiting for CRA
Waiting - Waiting for ATO
Waiting - Waiting for IRD
Waiting - Waiting for HMRC
Waiting - Waiting for Gov't
Waiting - Wait for confirmation
Waiting - Extended
Waiting - Wait for payment confirm
Completed
Completed - Not applicable
Completed - Billed
Completed - Not a fit
Completed - Closed lost
Completed - Closed won
Completed - Cancelled
Client Task Group - Sent to Client
1 | Advertising
1 | Commission
1 | E-Commerce
1 | Fee for Service
1 | Licensing
1 | Markup
1 | Production
1 | Subscription
2 | Advertising
2 | Commission
2 | E-Commerce
2 | Fee for Service
2 | Licensing
2 | Markup
2 | Production
2 | Subscription
3 | Advertising
3 | Commission
3 | E-Commerce
3 | Fee for Service
3 | Licensing
3 | Markup
3 | Production
3 | Subscription
4 | Advertising
4 | Commission
4 | E-Commerce
4 | Fee for Service
4 | Licensing
4 | Markup
4 | Production
4 | Subscription
5 | Advertising
5 | Commission
5 | E-Commerce
5 | Fee for Service
5 | Licensing
5 | Markup
5 | Production
5 | Subscription
6 | Advertising
6 | Commission
6 | E-Commerce
6 | Fee for Service
6 | Licensing
6 | Markup
6 | Production
6 | Subscription
7 | Advertising
7 | Commission
7 | E-Commerce
7 | Fee for Service
7 | Licensing
7 | Markup
7 | Production
7 | Subscription
8 | Advertising
8 | Commission
8 | E-Commerce
8 | Fee for Service
8 | Licensing
8 | Markup
8 | Production
8 | Subscription
9 | Advertising
9 | Commission
9 | E-Commerce
9 | Fee for Service
9 | Licensing
9 | Markup
9 | Production
9 | Subscription
10 | Advertising
10 | Commission
10 | E-Commerce
10 | Fee for Service
10 | Licensing
10 | Markup
10 | Production
10 | Subscription
11 | Advertising
11 | Commission
11 | E-Commerce
11 | Fee for Service
11 | Licensing
11 | Markup
11 | Production
11 | Subscription
12 | Advertising
12 | Commission
12 | E-Commerce
12 | Fee for Service
12 | Licensing
12 | Markup
12 | Production
12 | Subscription
13 | Advertising
13 | Commission
13 | E-Commerce
13 | Fee for Service
13 | Licensing
13 | Markup
13 | Production
13 | Subscription
14 | Advertising
14 | Commission
14 | E-Commerce
14 | Fee for Service
14 | Licensing
14 | Markup
14 | Production
14 | Subscription
15 | Advertising
15 | Commission
15 | E-Commerce
15 | Fee for Service
15 | Licensing
15 | Markup
15 | Production
15 | Subscription
16 | Advertising
16 | Commission
16 | E-Commerce
16 | Fee for Service
16 | Licensing
16 | Markup
16 | Production
16 | Subscription
1 | Accruals
1 | Cash
1 | None
2 | Accruals
2 | Cash
2 | None
3 | Accruals
3 | Cash
3 | Flat Rate Accrual
3 | Flat Rate Cash
3 | None
4 | Invoice
4 | None
4 | Payments
5 | Accruals
5 | Cash
5 | None
6 | Accruals
6 | Cash
8 | Débit
8 | Encaissements
10 | Accrual
10 | Cash Receipts
15 | Accruals
15 | Cash
15 | None
16 | Accruals
16 | Cash
16 | None
1 | Annually
1 | Monthly
1 | Six Monthly
1 | Three Monthly
1 | Two Monthly
2 | Annually
2 | Monthly
2 | Quarterly (Option 1)
2 | Quarterly (Option 2)
2 | Quarterly (Option 3)
3 | Monthly
3 | Quarterly
3 | Yearly
4 | Monthly
4 | Six Monthly
4 | Two Monthly
5 | Annually
5 | Annually (Quarterly Instalments)
5 | Monthly
5 | None
5 | Quarterly
5 | Six Monthly
6 | Monthly
6 | Three Monthly
6 | Two Monthly
8 | Bi-Annually
8 | Monthly
8 | Quarterly
10 | Bimonthly
10 | Four monthly
10 | Not Registered
10 | Six monthly
10 | Yearly
15 | Monthly
15 | Quarterly
15 | Yearly
16 | Each Semester
16 | Monthly
16 | Quarterly
16 | Yearly
1 | Other
1 | Products
1 | Products and Services
1 | Services
2 | Other
2 | Products
2 | Products and Services
2 | Services
3 | Other
3 | Products
3 | Products and Services
3 | Services
4 | Other
4 | Products
4 | Products and Services
4 | Services
5 | Other
5 | Products
5 | Products and Services
5 | Services
6 | Other
6 | Products
6 | Products and Services
6 | Services
7 | Other
7 | Products
7 | Products and Services
7 | Services
8 | Other
8 | Products
8 | Products and Services
8 | Services
9 | Other
9 | Products
9 | Products and Services
9 | Services
10 | Other
10 | Products
10 | Products and Services
10 | Services
11 | Other
11 | Products
11 | Products and Services
11 | Services
12 | Other
12 | Products
12 | Products and Services
12 | Services
13 | Other
13 | Products
13 | Products and Services
13 | Services
14 | Other
14 | Products
14 | Products and Services
14 | Services
15 | Other
15 | Products
15 | Products and Services
15 | Services
16 | Other
16 | Products
16 | Products and Services
16 | Services
1 | Monthly
1 | Quarterly
1 | Yearly
2 | Monthly
2 | Quarterly
2 | Yearly
3 | Monthly
3 | Quarterly
3 | Yearly
4 | Monthly
4 | Quarterly
4 | Yearly
5 | Monthly
5 | Quarterly
5 | Yearly
6 | Monthly
6 | Quarterly
6 | Yearly
7 | Monthly
7 | Quarterly
7 | Yearly
8 | Monthly
8 | Quarterly
8 | Yearly
9 | Monthly
9 | Quarterly
9 | Yearly
10 | Monthly
10 | Quarterly
10 | Yearly
11 | Monthly
11 | Quarterly
11 | Yearly
12 | Monthly
12 | Quarterly
12 | Yearly
13 | Monthly
13 | Quarterly
13 | Yearly
14 | Monthly
14 | Quarterly
14 | Yearly
15 | Monthly
15 | Quarterly
15 | Yearly
16 | Monthly
16 | Quarterly
16 | Yearly
1 | Club or Society
1 | Corporation
1 | Estate or Trust
1 | Exempt Organization
1 | Limited Liability
1 | Other/None
1 | Partnership
1 | Person
1 | Private Foundation
1 | S Corporation
1 | Sole Proprietor
2 | Club or Society
2 | Company
2 | Not for Profit
2 | Partnership
2 | Person
2 | Self Managed Superannuation Fund
2 | Sole Proprietor
2 | Superannuation Fund
2 | Trust
3 | Club or Society
3 | Company
3 | Housing Association
3 | Limited Company
3 | Look Through Company
3 | Not for Profit
3 | Partnership
3 | Person
3 | Sole Proprietor
3 | Trust
3 | Unincorporated Charity
4 | Charity
4 | Club or Society
4 | Company
4 | Look-Through Company
4 | Partnership
4 | Person
4 | Sole Proprietor
4 | Trust
5 | Club or Society
5 | Corporation
5 | Not for Profit
5 | Partnership
5 | Person
5 | Sole Proprietorship
5 | Trust
6 | Closed Corporation
6 | Club/Society or Religious Organisation
6 | Company
6 | Individual
6 | Non Profit Company
6 | Non Profit Organisation
6 | Partnership
6 | Sole Proprietor
6 | Trust
7 | Charity Limited Liability Company
7 | Foreign Company Office
7 | General Partnership
7 | Limited Partnership
7 | Private Limited Liability Company
7 | Public Limited Liability Company
7 | Sole Proprietorship
7 | Unlimited Company
8 | Bénéfices Non Commerciaux
8 | Entreprise individuelle
8 | Entreprise individuelle à responsabilité limitée
8 | Entreprise Unipersonnelle à Responsabilité Limitée
8 | Groupement d'Intérêt Economique
8 | Lureur Meublé Non Professionnel
8 | Société à Responsabilité Limitée
8 | Société Civile de Moyens
8 | Société Civile Immobilière
8 | Société d'Exercice Libéral à Responsabilité Limitée
8 | Société d'Exercice Libéral par Actions Simplifiée
8 | Société par Actions Simplifiée Unipersonnelle
8 | Société par Actions Simplifiées
9 | Company
9 | General Partnership
9 | Limited Liability Partnership
9 | Limited Partnership
9 | Private Limited Liability Company
9 | Public Limited Liability Company
9 | Sole Proprietorship
10 | Association
10 | Club Charity
10 | Company Limited by Guarantee
10 | Company Limited by Shares
10 | Designated Activity Company
10 | Dormant
10 | Foundation
10 | Limited Liability Partnership
10 | Partnership
10 | Public Limited
10 | Societas Europaea
10 | Sole Trade
10 | SSAP
10 | Trust
10 | Unlimited Liability Company
11 | Individual
11 | Limited Partnership
11 | Partnership
11 | Private Limited Liability
11 | Public Limited Liability
11 | Sole proprietor
12 | Cooperation Association
12 | Limited Company
12 | Limited Partnership
12 | Partnership
12 | Proprietorship
13 | General Partnership
13 | Limited Partnership
13 | Private Limited Company
13 | Public Limited Company
13 | Sole Proprietorship
14 | Club or Society
14 | Limited Company
14 | Look Through Company
14 | Not for Profit
14 | Partnership
14 | Person
14 | Sole Proprietor
14 | Trust
15 | Association of Persons (AoP)
15 | Bank
15 | Body of Individuals (BoI)
15 | Limited Liability Partnership (LLP)
15 | One Person Company (OPC)
15 | Other
15 | Partnership Firm
15 | Private Limited
15 | Public Limited
15 | Sole Proprietorship
15 | Trust
16 | Independent
16 | Société à Responsabilité Limitée
16 | Société Anonyme
16 | Société Coopérative
No Action
Create
No Action
Update
Delete
No Action
Create
No Action
Update
No Action
Create
No Action
Delete
No Action
Create
No Action
Update
Delete
No Action
Create
No Action
Update
Delete
No Action
Create
No Action
Update
No Action
Create
No Action
Delete
No Action
Create
No Action
Update
Delete
No Action
Create
No Action
Update
Delete
No Action
Create
No Action
Delete
No Action
Create
No Action
Update
No Action
Create
No Action
Update
Delete
No Action
Create
No Action
Delete
No Action
Create
No Action
Update
Delete
No Action
Create
No Action
Update
No Action
Create
No Action
Update
Delete
No Action
Create
No Action
Update
Delete
No Action
Create
No Action
Delete
No Action
Create
No Action
Update
Delete
No Action
Create
No Action
Update
Delete
No Action
Create
No Action
Update
Delete

## Composite Statuses (hidden)
Formula
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!