## Sheet1
Checklist Summary Details | [6 empty] | © 2018 Karbon
Checklist Name | Payroll Processing
Description | Start date is the day payroll is to be processed (e.g. Wednesday). This is Karbon's best practice payroll process for those providing outsourced payroll services using Gusto
Owner | Payroll Specialist
Expected Duration | 2 hours over 2 days
Workflow Status Details (in addition to major categories of Planned, In Progress, Waiting, and Completed) | [5 empty] | Job Role Details
Workflow ID# | Workflow status name |  |  |  |  | Job role ID# | Job role name
1 | In Progress |  |  |  |  | 1 | Payroll Specialist
2 | Waiting (Waiting for client)
3 | Completed (Cancelled)
Client Task Section | Payroll update needed
Step Type | Step Type | Step Title | Step Description | Owner | Duration (hours) | Dependent On Step # | Due Date
1 | Client task | Please confirm that your payroll timesheets and any additional payroll changes are up-to-date | Please confirm/complete the following: - Update this period's payroll timesheets and/or confirm your time tracking application (e.g. TSheets) is up-to-date. - Provide comments on any changes, additions and/or time-off requests. - Check complete to mark your approval to process the payroll. | Client | 0.5 |  | 1 day prior to start date
Section | Process payroll
Step Type | Step Type | Step Title | Step Description | Owner | Duration (hours) | Dependent On Step # | Due Date
2 | Task | Confirm that payroll timesheets and any relevant changes are up to date (with client) | Confirm the following with your client: - Upload this period's payroll timesheets or confirm time tracking application (e.g. TSheets) is up-to-date. - Ask client to provide any comments on any changes, additions and/or time-off requests. - Check complete to mark client's approval to process the payroll. - Confirm client has successfully completed set up for all employees | Payroll Specialist | 0.25 | 1 | 1 day prior to start date
3 | Task | Prep payroll based on updated client details | Change work status to "In Progress". | Payroll Specialist | 0.75 | 2 | 0 days after start date
3b | Nested task | Launch payroll run process — https://app.gusto.com/login | Navigate to "Run payroll" and select your payroll type (regular, bonus, off-cycle, or termination). |  |  | 3a | 0 days after start date
3c | Nested Task | Review (and/or process) employees' hours, reimbursements, and additional earnings | Verify/enter part-time and hourly time, overtime, payment method (check or direct deposit) and calculations. |  |  | 3b | 0 days after start date
3d | Nested Task | Review approved time-off requests | Includes vacation, sick, and PTO authorized requests. |  |  | 3c | 0 days after start date
3e | Nested Task | Check client bank balance | Review payroll preview and navigate to "Cash requirement summary" for in-depth analysis of expected pay run. |  |  | 3d | 0 days after start date
4 | Task | Verify & submit payroll | Final review of amounts to be taxed and debited, employee hours and take home pay, and total company payroll costs | Payroll Specialist | 0.25 | 3 | 0 days after start date
4a | Nested Task | Print checks (if applicable) | If any employees are paid through check, print check using Gusto template on check stock. |  |  | 3 | 0 days after start date
5 | Task | Follow-up with client & update systems |  | Payroll Specialist | 0.25 | 4 | 0 days after start date
5a | Nested Task | Update accounting software (if applicable) | Automatically sync payroll entries if using a Gusto accounting software partner (Xero, Freshbooks, QuickBooks, Aplos). If using other accounting software, manually enter in payroll journal information. | Payroll Specialist |  | 4 | 0 days after start date