## Primary
PHASE | TASK | START DATE | END DATE | DURATION (Days) | STATUS | OWNER | RESOURCE | NOTES
Phase 1: Discovery and Planning | When purchased: validate your Snyk plan is applied to correct organization |  |  |  | Not started |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-1-discovery-and-planning/validate-your-snyk-plan
Phase 1: Discovery and Planning | Identify business critical applications |  |  |  | Not started |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-1-discovery-and-planning/discovery
Phase 1: Discovery and Planning | Confirm Internal points of contact for SCM, CI/CD integrations |  |  |  | Not started |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-1-discovery-and-planning/discovery
Phase 1: Discovery and Planning | Identify internal stakeholders and responsibilities |  |  |  | Not started |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-1-discovery-and-planning/discovery
Phase 1: Discovery and Planning | Decide on organization name |  |  |  | Not started |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-1-discovery-and-planning/name-your-organization
Phase 1: Discovery and Planning | Determine member roles |  |  |  | Not started |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-1-discovery-and-planning/determine-member-roles
Phase 1: Discovery and Planning | Determine success metrics |  |  |  | Not started |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-1-discovery-and-planning/plan-for-success
Phase 1: Discovery and Planning | Choose Initial Integrations (SCM, CI/CD) |  |  |  | Not started |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-1-discovery-and-planning/choose-rollout-integrations
Phase 1: Discovery and Planning | Create rollout plan to the larger team |  |  |  | Not started |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-1-discovery-and-planning/create-rollout-plan
Phase 1: Discovery and Planning | Determine Exception Process/Handling |  |  |  | Not started |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-1-discovery-and-planning/create-rollout-plan#exception-handling
Phase 2: Configure Account | Name your organization |  |  |  | Not started |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-2-configure-your-organization#name-your-organization
Phase 2: Configure Account | Configure notifications |  |  |  | Not started |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-2-configure-your-organization#additional-settings-to-consider
Phase 2: Configure Account | Enable Snyk Code |  |  |  | Not started |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-2-configure-your-organization#additional-settings-to-consider
Phase 2: Configure Account | Set integrations settings for visibility |  |  |  | Not started |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-2-configure-your-organization/configure-integrations#git-repositories
Phase 2: Configure Account | Apply license policy |  |  |  | Not started |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-2-configure-your-organization#license-policy-optional
Phase 2: Configure Account | Configure SCM or CLI scanning |  |  |  | Not started |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-2-configure-your-organization/configure-integrations
Phase 3: Gain Visibility | Import projects into Snyk and gain visibility |  |  |  | Not started |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-3-gain-visibility/import-projects
Phase 3: Gain Visibility | Optional: Set Project Attributes |  |  |  | Not started |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-3-gain-visibility/add-project-attributes
Invite Users | Invite Users |  |  |  | Not started |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/invite-users
Phase 4: Create a Fix Strategy | Group issues & decide prioritization method |  |  |  | Not started |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-4-create-a-fix-strategy
Phase 4: Create a Fix Strategy | Update your timeline based on fix strategy |  |  |  | Not started |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-4-create-a-fix-strategy#update-your-timeline
Phase 5: Rolling out the prevention stage | Communicate prevention strategy to developers |  |  |  | Not started |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-5-rolling-out-the-prevention-stage
Phase 5: Rolling out the prevention stage | Enable and configure Snyk on PRs |  |  |  | Not started |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-5-rolling-out-the-prevention-stage/enable-and-configure-snyk-on-prs
Phase 5: Rolling out the prevention stage | Enable Snyk on pipelines to act as a gate using snyk test |  |  |  | Not started |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-5-rolling-out-the-prevention-stage/add-and-configure-snyk-to-your-ci-cd-pipeline
Phase 5: Rolling out the prevention stage | If using containers, consider configuring Snyk on container pipeline/registry |  |  |  | Not started |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-5-rolling-out-the-prevention-stage/add-and-configure-snyk-to-your-ci-cd-pipeline
Phase 5: Rolling out the prevention stage | If using infrastructure code, consider configuring Snyk in pipeline/Terraform Cloud |  |  |  | Not started |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-5-rolling-out-the-prevention-stage/infrastructure-as-code
Phase 7: Triage/ignores/Fixes | Implement the fix strategy created in Phase 4 & apply ignores as needed |  |  |  | Not started |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-6-triages-ignores-and-fixes
Phase 7: Triage/ignores/Fixes | Track the progress of your team by reviewing each project result |  |  |  | Not started

## Asana
Section/Column | Name | Type | START DATE | END DATE | DURATION (Days) | STATUS | Assignee | Collaborators | RESOURCE | Description | NOTES
Phase 1: Discovery and Planning | When purchased: validate your Snyk plan is applied to correct organization | Task |  |  |  | Not started |  |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-1-discovery-and-planning/validate-your-snyk-plan
Phase 1: Discovery and Planning | Identify business critical applications | Task |  |  |  | Not started |  |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-1-discovery-and-planning/discovery
Phase 1: Discovery and Planning | Confirm Internal points of contact for SCM, CI/CD integrations | Task |  |  |  | Not started |  |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-1-discovery-and-planning/discovery
Phase 1: Discovery and Planning | Identify internal stakeholders and responsibilities | Task |  |  |  | Not started |  |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-1-discovery-and-planning/discovery
Phase 1: Discovery and Planning | Decide on organization name | Task |  |  |  | Not started |  |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-1-discovery-and-planning/name-your-organization
Phase 1: Discovery and Planning | Determine member roles | Task |  |  |  | Not started |  |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-1-discovery-and-planning/determine-member-roles
Phase 1: Discovery and Planning | Determine success metrics | Task |  |  |  | Not started |  |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-1-discovery-and-planning/plan-for-success
Phase 1: Discovery and Planning | Choose Initial Integrations (SCM, CI/CD) | Task |  |  |  | Not started |  |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-1-discovery-and-planning/choose-rollout-integrations
Phase 1: Discovery and Planning | Create rollout plan to the larger team | Task |  |  |  | Not started |  |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-1-discovery-and-planning/create-rollout-plan
Phase 1: Discovery and Planning | Determine Exception Process/Handling | Task |  |  |  | Not started |  |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-1-discovery-and-planning/create-rollout-plan#exception-handling
Phase 2: Configure Account | Name your organization | Task |  |  |  | Not started |  |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-2-configure-your-organization#name-your-organization
Phase 2: Configure Account | Configure notifications | Task |  |  |  | Not started |  |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-2-configure-your-organization#additional-settings-to-consider
Phase 2: Configure Account | Enable Snyk Code | Task |  |  |  | Not started |  |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-2-configure-your-organization#additional-settings-to-consider
Phase 2: Configure Account | Set integrations settings for visibility | Task |  |  |  | Not started |  |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-2-configure-your-organization/configure-integrations#git-repositories
Phase 2: Configure Account | Apply license policy | Task |  |  |  | Not started |  |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-2-configure-your-organization#license-policy-optional
Phase 2: Configure Account | Configure SCM or CLI scanning | Task |  |  |  | Not started |  |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-2-configure-your-organization/configure-integrations
Phase 3: Gain Visibility | Import projects into Snyk and gain visibility | Task |  |  |  | Not started |  |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-3-gain-visibility/import-projects
Phase 3: Gain Visibility | Optional: Set Project Attributes | Task |  |  |  | Not started |  |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-3-gain-visibility/add-project-attributes
Invite Users | Invite Users | Task |  |  |  | Not started |  |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/invite-users
Phase 4: Create a Fix Strategy | Group issues & decide prioritization method | Task |  |  |  | Not started |  |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-4-create-a-fix-strategy
Phase 4: Create a Fix Strategy | Update your timeline based on fix strategy | Task |  |  |  | Not started |  |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-4-create-a-fix-strategy#update-your-timeline
Phase 5: Rolling out the prevention stage | Communicate prevention strategy to developers | Task |  |  |  | Not started |  |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-5-rolling-out-the-prevention-stage
Phase 5: Rolling out the prevention stage | Enable and configure Snyk on PRs | Task |  |  |  | Not started |  |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-5-rolling-out-the-prevention-stage/enable-and-configure-snyk-on-prs
Phase 5: Rolling out the prevention stage | Enable Snyk on pipelines to act as a gate using snyk test | Task |  |  |  | Not started |  |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-5-rolling-out-the-prevention-stage/add-and-configure-snyk-to-your-ci-cd-pipeline
Phase 5: Rolling out the prevention stage | If using containers, consider configuring Snyk on container pipeline/registry | Task |  |  |  | Not started |  |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-5-rolling-out-the-prevention-stage/add-and-configure-snyk-to-your-ci-cd-pipeline
Phase 5: Rolling out the prevention stage | If using infrastructure code, consider configuring Snyk in pipeline/Terraform Cloud | Task |  |  |  | Not started |  |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-5-rolling-out-the-prevention-stage/infrastructure-as-code
Phase 7: Triage/ignores/Fixes | Implement the fix strategy created in Phase 4 & apply ignores as needed | Task |  |  |  | Not started |  |  | https://docs.snyk.io/implement-snyk/team-implementation-guide/phase-6-triages-ignores-and-fixes
Phase 7: Triage/ignores/Fixes | Track the progress of your team by reviewing each project result | Task |  |  |  | Not started