## Primary
PHASE | TASK | START DATE | END DATE | DURATION (Days) | STATUS | OWNER | RESOURCE | NOTES
Phase 1: Discovery and Planning | Connect with your Snyk account manager | 2023-11-01 | 2023-11-07 | 5 | Not started |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-1-discovery-and-planning/connect-with-snyk
Phase 1: Discovery and Planning | Confirm Snyk License is Applied with Account Manager | 2023-11-01 | 2023-11-07 | 5 | Not started |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-1-discovery-and-planning/connect-with-snyk
Phase 1: Discovery and Planning | Identify business critical applications | 2023-11-01 | 2023-11-07 | 5 | Not started |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-1-discovery-and-planning/conduct-discovery
Phase 1: Discovery and Planning | Confirm Internal points of contact for SSO, SCM, CI/CD integrations | 2023-11-01 | 2023-11-07 | 5 | Not started |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-1-discovery-and-planning/conduct-discovery
Phase 1: Discovery and Planning | Identify internal stakeholders and responsibilities | 2023-11-01 | 2023-11-07 | 5 | Not started |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-1-discovery-and-planning/conduct-discovery
Phase 1: Discovery and Planning | Plan Snyk Organization/Group structure | 2023-11-01 | 2023-11-07 | 5 | Not started |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-1-discovery-and-planning/plan-organization-structure
Phase 1: Discovery and Planning | Determine member roles (default or custom) | 2023-11-10 | 2023-11-16 | 5 | Not started |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-1-discovery-and-planning/determine-member-roles
Phase 1: Discovery and Planning | Decide SSO access model (Open to all, Require an Invite) | 2023-11-10 | 2023-11-16 | 5 | Not started |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-1-discovery-and-planning/decide-sso-access
Phase 1: Discovery and Planning | Determine success metrics | 2023-11-10 | 2023-11-16 | 5 | Not started |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-1-discovery-and-planning/plan-for-success
Phase 1: Discovery and Planning | Choose Initial Integrations (SCM, CI/CD) | 2023-11-10 | 2023-11-16 | 5 | Not started |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-1-discovery-and-planning/choose-rollout-integrations
Phase 1: Discovery and Planning | Create rollout plan to the larger team | 2023-11-10 | 2023-11-16 | 5 | Not started |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-1-discovery-and-planning/create-rollout-plan
Phase 1: Discovery and Planning | Determine Exception Process/Handling | 2023-11-10 | 2023-11-16 | 5 | Not started |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-1-discovery-and-planning/create-rollout-plan
Phase 2: Configure Account | Configure SSO | 2023-11-19 | 2023-11-23 | 5 | Not started |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-2-configure-account/configure-sso
Phase 2: Configure Account | Configure an Organization template | 2023-11-19 | 2023-11-23 | 5 | Not started |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-2-configure-account/set-visibility-and-configure-an-organization-template
Phase 2: Configure Account | Configure notifications | 2023-11-19 | 2023-11-23 | 5 | Not started |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-2-configure-account/set-visibility-and-configure-an-organization-template/configure-notifications
Phase 2: Configure Account | Enable Snyk Code | 2023-11-19 | 2023-11-23 | 5 | Not started |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-2-configure-account/set-visibility-and-configure-an-organization-template/enable-snyk-code
Phase 2: Configure Account | Set integrations settings for visibility | 2023-11-19 | 2023-11-23 | 5 | Not started |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-2-configure-account/set-visibility-and-configure-an-organization-template/configure-integrations
Phase 2: Configure Account | Create additional organizations from template | 2023-11-26 | 2023-11-30 | 5 | Not started |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-2-configure-account/set-visibility-and-configure-an-organization-template/create-organizations
Phase 2: Configure Account | Apply security and license policies | 2023-11-26 | 2023-11-30 | 5 | Not started |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-2-configure-account/apply-security-and-license-policies
Phase 3: Gain Visibility | Import projects into Snyk and gain visibility | 2023-12-03 | 2023-12-14 | 10 | Not started |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-3-gain-visibility/import-projects
Phase 3: Gain Visibility | Optional: Add Project Tags or Project Attributes | 2023-12-03 | 2023-12-14 | 10 | Not started |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-3-gain-visibility/add-project-tags-and-attributes
Phase 4: Create a Fix Strategy | Group issues & decide prioritization method | 2023-12-17 | 2023-12-21 | 5 | Not started |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-4-create-a-fix-strategy
Phase 4: Create a Fix Strategy | Update your timeline based on fix strategy | 2023-12-17 | 2023-12-21 | 5 | Not started |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-4-create-a-fix-strategy
Phase 5: Initial rollout to team | Notify the team by email/slack | 2023-12-24 | 2023-12-24 | 1 | Not started |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-5-initial-rollout-to-team/notifying-the-team
Phase 5: Initial rollout to team | Consider Snyk Product training, or security training via Snyk Learn | 2023-12-24 | 2024-01-04 | 10 | Not started |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-5-initial-rollout-to-team/developer-training-from-snyk
Phase 5: Initial rollout to team | Engage Development with IDE Plugins | 2023-12-24 | 2024-01-04 | 10 | Not started |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-5-initial-rollout-to-team/engage-development-with-ide-plugins
Phase 6: Rolling out the prevention stage | Communicate prevention strategy to developers | 2024-01-07 | 2024-01-07 | 1 | Not started |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-6-rolling-out-the-prevention-stage
Phase 6: Rolling out the prevention stage | Enable and configure Snyk on PRs | 2024-01-07 | 2024-01-18 | 10 | Not started |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-6-rolling-out-the-prevention-stage/enable-and-configure-snyk-on-prs
Phase 6: Rolling out the prevention stage | Enable Snyk on pipelines to act as a gate using snyk test | 2024-01-07 | 2024-01-18 | 10 | Not started |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-6-rolling-out-the-prevention-stage/add-and-configure-snyk-to-your-ci-cd-pipeline
Phase 6: Rolling out the prevention stage | If using containers, consider configuring Snyk on container pipeline/registry | 2024-01-07 | 2024-01-18 | 10 | Not started |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-6-rolling-out-the-prevention-stage/custom-base-images
Phase 6: Rolling out the prevention stage | If using infrastructure code, consider configuring Snyk in pipeline/Terraform Cloud | 2024-01-07 | 2024-01-18 | 10 | Not started |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-6-rolling-out-the-prevention-stage/infrastructure-as-code
Phase 7: Triage/ignores/Fixes | Implement the fix strategy created in Phase 4 & apply ignores as needed | 2024-01-21 | 2024-02-15 | 20 | Not started |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-7-triages-ignores-and-fixes
Phase 7: Triage/ignores/Fixes | Track the progress of your teams using reports | 2024-01-21 | 2024-02-15 | 20 | Not started |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-7-triages-ignores-and-fixes
Formulas:
END DATE = WORKDAY.INTL([START DATE],[DURATION (Days)]-1)
START DATE = [START DATE, row above]
Note on C2: Please only change cell C2 to reflect the actual start date and the rest of the timeline will get aligned accordingly

## Asana
Section/Column | Name | Type | START DATE | END DATE | DURATION (Days) | STATUS | Assignee | Collaborators | RESOURCE | Description | NOTES
Phase 1: Discovery and Planning | Connect with your Snyk account manager | Task | 2023-11-01 | 2023-11-07 | 5 | Not started |  |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-1-discovery-and-planning/connect-with-snyk
Phase 1: Discovery and Planning | Confirm Snyk License is Applied with Account Manager | Task | 2023-11-01 | 2023-11-07 | 5 | Not started |  |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-1-discovery-and-planning/connect-with-snyk
Phase 1: Discovery and Planning | Identify business critical applications | Task | 2023-11-01 | 2023-11-07 | 5 | Not started |  |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-1-discovery-and-planning/conduct-discovery
Phase 1: Discovery and Planning | Confirm Internal points of contact for SSO, SCM, CI/CD integrations | Task | 2023-11-01 | 2023-11-07 | 5 | Not started |  |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-1-discovery-and-planning/conduct-discovery
Phase 1: Discovery and Planning | Identify internal stakeholders and responsibilities | Task | 2023-11-01 | 2023-11-07 | 5 | Not started |  |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-1-discovery-and-planning/conduct-discovery
Phase 1: Discovery and Planning | Plan Snyk Organization/Group structure | Task | 2023-11-01 | 2023-11-07 | 5 | Not started |  |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-1-discovery-and-planning/plan-organization-structure
Phase 1: Discovery and Planning | Determine member roles (default or custom) | Task | 2023-11-10 | 2023-11-16 | 5 | Not started |  |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-1-discovery-and-planning/determine-member-roles
Phase 1: Discovery and Planning | Decide SSO access model (Open to all, Require an Invite) | Task | 2023-11-10 | 2023-11-16 | 5 | Not started |  |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-1-discovery-and-planning/decide-sso-access
Phase 1: Discovery and Planning | Determine success metrics | Task | 2023-11-10 | 2023-11-16 | 5 | Not started |  |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-1-discovery-and-planning/plan-for-success
Phase 1: Discovery and Planning | Choose Initial Integrations (SCM, CI/CD) | Task | 2023-11-10 | 2023-11-16 | 5 | Not started |  |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-1-discovery-and-planning/choose-rollout-integrations
Phase 1: Discovery and Planning | Create rollout plan to the larger team | Task | 2023-11-10 | 2023-11-16 | 5 | Not started |  |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-1-discovery-and-planning/create-rollout-plan
Phase 1: Discovery and Planning | Determine Exception Process/Handling | Task | 2023-11-10 | 2023-11-16 | 5 | Not started |  |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-1-discovery-and-planning/create-rollout-plan
Phase 2: Configure Account | Configure SSO | Task | 2023-11-19 | 2023-11-23 | 5 | Not started |  |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-2-configure-account/configure-sso
Phase 2: Configure Account | Configure an Organization template | Task | 2023-11-19 | 2023-11-23 | 5 | Not started |  |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-2-configure-account/set-visibility-and-configure-an-organization-template
Phase 2: Configure Account | Configure notifications | Task | 2023-11-19 | 2023-11-23 | 5 | Not started |  |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-2-configure-account/set-visibility-and-configure-an-organization-template/configure-notifications
Phase 2: Configure Account | Enable Snyk Code | Task | 2023-11-19 | 2023-11-23 | 5 | Not started |  |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-2-configure-account/set-visibility-and-configure-an-organization-template/enable-snyk-code
Phase 2: Configure Account | Set integrations settings for visibility | Task | 2023-11-19 | 2023-11-23 | 5 | Not started |  |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-2-configure-account/set-visibility-and-configure-an-organization-template/configure-integrations
Phase 2: Configure Account | Create additional organizations from template | Task | 2023-11-26 | 2023-11-30 | 5 | Not started |  |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-2-configure-account/set-visibility-and-configure-an-organization-template/create-organizations
Phase 2: Configure Account | Apply security and license policies | Task | 2023-11-26 | 2023-11-30 | 5 | Not started |  |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-2-configure-account/apply-security-and-license-policies
Phase 3: Gain Visibility | Import projects into Snyk and gain visibility | Task | 2023-12-03 | 2023-12-14 | 10 | Not started |  |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-3-gain-visibility/import-projects
Phase 3: Gain Visibility | Optional: Add Project Tags or Project Attributes | Task | 2023-12-03 | 2023-12-14 | 10 | Not started |  |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-3-gain-visibility/add-project-tags-and-attributes
Phase 4: Create a Fix Strategy | Group issues & decide prioritization method | Task | 2023-12-17 | 2023-12-21 | 5 | Not started |  |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-4-create-a-fix-strategy
Phase 4: Create a Fix Strategy | Update your timeline based on fix strategy | Task | 2023-12-17 | 2023-12-21 | 5 | Not started |  |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-4-create-a-fix-strategy
Phase 5: Initial rollout to team | Notify the team by email/slack | Task | 2023-12-24 | 2023-12-24 | 1 | Not started |  |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-5-initial-rollout-to-team/notifying-the-team
Phase 5: Initial rollout to team | Consider Snyk Product training, or security training via Snyk Learn | Task | 2023-12-24 | 2024-01-04 | 10 | Not started |  |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-5-initial-rollout-to-team/developer-training-from-snyk
Phase 5: Initial rollout to team | Engage Development with IDE Plugins | Task | 2023-12-24 | 2024-01-04 | 10 | Not started |  |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-5-initial-rollout-to-team/engage-development-with-ide-plugins
Phase 6: Rolling out the prevention stage | Communicate prevention strategy to developers | Task | 2024-01-07 | 2024-01-07 | 1 | Not started |  |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-6-rolling-out-the-prevention-stage
Phase 6: Rolling out the prevention stage | Enable and configure Snyk on PRs | Task | 2024-01-07 | 2024-01-18 | 10 | Not started |  |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-6-rolling-out-the-prevention-stage/enable-and-configure-snyk-on-prs
Phase 6: Rolling out the prevention stage | Enable Snyk on pipelines to act as a gate using snyk test | Task | 2024-01-07 | 2024-01-18 | 10 | Not started |  |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-6-rolling-out-the-prevention-stage/add-and-configure-snyk-to-your-ci-cd-pipeline
Phase 6: Rolling out the prevention stage | If using containers, consider configuring Snyk on container pipeline/registry | Task | 2024-01-07 | 2024-01-18 | 10 | Not started |  |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-6-rolling-out-the-prevention-stage/custom-base-images
Phase 6: Rolling out the prevention stage | If using infrastructure code, consider configuring Snyk in pipeline/Terraform Cloud | Task | 2024-01-07 | 2024-01-18 | 10 | Not started |  |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-6-rolling-out-the-prevention-stage/infrastructure-as-code
Phase 7: Triage/ignores/Fixes | Implement the fix strategy created in Phase 4 & apply ignores as needed | Task | 2024-01-21 | 2024-02-15 | 20 | Not started |  |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-7-triages-ignores-and-fixes
Phase 7: Triage/ignores/Fixes | Track the progress of your teams using reports | Task | 2024-01-21 | 2024-02-15 | 20 | Not started |  |  | https://docs.snyk.io/enterprise-setup/enterprise-implementation-guide/phase-7-triages-ignores-and-fixes
Formulas:
END DATE = WORKDAY.INTL([START DATE],[DURATION (Days)]-1)
START DATE = [START DATE, row above]
Note on D2: Please only change cell C2 to reflect the actual start date and the rest of the timeline will get aligned accordingly

## Jira
PHASE | Summary | START DATE | END DATE | DURATION (Days) | STATUS | OWNER | RESOURCE (Page in guide) | NOTES
Phase 1: Discovery and Planning | Connect with your Snyk account manager | 2023-11-01 | 2023-11-07 | 5 | Not started |  | Page 8
Phase 1: Discovery and Planning | Confirm Snyk License is Applied with Account Manager | 2023-11-01 | 2023-11-07 | 5 | Not started |  | Page 8
Phase 1: Discovery and Planning | Identify business critical applications | 2023-11-01 | 2023-11-07 | 5 | Not started |  | Page 9
Phase 1: Discovery and Planning | Confirm Internal points of contact for SSO, SCM, CI/CD integrations | 2023-11-01 | 2023-11-07 | 5 | Not started |  | Page 9
Phase 1: Discovery and Planning | Identify internal stakeholders and responsibilities | 2023-11-01 | 2023-11-07 | 5 | Not started |  | Page 9-10
Phase 1: Discovery and Planning | Plan Snyk Organization/Group structure | 2023-11-01 | 2023-11-07 | 5 | Not started |  | Page 11-12
Phase 1: Discovery and Planning | Determine member roles (default or custom) | 2023-11-10 | 2023-11-16 | 5 | Not started |  | Page 13-14
Phase 1: Discovery and Planning | Determine SSO access model (Open to all, Require an Invite) | 2023-11-10 | 2023-11-16 | 5 | Not started |  | Page 15
Phase 1: Discovery and Planning | Determine success metrics | 2023-11-10 | 2023-11-16 | 5 | Not started |  | Page 16-17
Phase 1: Discovery and Planning | Choose Initial Integrations (SCM, CI/CD) | 2023-11-10 | 2023-11-16 | 5 | Not started |  | Page 18-21
Phase 1: Discovery and Planning | Create rollout plan to the larger team | 2023-11-10 | 2023-11-16 | 5 | Not started |  | Page 22-23
Phase 1: Discovery and Planning | Determine Exception Process/Handling | 2023-11-10 | 2023-11-16 | 5 | Not started |  | Page 23
Phase 2: Configure Account | Configure SSO | 2023-11-19 | 2023-11-23 | 5 | Not started |  | Page 25
Phase 2: Configure Account | Configure an Organization template | 2023-11-19 | 2023-11-23 | 5 | Not started |  | Page 26-28
Phase 2: Configure Account | Configure notifications | 2023-11-19 | 2023-11-23 | 5 | Not started |  | Page 29-30
Phase 2: Configure Account | Enable Snyk Code | 2023-11-19 | 2023-11-23 | 5 | Not started |  | Page 31
Phase 2: Configure Account | Set integrations settings for visibility | 2023-11-19 | 2023-11-23 | 5 | Not started |  | Page 32-34
Phase 2: Configure Account | Create additional organizations from template | 2023-11-26 | 2023-11-30 | 5 | Not started |  | Page 35
Phase 2: Configure Account | Apply security and license policies | 2023-11-26 | 2023-11-30 | 5 | Not started |  | Page 36
Phase 3: Gain Visibility | Import projects into Snyk and gain visibility | 2023-12-03 | 2023-12-14 | 10 | Not started |  | Page 38-40
Phase 3: Gain Visibility | Optional: Add Project Tags or Project Attributes | 2023-12-03 | 2023-12-14 | 10 | Not started |  | Page 41
Phase 4: Create a Fix Strategy | Group issues & decide prioritization method | 2023-12-17 | 2023-12-21 | 5 | Not started |  | Page 42-44
Phase 4: Create a Fix Strategy | Update your timeline based on fix strategy | 2023-12-17 | 2023-12-21 | 5 | Not started |  | Page 44
Phase 5: Initial rollout to team | Notify the team by email/slack | 2023-12-24 | 2023-12-24 | 1 | Not started |  | Page 46-48
Phase 5: Initial rollout to team | Consider Snyk Product, or security training via Snyk Learn | 2023-12-24 | 2024-01-04 | 10 | Not started |  | Page 49
Phase 5: Initial rollout to team | Engage Development with IDE Plugins | 2023-12-24 | 2024-01-04 | 10 | Not started |  | Page 50
Phase 6: Rolling out the prevention stage | Communicate prevention strategy to developers | 2024-01-07 | 2024-01-07 | 1 | Not started |  | Page 52, 60-61
Phase 6: Rolling out the prevention stage | Enable and configure Snyk on PRs | 2024-01-07 | 2024-01-18 | 10 | Not started |  | Page 54
Phase 6: Rolling out the prevention stage | Enable Snyk on pipelines to act as a gate using snyk test | 2024-01-07 | 2024-01-18 | 10 | Not started |  | Page 56
Phase 6: Rolling out the prevention stage | If using containers, consider configuring Snyk on container pipeline/registry | 2024-01-07 | 2024-01-18 | 10 | Not started |  | Pag 58
Phase 6: Rolling out the prevention stage | If using infrastructure code, consider configuring Snyk in pipeline/Terraform Cloud | 2024-01-07 | 2024-01-18 | 10 | Not started |  | Page 59
Phase 7: Triage/ignores/Fixes | Implement fix strategy & apply ignores as needed | 2024-01-21 | 2024-02-15 | 20 | Not started |  | Page 62
Phase 7: Triage/ignores/Fixes | Track the progress of your teams using reports | 2024-01-21 | 2024-02-15 | 20 | Not started |  | Page 63
Formulas:
END DATE = WORKDAY.INTL([START DATE],[DURATION (Days)]-1)
START DATE = [START DATE, row above]
Note on C2: Please only change cell C2 to reflect the actual start date and the rest of the timeline will get aligned accordingly

## Full
PHASE | TASK | START DATE | END DATE | SNYK OWNER | CUSTOMER OWNER | DURATION (Days) | STATUS | RESOURCES (Articles) | RESOURCES (Videos) | RESOURCES (Tooling/Scripts) | NOTES
Phase 1: Discovery | Confirm points of contact and roles (champions, admins) | 2023-12-31 | 2024-01-05 | AE | TBD | 5 | Open
Phase 1: Discovery | Determine project import strategy (CLI, API, Git repo integration) | 2023-12-31 | 2024-01-05 | TSM | TBD | 5 | Open | https://docs.snyk.io/integrations |  | https://docs.snyk.io/snyk-api-info/other-tools/tool-snyk-api-import
Phase 1: Discovery | Educate customer on Snyk organization structure (organize based on products, teams, etc) | 2023-12-31 | 2024-01-05 | TSM | TBD | 5 | Open | Manage Groups and Organizations - Snyk User Docs |  |  | https://training.snyk.io/learn/course/snyk-account-structure/account-structure-considerations/an-overview-of-account-structure?page=1
Phase 1: Discovery | Educate customer on SSO options (based on policy, pick relevant SSO option to give access to users) | 2023-12-31 | 2024-01-05 | TSM | TBD | 5 | Open | Set up Single Sign-On (SSO) for authentication - Snyk User Docs |  |  | https://training.snyk.io/learn/course/sso/authentication-to-snyk/an-overview-of-authentication-and-provisioning?page=1
Phase 1: Discovery | Consider SSO options with custom mapping | 2023-12-31 | 2024-01-05 | TSM | TBD | 5 | Open | Custom Mapping Option - Snyk User Docs
Phase 1: Discovery | Customer to fill in Snyk Discovery Document | 2023-12-31 | 2024-01-05 | TSM | TBD | 5 | Open
Phase 1: Discovery | Confirm how many repos have to be imported | 2023-12-31 | 2024-01-05 | TSM | TBD | 5 | Open | https://docs.snyk.io/manage-issues/introduction-to-snyk-projects
Phase 1: Discovery | Confirm with customer how their developlment and engineering teams are structured, e.g. per team, per application, per agile tribe, etc. | 2023-12-31 | 2024-01-05 | TSM | TBD | 5 | Open
Phase 1: Discovery | Confirm AppSec governance (centralized or autonomous) | 2023-12-31 | 2024-01-05 | TSM | TSM | 5 | Open
Phase 1: Discovery | Define project success metrics, onboarding objectives and milestones with due dates | 2023-12-31 | 2024-01-05 | TSM | TBD | 5 | Open
Phase 1: Discovery | Identify pilot group(s) | 2023-12-31 | 2024-01-05 | TSM | TBD | 5 | Open
Phase 1: Discovery | Determine SDLC Integration Points (IDE, Git Repo, CI/CD, Container Registry) | 2023-12-31 | 2024-01-05 | TSM | TBD | 5 | Open | Integrate with Snyk
Phase 1: Discovery | Define Snyk policies (ex in Git: fail PR when a fix is available) | 2023-12-31 | 2024-01-05 | TSM | TBD | 5 | Open
Phase 1: Discovery | DSO Capability Assessment | 2024-01-14 | 2024-02-03 | TSM | TBD | 20 | Open
Phase 1: Discovery | Snyk Container Specific: Describe the images ownership and deployment process in your organisation | 2024-01-14 | 2024-02-03 | TSM | TBD | 20 | Open
Phase 1: Discovery | Snyk IaC Specific: Describe the ownership of your IaC templates in your organisation | 2024-01-14 | 2024-02-03 | TSM | TBD | 20 | Open
Phase 2: Accounts Configuration | Set up SSO | 2024-01-14 | 2024-01-19 | TSM | TBD | 5 | Open | https://docs.snyk.io/enterprise-setup/set-up-single-sign-on-sso-for-authentication |  |  | *assuming all info is collected
Phase 2: Accounts Configuration | Optional: Set up Custom Mapping (SSO) | 2024-01-14 | 2024-01-19 | TSM | TBD | 5 | Open | https://docs.snyk.io/enterprise-setup/using-single-sign-on-sso-for-authentication/custom-mapping-option
Phase 2: Accounts Configuration | Create organizations with desired settings, duplicate for additional orgs | 2024-01-14 | 2024-01-19 | TSM | TBD | 5 | Open | https://docs.snyk.io/snyk-admin/manage-groups-and-organizations/manage-organizations#create-an-organization |  | All projects these tasks can be achieved by the next tool - https://github.com/snyk-tech-services/snyk-api-import
Phase 2: Accounts Configuration | Set account for visibility stage (disable notifications, Snyk tests on PRs and autofix PRs, set notifications for admin only - weekly reports) | 2024-01-14 | 2024-01-19 | TSM | - | 5 | Open
Phase 2: Accounts Configuration | Set broker integrations for SCM | 2024-01-14 | 2024-01-19 | TSM | TBD | 5 | Open | https://docs.snyk.io/enterprise-setup/snyk-broker
Phase 2: Accounts Configuration | Set broker integrations for Private Registry (mark status as Skipped if not relevant) | 2024-01-14 | 2024-01-19 | TSM | TBD | 5 | Open | https://docs.snyk.io/enterprise-setup/snyk-broker/install-and-configure-snyk-broker/artifactory-repository-install-and-configure-broker/set-up-snyk-broker-with-artifactory-repository
Phase 2: Accounts Configuration | Set broker integrations for Container Registry (mark status as Skipped if not relevant) | 2024-01-14 | 2024-01-19 | TSM | TBD | 5 | Open | https://docs.snyk.io/enterprise-setup/snyk-broker/snyk-broker-container-registry-agent
Phase 2: Accounts Configuration | Set broker integrations for Jira (mark status as Skipped if not relevant) | 2024-01-14 | 2024-01-19 | TSM | TBD | 5 | Open | https://docs.snyk.io/enterprise-setup/snyk-broker/install-and-configure-snyk-broker/jira-install-and-configure-broker/setup-broker-with-jira
Phase 2: Accounts Configuration | Set SDLC Integration Points (IDE, Git Repo, CI/CD, Container Registry) | 2024-01-14 | 2024-01-19 | TSM | TBD | 5 | Open | https://docs.snyk.io/integrations
Phase 2: Accounts Configuration | Start onboarding all projects | 2024-01-14 | 2024-02-04 | TSM | TBD | 21 | Open
Phase 2: Accounts Configuration | Consider tagging strategy (can later query data to sort and get more granular view) | 2024-01-14 | 2024-01-19 | TSM | - | 5 | Open | https://docs.snyk.io/manage-issues/introduction-to-snyk-projects/project-tags |  | https://github.com/snyk-labs/snyk-tags-tool
Phase 2: Accounts Configuration | License policies (tag specific open source licenses that don't comply with company policy | 2024-01-14 | 2024-01-19 | TSM | TBD | 5 | Open | https://docs.snyk.io/manage-issues/policies/license-policies
Phase 3: Rollout to Pilot Team | Snyk Container Specific: In case that your org as a pipeline to submit new images to your container registry, integrate Snyk to this workflow to set a gatekeeper to block new images from being submitted to the registry and shit left the risk | 2024-01-28 | 2024-02-17 | TSM | TBD | 20 | Open
Phase 3: Rollout to Pilot Team | Snyk IaC Specific: In case that your org maintain IaC templates repo, integrate Snyk to the pipeline that cover these repos | 2024-01-28 | 2024-02-17 | TSM | TBD | 20 | Open
Phase 3: Rollout to Pilot Team | Snyk IaC Specific: If you are using terraform Cloud, set the integration | 2024-01-28 | 2024-02-17 | TSM | TBD | 20 | Open
Phase 3: Rollout to Pilot Team | Apply Snyk and License Policies | 2024-01-28 | 2024-02-02 | TSM | TBD | 5 | Open | https://docs.snyk.io/manage-issues/policies
Phase 3: Rollout to Pilot Team | Educate teams on why Snyk and why now | 2024-01-28 | 2024-02-02 | TSM | TBD | 5 | Open
Phase 3: Rollout to Pilot Team | Team training | 2024-01-28 | 2024-02-02 | TSM | TBD | 5 | Open
Phase 3: Rollout to Pilot Team | Address gaps/issues (office hours, special topic sessions) | 2024-01-28 | 2024-02-02 | TBD | TBD | 5 | Open
Phase 4: Rollout to remaining teams: apply key learnings from pilot team(s) | Educate teams on why Snyk and why now | 2024-02-11 | 2024-05-11 | TSM | TBD | 90 | Open
Phase 4: Rollout to remaining teams: apply key learnings from pilot team(s) | Team Training | 2024-02-11 | 2024-05-11 | TSM | TBD | 90 | Open |  |  |  | Up to 500 devs a month
Phase 4: Rollout to remaining teams: apply key learnings from pilot team(s) | Stranger Danger Session | 2024-02-11 | 2024-02-16 | TBD | TBD | 5 | Open | https://docs.google.com/presentation/d/1bm1yqSr1CyDmO46ffALSE-R32R0q21VgvP2KCPzbI_g/edit | https://www.youtube.com/watch?v=pCaOY8RC_Ag
Phase 4: Rollout to remaining teams: apply key learnings from pilot team(s) | Address gaps/issues (office hours, special topic sessions) | 2024-02-11 | 2024-02-16 | TBD | TBD | 5 | Open
Phase 4: Rollout to remaining teams: apply key learnings from pilot team(s) | Notification settings (email and/MS notifications for vulnerability alerts) | 2024-02-11 | 2024-02-16 | TSM | TBD | 5 | Open | https://docs.snyk.io/snyk-admin/manage-notifications
Phase 5: Setting The Account For The prevention Stage | Enable the teams about the prevention campaign | 2024-02-25 | 2024-03-01 | TSM | TBD | 5 | Open
Phase 5: Setting The Account For The prevention Stage | Enable Test on PRs. | 2024-02-25 | 2024-03-01 | TSM | TBD | 5 | Open |  | See Video
Phase 5: Setting The Account For The prevention Stage | Enforce gatekeeper process in the CI/PR Check | 2024-02-25 | 2024-03-01 | TSM | TBD | 5 | Open |  | See Video
Phase 5: Setting The Account For The prevention Stage | Review analytics about how many PRs/builds were blocked by snyk (use your SCM/CI to get the data, or contact your TSM/AE to get the data) in addition you can review how many new issues were introduced to every org from the reporting view of the group | 2024-02-25 | 2024-02-26 | TSM | TBD | 1 | Open
Phase 6: Triage, ignore and Fixing | Enable Fix PRs | 2024-03-10 | 2024-03-11 | TSM | TBD | 1 | Open | https://docs.snyk.io/scan-application-code/snyk-open-source/open-source-basics/fix-pull-requests-for-known-vulnerabilities-backlog
Phase 6: Triage, ignore and Fixing | Run a weekly triage process with in each team, and create jira tickets for them to fix backlog issue | 2024-03-10 | 2024-04-09 | TSM | TBD | 30 | Open
Phase 6: Triage, ignore and Fixing | Review Snyk reports to observe team's performance | 2024-03-10 | 2024-03-11 | TSM | TBD | 1 | Open | https://docs.snyk.io/manage-issues/reporting/available-snyk-reports
Phase 7 Optimisation | Leverage Snyk APIs/security policy to run bulk ignores | 2024-03-24 | 2024-03-31 | TSM | TBD | 7 | Open
Phase 7 Optimisation | Leverage Snyk Pysyk to create jira tickets to multi issues | 2024-03-24 | 2024-03-31 | TSM | TBD | 7 | Open | Read more
Phase 7 Optimisation | Introduce Snyk IDE plugins to your developers | 2024-03-24 | 2024-03-31 | TSM | TBD | 7 | Open | https://www.youtube.com/watch?v=jzUJS6S6H48
Formulas:
END DATE = [START DATE]+[DURATION (Days)]
START DATE = [START DATE, row above]
Note on C2: Please only change cell C2 to reflect the actual start date and the rest of the timeline will get aligned accordingly