## Overview
Burndown Chart
SPRINT INFORMATION |  | CURRENT SPRINTINFO
Field | Value
Start date | 2019-09-15 | End date Sprint | 2019-09-29
Sprint length (gross) | 14 | Sprint length (net) | 10
Holidays | 0 | Available hours Total | 240
Team size | 4 | Total storypoints | 62
Maximum team capacity | 80% | Open Storypoints | 13
Daily working time in hours | 7.5 | Number of stories in the sprint | 8
Number of the current sprint | 1 | Completed Stories | 7
Team members
Jan
Peter
Claudia
Paul
Max
Status
In progress
Done
Open
Please enter the key data for your project here. It is important that you always keep this information up to date!
General information:
Start date
Sprint length (specify number of gross days)
Vacation days in the sprint period
Your team size
The maximum, desired workload of the team
The daily working hours
Enter the names of your team members here:
You can define the status of the tasks here

## Backlog
| Sprint start | 2019-09-15
| Sprint time in days | 10
| Velocity | 80
Sprint ID | Backlog Item ID | StoryPoints | Story | Assigned to | Status | Completed on | Sprint day | Help column
1 | 1 | 4 | a | Jan | erledigt | 2019-09-16 | 1 | y
1 | 2 | 8 | b |  |  | 2019-09-22 | 7 | y
1 | 3 | 3 | c |  |  | 2019-09-18 | 3 | y
1 | 4 | 8 | d |  |  | 2019-09-16 | 1 | y
1 | 5 | 13 | e |  |  |  |  | n
1 | 6 | 5 | f |  |  | 2019-09-20 | 5 | y
1 | 7 | 8 | g |  |  | 2019-09-16 | 1 | y
1 | 8 | 13 | h |  |  | 2019-09-21 | 6 | y
2 | [7 empty] | n
2 | [7 empty] | n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
Storypoints |  | 62
Enter your current velocity from the last sprint in Storypoints here. The velocity describes the number of storypoints you completed during your last sprint.
Always filter the current sprint according to the sprint ID.
Describe your backlog item, estimate the associated storypoints and assign it to a responsible person.
Enter the date when a story was completed here.

## Auxiliary tab - BurnDownTable
Storypoints
Sprint day | Ideal line | Real course | Finished SP | Aktuell
0 | 62 | 62 | 0 | y
1 | 55.8 | 42 | 20 | y
2 | 49.6 | 42 | 0 | y
3 | 43.4 | 39 | 3 | y
4 | 37.2 | 39 | 0 | y
5 | 31 | 34 | 5 | y
6 | 24.8 | 21 | 13 | y
7 | 18.6 | 13 | 8 | y
8 | 12.4 | 13 | 0 | y
9 | 6.2 | 13 | 0 | y
10 | 0 | 13 | 0 | y
Outcome |  |  | 49 | 11