## 1. Contract processes
Contract processes
Contract management & archiving
Contract manager
Accountabilities
Recurring activities
Storage platform
Archiving structure
Contract processes
Approval processes
Legal regulations
Welcome to the contract management template!
This template helps you to present your contract management clearly and manage it effectively.
Contract management is made up of three aspects:
I. Administration - The overview of contract scope and content
II. Controlling - The risk assessment of contracts, risk mitigation measures and evaluation using key performance indicators (KPIs)
III. Archiving - The secure storage of documents in a structured filing system
While archiving is covered outside of this template, the template focuses primarily on the first two points. However, we start with some reflective questions on the criteria for archiving. This is followed by data entry for managing contracts and an automatically generated evaluation for controlling.
To a successful contract management!
Who is responsible for contract management?
What are the responsibilities of the contract manager role?
What regular tasks or deadlines need to be considered?
Where are contract documents (physical / electronic) stored?
What logic is used for archiving contracts?
What contract management processes do you use? Where are these documented?
Which approvals are relevant for your contracts?
Which legal regulations in the area of contract management are binding for you? (e.g. reporting and control obligations, data protection, audit-proof archiving, minimum and maximum retention periods, etc.)?
Overview of spreadsheets:
1. Contract processes Reflection on contract management & archiving [III]
2. Supplier data Contact details of suppliers [I]
3. Customer data Contact data of customers [I]
4. Contract terms Contractual partners, contract type and duration [I]
5. Contract costs Payment methods, deadlines, and amount [I]
6. Contract delivery Scope of delivery and quality control [II]
7. Risk management Contract risk assessment and mitigation [II]
8. Evaluation Dashboard of key figures [II]
LISTS Data for drop-down menus [BEWARE OF CHANGES]

## 2. Supplier data
Supplier data | [19 empty] | Sum: | 3300 | 4500 | 3
Identification |  | Contact details | [12 empty] | Bank details |  |  |  |  | Further information | Evaluation
No. | Supplier ID | Company | VAT number | Commercial register | Commercial register number | Contact person | Phone | Email | Street | No. | Postal code | Place | Region | Country | Bank | Account number | Bank code | IBAN | BIC | Comment | Σ Contract value (contractually bound) | Σ Contract value (weighted) | Supplier contracts
1 | S001 | Microsoft Corporation |  |  |  | Mr Smith | 123 456 789 | smith@Microsoft.com | Microsoft Way | 1 | 98052 | Redmond | WA | USA | [6 empty] | 3300 | 3300 | 2
2 | S002 | Deutsche Telekom AG |  |  |  | Mrs Jones | 234 567 890 | jones@Telekom.com | Friedrich-Ebert-Allee | 140 | 53113 | Bonn | NRW | Deutschland | [6 empty] | 0 | 1200 | 1
3 | [20 empty] | 0 | 0
4 | [20 empty] | 0 | 0
5 | [20 empty] | 0 | 0
6 | [20 empty] | 0 | 0
7 | [20 empty] | 0 | 0
8 | [20 empty] | 0 | 0
9 | [20 empty] | 0 | 0
10 | [20 empty] | 0 | 0
11 | [20 empty] | 0 | 0
12 | [20 empty] | 0 | 0
13 | [20 empty] | 0 | 0
14 | [20 empty] | 0 | 0
15 | [20 empty] | 0 | 0
16 | [20 empty] | 0 | 0
17 | [20 empty] | 0 | 0
18 | [20 empty] | 0 | 0
19 | [20 empty] | 0 | 0
20 | [20 empty] | 0 | 0
21 | [20 empty] | 0 | 0
22 | [20 empty] | 0 | 0
23 | [20 empty] | 0 | 0
24 | [20 empty] | 0 | 0
25 | [20 empty] | 0 | 0
26 | [20 empty] | 0 | 0
27 | [20 empty] | 0 | 0
28 | [20 empty] | 0 | 0
29 | [20 empty] | 0 | 0
30 | [20 empty] | 0 | 0
31 | [20 empty] | 0 | 0
32 | [20 empty] | 0 | 0
33 | [20 empty] | 0 | 0
34 | [20 empty] | 0 | 0
35 | [20 empty] | 0 | 0
36 | [20 empty] | 0 | 0
37 | [20 empty] | 0 | 0
38 | [20 empty] | 0 | 0
39 | [20 empty] | 0 | 0
40 | [20 empty] | 0 | 0
41 | [20 empty] | 0 | 0
42 | [20 empty] | 0 | 0
43 | [20 empty] | 0 | 0
44 | [20 empty] | 0 | 0
45 | [20 empty] | 0 | 0
46 | [20 empty] | 0 | 0
47 | [20 empty] | 0 | 0
48 | [20 empty] | 0 | 0
49 | [20 empty] | 0 | 0
50 | [20 empty] | 0 | 0
51 | [20 empty] | 0 | 0
52 | [20 empty] | 0 | 0
53 | [20 empty] | 0 | 0
54 | [20 empty] | 0 | 0
55 | [20 empty] | 0 | 0
56 | [20 empty] | 0 | 0
57 | [20 empty] | 0 | 0
58 | [20 empty] | 0 | 0
59 | [20 empty] | 0 | 0
60 | [20 empty] | 0 | 0
61 | [20 empty] | 0 | 0
62 | [20 empty] | 0 | 0
63 | [20 empty] | 0 | 0
64 | [20 empty] | 0 | 0
65 | [20 empty] | 0 | 0
66 | [20 empty] | 0 | 0
67 | [20 empty] | 0 | 0
68 | [20 empty] | 0 | 0
69 | [20 empty] | 0 | 0
70 | [20 empty] | 0 | 0
71 | [20 empty] | 0 | 0
72 | [20 empty] | 0 | 0
73 | [20 empty] | 0 | 0
74 | [20 empty] | 0 | 0
75 | [20 empty] | 0 | 0
76 | [20 empty] | 0 | 0
77 | [20 empty] | 0 | 0
78 | [20 empty] | 0 | 0
79 | [20 empty] | 0 | 0
80 | [20 empty] | 0 | 0
81 | [20 empty] | 0 | 0
82 | [20 empty] | 0 | 0
83 | [20 empty] | 0 | 0
84 | [20 empty] | 0 | 0
85 | [20 empty] | 0 | 0
86 | [20 empty] | 0 | 0
87 | [20 empty] | 0 | 0
88 | [20 empty] | 0 | 0
89 | [20 empty] | 0 | 0
90 | [20 empty] | 0 | 0
91 | [20 empty] | 0 | 0
92 | [20 empty] | 0 | 0
93 | [20 empty] | 0 | 0
94 | [20 empty] | 0 | 0
95 | [20 empty] | 0 | 0
96 | [20 empty] | 0 | 0
97 | [20 empty] | 0 | 0
98 | [20 empty] | 0 | 0
99 | [20 empty] | 0 | 0
100 | [20 empty] | 0 | 0
In this 'Supplier data' worksheet, the suppliers' contact details are stored.
This basic data serves as input for the 'Contract register' worksheet.
Give the supplier an unique identification number.
Enter the contact details of the supplier.
Enter the supplier's bank details (optional).
The total secured amount of the contracts per supplier is displayed here.
Number of contracts per supplier.
The weighted total amount of contracts per supplier is displayed here.
Sum of the contract values of all contractually bound suppliers.
Sum of the weighted contract values of all suppliers.
Total number of supplier contracts.

## 3. Customer data
Customer data | [20 empty] | Sum: | 5000 | 10400 | 2
Identification |  | Contact details | [13 empty] | Bankdaten |  |  |  |  | Further information | Evaluation
No. | Customer ID | Company | VAT number | Commercial register | Commercial register number | Contact person | Phone | Email | Street | No. | No. | Postal code | Place | Region | Country | Bank | Account number | Bank code | IBAN | BIC | Comment | Σ Contract value (contractually bound) | Σ Contract value (weighted) | Customer contracts
1 | C001 | ABC LLC |  |  |  | Mr Wolf | 111 222 333 | wolf@abc.de | Musterstraße | 1 | 123456 | [10 empty] | 5000 | 10400 | 2
2 | [21 empty] | 0 | 0
3 | [21 empty] | 0 | 0
4 | [21 empty] | 0 | 0
5 | [21 empty] | 0 | 0
6 | [21 empty] | 0 | 0
7 | [21 empty] | 0 | 0
8 | [21 empty] | 0 | 0
9 | [21 empty] | 0 | 0
10 | [21 empty] | 0 | 0
11 | [21 empty] | 0 | 0
12 | [21 empty] | 0 | 0
13 | [21 empty] | 0 | 0
14 | [21 empty] | 0 | 0
15 | [21 empty] | 0 | 0
16 | [21 empty] | 0 | 0
17 | [21 empty] | 0 | 0
18 | [21 empty] | 0 | 0
19 | [21 empty] | 0 | 0
20 | [21 empty] | 0 | 0
21 | [21 empty] | 0 | 0
22 | [21 empty] | 0 | 0
23 | [21 empty] | 0 | 0
24 | [21 empty] | 0 | 0
25 | [21 empty] | 0 | 0
26 | [21 empty] | 0 | 0
27 | [21 empty] | 0 | 0
28 | [21 empty] | 0 | 0
29 | [21 empty] | 0 | 0
30 | [21 empty] | 0 | 0
31 | [21 empty] | 0 | 0
32 | [21 empty] | 0 | 0
33 | [21 empty] | 0 | 0
34 | [21 empty] | 0 | 0
35 | [21 empty] | 0 | 0
36 | [21 empty] | 0 | 0
37 | [21 empty] | 0 | 0
38 | [21 empty] | 0 | 0
39 | [21 empty] | 0 | 0
40 | [21 empty] | 0 | 0
41 | [21 empty] | 0 | 0
42 | [21 empty] | 0 | 0
43 | [21 empty] | 0 | 0
44 | [21 empty] | 0 | 0
45 | [21 empty] | 0 | 0
46 | [21 empty] | 0 | 0
47 | [21 empty] | 0 | 0
48 | [21 empty] | 0 | 0
49 | [21 empty] | 0 | 0
50 | [21 empty] | 0 | 0
51 | [21 empty] | 0 | 0
52 | [21 empty] | 0 | 0
53 | [21 empty] | 0 | 0
54 | [21 empty] | 0 | 0
55 | [21 empty] | 0 | 0
56 | [21 empty] | 0 | 0
57 | [21 empty] | 0 | 0
58 | [21 empty] | 0 | 0
59 | [21 empty] | 0 | 0
60 | [21 empty] | 0 | 0
61 | [21 empty] | 0 | 0
62 | [21 empty] | 0 | 0
63 | [21 empty] | 0 | 0
64 | [21 empty] | 0 | 0
65 | [21 empty] | 0 | 0
66 | [21 empty] | 0 | 0
67 | [21 empty] | 0 | 0
68 | [21 empty] | 0 | 0
69 | [21 empty] | 0 | 0
70 | [21 empty] | 0 | 0
71 | [21 empty] | 0 | 0
72 | [21 empty] | 0 | 0
73 | [21 empty] | 0 | 0
74 | [21 empty] | 0 | 0
75 | [21 empty] | 0 | 0
76 | [21 empty] | 0 | 0
77 | [21 empty] | 0 | 0
78 | [21 empty] | 0 | 0
79 | [21 empty] | 0 | 0
80 | [21 empty] | 0 | 0
81 | [21 empty] | 0 | 0
82 | [21 empty] | 0 | 0
83 | [21 empty] | 0 | 0
84 | [21 empty] | 0 | 0
85 | [21 empty] | 0 | 0
86 | [21 empty] | 0 | 0
87 | [21 empty] | 0 | 0
88 | [21 empty] | 0 | 0
89 | [21 empty] | 0 | 0
90 | [21 empty] | 0 | 0
91 | [21 empty] | 0 | 0
92 | [21 empty] | 0 | 0
93 | [21 empty] | 0 | 0
94 | [21 empty] | 0 | 0
95 | [21 empty] | 0 | 0
96 | [21 empty] | 0 | 0
97 | [21 empty] | 0 | 0
98 | [21 empty] | 0 | 0
99 | [21 empty] | 0 | 0
100 | [21 empty] | 0 | 0
In this 'Customer data' worksheet, the customers' contact details are stored.
This basic data serves as input for the 'Contract register' worksheet.
Give the customer an unique identification number.
Enter the customer's contact details.
Enter the customer's bank details (optional).
The total secured amount of the contracts per customer is displayed here.
Number of contracts per customer.
The weighted total amount of contracts per customer is displayed here.
Sum of the contract values of all contractually bound customers.
Sum of the weighted contract values of all customers.
Total number of customer contracts.

## 4. Contract terms
Contract terms
Contract data | [6 empty] | Contract partner |  |  |  |  | Contract type |  |  |  | Contract duration
No. | Contract ID | Contract name | Purchasing / Sales | Status | Probability [%] | Filing location | Supplier / Customer ID | Company | Contact person | Phone | Email | Internal contact person | Type of goods | Delievery interval | Delievery frequency | Start date | End date | Duration [Month] | Remaining duration [Month] | Extension | Comment | Minimum duration | Notice period
1 | #001 | Microsoft Office 365 License | Purchasing | Contract terminated | 100% |  | S001 | Microsoft Corporation | Mr Smith | 123 456 789 | smith@Microsoft.com | Mr Purchase | License | Regularly | Daily | 2023-07-01 | 2023-07-31 | 0 | -4 | Yes | Trial month resulted in 6 month subscription. See contract ID #001a | 1 month
2 | #001a | Microsoft Office 365 License | Purchasing | Contractually bound | 100% |  | S001 | Microsoft Corporation | Mr Smith | 123 456 789 | smith@Microsoft.com | Mr Purchase | License | Regularly | Daily | 2023-08-01 | 2024-01-31 | 6 | 3 |  |  | 6 months
3 | #002 | Cell phone contracts | Purchasing | In negotiation | 50% |  | S002 | Deutsche Telekom AG | Mrs Jones | 234 567 890 | jones@Telekom.com | Mr Purchase | Service | Regularly | Daily | 2023-07-01 | 2025-06-30 | 24 | 20 |  |  | 2 years | 1 month
4 | #003 | Webseite concept | Sales | Contractually bound | 100% |  | C001 | ABC LLC | Mr Wolf | 111 222 333 | wolf@abc.de | Mrs Sales | Good | One-off |  | 2023-08-01 | 2023-10-31 | 2 | -1
5 | #004 | Webseite maintenance | Sales | Draft contract available | 90% |  | C001 | ABC LLC | Mr Wolf | 111 222 333 | wolf@abc.de | Mrs Sales | Service | Regularly | Monthly | 2023-11-01 | 2024-10-30 | 12 | 12 |  |  | 12 months | 3 months
6 | [7 empty] | #N/A | #N/A | #N/A | #N/A
7 | [7 empty] | #N/A | #N/A | #N/A | #N/A
8 | [7 empty] | #N/A | #N/A | #N/A | #N/A
9 | [7 empty] | #N/A | #N/A | #N/A | #N/A
10 | [7 empty] | #N/A | #N/A | #N/A | #N/A
11 | [7 empty] | #N/A | #N/A | #N/A | #N/A
12 | [7 empty] | #N/A | #N/A | #N/A | #N/A
13 | [7 empty] | #N/A | #N/A | #N/A | #N/A
14 | [7 empty] | #N/A | #N/A | #N/A | #N/A
15 | [7 empty] | #N/A | #N/A | #N/A | #N/A
16 | [7 empty] | #N/A | #N/A | #N/A | #N/A
17 | [7 empty] | #N/A | #N/A | #N/A | #N/A
18 | [7 empty] | #N/A | #N/A | #N/A | #N/A
19 | [7 empty] | #N/A | #N/A | #N/A | #N/A
20 | [7 empty] | #N/A | #N/A | #N/A | #N/A
21 | [7 empty] | #N/A | #N/A | #N/A | #N/A
22 | [7 empty] | #N/A | #N/A | #N/A | #N/A
23 | [7 empty] | #N/A | #N/A | #N/A | #N/A
24 | [7 empty] | #N/A | #N/A | #N/A | #N/A
25 | [7 empty] | #N/A | #N/A | #N/A | #N/A
26 | [7 empty] | #N/A | #N/A | #N/A | #N/A
27 | [7 empty] | #N/A | #N/A | #N/A | #N/A
28 | [7 empty] | #N/A | #N/A | #N/A | #N/A
29 | [7 empty] | #N/A | #N/A | #N/A | #N/A
30 | [7 empty] | #N/A | #N/A | #N/A | #N/A
31 | [7 empty] | #N/A | #N/A | #N/A | #N/A
32 | [7 empty] | #N/A | #N/A | #N/A | #N/A
33 | [7 empty] | #N/A | #N/A | #N/A | #N/A
34 | [7 empty] | #N/A | #N/A | #N/A | #N/A
35 | [7 empty] | #N/A | #N/A | #N/A | #N/A
36 | [7 empty] | #N/A | #N/A | #N/A | #N/A
37 | [7 empty] | #N/A | #N/A | #N/A | #N/A
38 | [7 empty] | #N/A | #N/A | #N/A | #N/A
39 | [7 empty] | #N/A | #N/A | #N/A | #N/A
40 | [7 empty] | #N/A | #N/A | #N/A | #N/A
41 | [7 empty] | #N/A | #N/A | #N/A | #N/A
42 | [7 empty] | #N/A | #N/A | #N/A | #N/A
43 | [7 empty] | #N/A | #N/A | #N/A | #N/A
44 | [7 empty] | #N/A | #N/A | #N/A | #N/A
45 | [7 empty] | #N/A | #N/A | #N/A | #N/A
46 | [7 empty] | #N/A | #N/A | #N/A | #N/A
47 | [7 empty] | #N/A | #N/A | #N/A | #N/A
48 | [7 empty] | #N/A | #N/A | #N/A | #N/A
49 | [7 empty] | #N/A | #N/A | #N/A | #N/A
50 | [7 empty] | #N/A | #N/A | #N/A | #N/A
51 | [7 empty] | #N/A | #N/A | #N/A | #N/A
52 | [7 empty] | #N/A | #N/A | #N/A | #N/A
53 | [7 empty] | #N/A | #N/A | #N/A | #N/A
54 | [7 empty] | #N/A | #N/A | #N/A | #N/A
55 | [7 empty] | #N/A | #N/A | #N/A | #N/A
56 | [7 empty] | #N/A | #N/A | #N/A | #N/A
57 | [7 empty] | #N/A | #N/A | #N/A | #N/A
58 | [7 empty] | #N/A | #N/A | #N/A | #N/A
59 | [7 empty] | #N/A | #N/A | #N/A | #N/A
60 | [7 empty] | #N/A | #N/A | #N/A | #N/A
61 | [7 empty] | #N/A | #N/A | #N/A | #N/A
62 | [7 empty] | #N/A | #N/A | #N/A | #N/A
63 | [7 empty] | #N/A | #N/A | #N/A | #N/A
64 | [7 empty] | #N/A | #N/A | #N/A | #N/A
65 | [7 empty] | #N/A | #N/A | #N/A | #N/A
66 | [7 empty] | #N/A | #N/A | #N/A | #N/A
67 | [7 empty] | #N/A | #N/A | #N/A | #N/A
68 | [7 empty] | #N/A | #N/A | #N/A | #N/A
69 | [7 empty] | #N/A | #N/A | #N/A | #N/A
70 | [7 empty] | #N/A | #N/A | #N/A | #N/A
71 | [7 empty] | #N/A | #N/A | #N/A | #N/A
72 | [7 empty] | #N/A | #N/A | #N/A | #N/A
73 | [7 empty] | #N/A | #N/A | #N/A | #N/A
74 | [7 empty] | #N/A | #N/A | #N/A | #N/A
75 | [7 empty] | #N/A | #N/A | #N/A | #N/A
76 | [7 empty] | #N/A | #N/A | #N/A | #N/A
77 | [7 empty] | #N/A | #N/A | #N/A | #N/A
78 | [7 empty] | #N/A | #N/A | #N/A | #N/A
79 | [7 empty] | #N/A | #N/A | #N/A | #N/A
80 | [7 empty] | #N/A | #N/A | #N/A | #N/A
81 | [7 empty] | #N/A | #N/A | #N/A | #N/A
82 | [7 empty] | #N/A | #N/A | #N/A | #N/A
83 | [7 empty] | #N/A | #N/A | #N/A | #N/A
84 | [7 empty] | #N/A | #N/A | #N/A | #N/A
85 | [7 empty] | #N/A | #N/A | #N/A | #N/A
86 | [7 empty] | #N/A | #N/A | #N/A | #N/A
87 | [7 empty] | #N/A | #N/A | #N/A | #N/A
88 | [7 empty] | #N/A | #N/A | #N/A | #N/A
89 | [7 empty] | #N/A | #N/A | #N/A | #N/A
90 | [7 empty] | #N/A | #N/A | #N/A | #N/A
91 | [7 empty] | #N/A | #N/A | #N/A | #N/A
92 | [7 empty] | #N/A | #N/A | #N/A | #N/A
93 | [7 empty] | #N/A | #N/A | #N/A | #N/A
94 | [7 empty] | #N/A | #N/A | #N/A | #N/A
95 | [7 empty] | #N/A | #N/A | #N/A | #N/A
96 | [7 empty] | #N/A | #N/A | #N/A | #N/A
97 | [7 empty] | #N/A | #N/A | #N/A | #N/A
98 | [7 empty] | #N/A | #N/A | #N/A | #N/A
99 | [7 empty] | #N/A | #N/A | #N/A | #N/A
100 | [7 empty] | #N/A | #N/A | #N/A | #N/A
Formulas:
Remaining duration [Month] = IF([End date]="","", IF(YEAR([End date])=YEAR(TODAY()), MONTH([End date])-MONTH(TODAY()), (YEAR([End date])-YEAR(TODAY()))*12+1+(MONTH([End date])-MONTH(TODAY())) ))
In the this worksheet 'Contract terms', all important contract data is recorded to provide a general overview of the contract partner, type, and duration.
Once completed, the contract data is automatically transferred to the other spreadsheets.
Give the contract an unique identification number.
Give the contract a name.
Select the contract status. The probability is automatically calculated:
- Initial contact (25%)
- In negotiation (50%)
- Draft contract available (90%)
- Contractually bound (100%)
- Contract terminated (100%)
(A more detailed description of the statuses can be found in the worksheet 'LISTS'.)
Enter the supplier / customer ID.
The remaining cells for the 'Contract partner' section are filled in automatically based on the information from the 'Supplier data' and 'Customer data' worksheets.
Enter the internally responsible person.
Choose the type of goods:
Good - material asset,
e.g. software
Service - intangible asset,
e.g. training for software application
License - Right to use material or intangible asset,
e.g. access to Software-as-a-Service (SaaS)
Choose between one-off or regular delivery and specify the delivery frequency.
Enter the start and end date of the contract.
Select whether the contract has been extended and specify in the comment field if necessary.
Enter the minimum contract duration.
Enter the notice period.
Specify the filing location of the contract documents.
Select whether it is purchasing or sales.
The contract duration is calculated in months.
The remaining duration of the contract is calculated here in months.

## 5. Contract costs
Contract costs | [12 empty] | Sum: | 14600 | 15900 | 16700 | -800 | 14900 | 1000 | 3300 | 5000 | 4500 | 10400
Contract data | [7 empty] | Payment method & deadlines | [5 empty] | Payment amount | [5 empty] | Contract volume
No. | Contract ID | Contract name | Purchasing / Sales | Status | Probability [%] | Filing location | Supplier / Customer ID | Due date [Date] | Terms of payment [Days] | Payment cycle | Next payment date | Type of payment | Method of payment | Value next invoice | Approved contract budget | Contract value | Budget | Contract value (probability-adjusted) | Budget (probability-adjusted) | Expenses (secured) | Income (secured) | Expenses (incl. probability) | Income (incl. probability)
1 | #001 | Microsoft Office 365 License | Purchasing | Contract terminated | 100% | 0 | S001 | 2023-07-01 | 0 | One-off | 2023-06-30 | Prepayment | Paypal | 500 | 500 | 500 | 0 | 500 | 0 | 500 |  | 500
2 | #001a | Microsoft Office 365 License | Purchasing | Contractually bound | 100% | 0 | S001 | 2023-08-15 | 14 | One-off |  | Upon receipt | Credit card | 2800 | 3000 | 2800 | 200 | 2800 | 200 | 2800 |  | 2800
3 | #002 | Cell phone contracts | Purchasing | In negotiation | 50% | 0 | S002 | 2023-07-30 | 0 | Quarterly | 2023-08-01 | Invoice | Direct debit | 300 | 2400 | 2400 | 0 | 1200 | 1200 |  |  | 1200
4 | #003 | Webseite concept | Sales | Contractually bound | 100% | 0 | C001 | 2023-11-30 | 30 | One-off |  | Invoice | Cash | 5000 | 5000 | 5000 | 0 | 5000 | 0 |  | 5000 |  | 5000
5 | #004 | Webseite maintenance | Sales | Draft contract available | 90% | 0 | C001 | 2023-12-31 | 30 | Yearly |  | Invoice | Bank transfer | 6000 | 5000 | 6000 | -1000 | 5400 | -400 |  |  |  | 5400
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
The contract data is automatically transferred from the 'Contract terms' worksheet.
In the 'Contract costs' worksheet the financial side of contract management is mapped in order to plan payments.
Enter the next due date for the contract.
Enter the terms of payment in days.
Choose the payment cycle:
- One-off
- Monthly
- Quarterly
- Yearly
Choose the method of payment:
- Cash
- Credit card
- Paypal
- Bank transfer
- Direct debit
Choose the type of payment:
- Prepayment
- Upon receipt
- Invoice
Enter the payment date.
Based on your entry, a traffic light system is automatically generated which shows you various options for action.
Green: Payment date is before payment target => No action necessary
Yellow: Payment date not yet set
=> Schedule invoice payment
Red: Payment date is after the payment target
=> Pay / claim invoice
Enter the value of the next invoice.
Enter the approved contract budget.
The total costs for the duration of a contract are displayed here.
This shows you how your contract value (ACTUAL) relates to your planned budget (TARGET).
The probability-adjusted total value for the duration of a contract are displayed here.
This shows you how your probability-adjusted contract value (PROBABILITY ACTUAL) relates to your planned budget (TARGET).
The contract volume ("secured" and "weighted") is shown here, broken down by supplier ("expenses") and customer ("income").
These columns are mainly used to calculate the contract volume per supplier (worksheet: '2. Supplier data') and customer (worksheet: '3. Customer data').

## 6. Contract delivery
Contract delivery
Contract data | [6 empty] | Scope of delivery | [5 empty] | Quality control
No. | Contract ID | Contract name | Purchasing / Sales | Status | Probability [%] | Filing location | Delievery frequency | Next delivery date | Asset | Criteria | Quantity | Completion date | Status | Quality control [Date] | Type of quality control | Comment
1 | #001 | Microsoft Office 365 License | Purchasing | Contract terminated | 100% | 0 | Daily | 2023-07-01 | Access to Microsoft Office solutions |  | 1 | - | Executed | 2023-06-28 | Manual testing | Used Test month to try out various functions based on our requirements
2 | #001a | Microsoft Office 365 License | Purchasing | Contractually bound | 100% | 0 | Daily | 2023-08-01 | Access to Microsoft Office solutions |  | 5 | - | Not relevant
3 | #002 | Cell phone contracts | Purchasing | In negotiation | 50% | 0 | Daily | 2024-01-01 | Mobile phones and unlimited usage |  | 3 | - | To be defined
4 | #003 | Webseite concept | Sales | Contractually bound | 100% | 0 | 0 | 2024-01-01 | Website conceptualized and created |  | 1 | 2023-12-15 | To be defined
5 | #004 | Webseite maintenance | Sales | Draft contract available | 90% | 0 | Monthly |  | Monthly maintenance based on agreed upon criteria | Uptime >95% | 1 | 2023-12-15 | Planned | 2023-12-15 | Standard quality control | Requirements based on criteria defined in contract
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
The 'Contract delivery' worksheet displays the scope of delivery and quality control. This serves to adjust the production volume if necessary and to deliver or receive assets on time.
The contract data is automatically transferred from the 'Contract terms' worksheet.
Enter the next delivery date.
Specifiy the asset.
Enter the criteria that must be fulfilled according to the contract.
Enter the quanity of the delivery.
Define the date when the asset has to be completed the latest.
Choose the statusof the quality control:
- Not relevant
- To be defined
- Planned
- Executed
Enter the date for the quality control.
Describe the type of quality control. Specify in the comment field.

## 7. Risk management
Risk management
Contract data | [6 empty] | Risk assessment & mitigation
No. | Contract ID | Contract name | Purchasing / Sales | Status | Probability [%] | Filing location | Risk I | Probability | Impact | Total risk | Preventive measures | Risk II | Probability | Impact | Total risk | Preventive measures | Risk III | Probability | Impact | Total risk | Preventive measures
1 | #001 | Microsoft Office 365 License | Purchasing | Contract terminated | 100% | 0 | Functionality not suitable for requirements | 1 | 2 | Low | Define requirements | Functionality not suitable for requirements | 1 | 3 | Low | Test requirements in test month |  |  |  | –
2 | #001a | Microsoft Office 365 License | Purchasing | Contractually bound | 100% | 0 |  |  |  | – |  |  |  |  | – |  |  |  |  | –
3 | #002 | Cell phone contracts | Purchasing | In negotiation | 50% | 0 | Contracts not valid for whole Europe | 4 | 5 | High | Research subscription options |  |  |  | – |  |  |  |  | –
4 | #003 | Webseite concept | Sales | Contractually bound | 100% | 0 | Production starts without signed contract | 3 | 3 | Moderate | Sign a letter of intent |  |  |  | – |  |  |  |  | –
5 | #004 | Webseite maintenance | Sales | Draft contract available | 90% | 0 |  |  |  | – |  |  |  |  | – |  |  |  |  | –
6 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
7 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
8 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
9 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
10 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
11 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
12 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
13 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
14 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
15 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
16 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
17 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
18 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
19 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
20 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
21 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
22 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
23 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
24 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
25 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
26 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
27 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
28 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
29 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
30 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
31 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
32 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
33 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
34 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
35 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
36 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
37 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
38 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
39 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
40 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
41 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
42 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
43 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
44 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
45 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
46 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
47 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
48 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
49 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
50 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
51 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
52 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
53 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
54 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
55 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
56 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
57 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
58 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
59 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
60 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
61 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
62 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
63 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
64 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
65 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
66 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
67 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
68 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
69 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
70 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
71 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
72 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
73 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
74 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
75 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
76 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
77 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
78 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
79 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
80 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
81 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
82 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
83 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
84 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
85 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
86 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
87 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
88 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
89 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
90 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
91 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
92 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
93 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
94 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
95 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
96 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
97 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
98 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
99 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
100 | [9 empty] | – |  |  |  |  | – |  |  |  |  | –
The contract data is automatically transferred from the 'Contract terms' worksheet.
The 'Risk management' worksheet considers possible risks of a contract as well as appropriate risk mitigation measures to ensure delivery in accordance with the contract.
Indicate a possible risk. It can be of legal, technical, personnel, scheduling or financial nature.
Choose the probability of the risk:
1 - Highly unlikely
2 - Unlikely
3 - Possible
4 - Likely
5 - Highly likely
The total risk is calculated automatically.
The entry of two more risks is possible.
Choose the impact of the risk:
1 - Very low
2 - Low
3 - Moderate
4 - High
5 - Critical

## 8. Evaluation
Evaluation
Dashboard
| Total income (secured) | Total income (incl. probability) | Number of contracts | Number of contract partner | Number of contract extensions | Contract length in months (average)
Customer | 5000 | 10400 | 2 | 1 | 0 | 7
Supplier | -3300 | -4500 | 3 | 2 | 1 | 10
Sum | 1700 | 5900
remaining duration customer projects
1 | up to 2 months
0 | 3-6 months
0 | 7-12 months
0 | > 1 year
In the 'Evaluation' worksheet, key figures are displayed to enable controlling for the contract management.
All key figures are calculated automatically!

## LISTS
Type of contract | Status of contract | Probability | Definition | Type of goods | Definition | Delivery interval | Delivery frequency | Extension | Type of payment | Method of payment | Payment cycle |  | Quality control | Probability |  | Impact |  | Total risk
Purchasing | Initial contact | 25% | Non-binding introduction | Good | Material asset, e.g. software | One-off | Daily | Yes | Prepayment | Cash | One-off | 1 | Not relevant | 1 | Highly unlikely | 1 | Very low | Low
Sales | In negotiation | 50% | Discussion of specific cooperation | Service | Intangible asset, e.g. training for software application | Regularly | Weekly | No | Upon receipt | Credit card | Monthly | 1 | To be defined | 2 | Unlikely | 2 | Low | Moderate
| Draft contract available | 90% | Contract about to be signed | License | Right to use material or intangible asset, e.g. access to Software-as-a-Service (SaaS) |  | Fortnightly |  | Invoice | Paypal | Quarterly | 4 | Planned | 3 | Possible | 3 | Moderate | High
| Contractually bound | 100% | Contract delivery in progress | Other |  |  | Monthly |  |  | Bank transfer | Yearly | 1 | Executed | 4 | Likely | 4 | High
| Contract terminated | 100% | Contract has ended |  |  |  | Quarterly |  |  | Direct debit |  |  |  | 5 | Highly likely | 5 | Critical
Yearly
This worksheet contains the lists that provide the data for the drop-down menus.
Feel free to adapt the contents of the lists to your situation! However, make sure to update the corresponding cells accordingly if necessary.