## Basic Data
Cost and Resource Plan
General project data |  |  |  | Cost types
project name | Example project |  |  | internal personnel costs
Project description | In project for testing |  |  | external personnel costs
principal | Max Mustermann |  |  | cost of materials
project manager | Joe Dalton. |  |  | travel expenses
project start | 2019-09-15 |  |  | licensing costs
Expected end of project | 2020-03-15 |  |  | investments
Marketing/advertising costs
other expenses
Resources
Name | Type | Unit | Hourly rate | Planned flat rate or one-off costs | Change costs resulting from change requests
Person 1 | Internal | hours | 80
Person 2 | Internal | hours | 120
Person 3 | External | hours | 130
Service 1 | External | lump sum |  | 800 | 2000
Material 1 | External | lump sum |  | 8000
Person 4 | External | hours | 80
External service 1 | Internal | lump sum |  | 5000 | 6000
Person 5 | Internal | hours | 80
Person 6 | Internal | hours | 90
Fill this entire area with your project-specific data.
You can extend the cost types and the resource list as you wish by simply writing in the next line. It is best to copy the previous line and then adjust the values.
In general, you can differentiate between initial planning costs and change costs (changer requests) with this planning tool. You can also use this when creating resources.

## General Plan
Kosten- und Ressourcenplan
[5 empty] | Planned costs |  | Unplanned costs
TYPE | PSP-Code | Work package / Task | Resources | Type of costs | Quantity | Planned costs | Quantity | Alteration costs | Release takes place on | Total costs | Cost types
P | 1 | Phase 1 |  |  |  | 18910 |  | 1400 |  | 19270
AP | 1.1 | as-is analysis | Person 2 | hours | 4 | 480 | 3 | 360 | 43730 | 840 | internal personnel costs
AP | 1.2 | Stakeholder - Mgmnt | Person 2 | hours | 24 | 2880 |  | 0 |  | 2880 | internal personnel costs
AP | 1.3 | environment analysis | Person 3 | hours | 3 | 390 | 8 | 1040 |  | 390 | cost of materials
AP | 1.4 | Pick up Mgmnt | Person 2 | hours | 23 | 2760 |  | 0 |  | 2760 | investments
AP | 1.5 | Buy calculator | Material 1 | lump sum |  | 8000 |  | 0 |  | 8000 | travel expenses
AP | 1.6 | Develop Gui | Person 4 | hours | 25 | 2000 |  | 0 |  | 2000 | internal personnel costs
AP | 1.7 | Collect requirements | Person 1 | hours | 30 | 2400 |  | 0 |  | 2400 | external personnel costs
P | 2 | Phase 2 |  |  |  | 19800 |  | 6000 |  | 25800
AP | 2.1 | Programming DB | Person 2 | hours | 50 | 6000 |  | 0 |  | 6000 | Marketing/advertising costs
AP | 2.2 | Prepare network | Person 4 | hours | 20 | 1600 |  | 0 |  | 1600 | cost of materials
AP | 2.3 | licenses | External service 1 | lump sum |  | 5000 |  | 6000 | 43728 | 11000 | internal personnel costs
AP | 2.4 | Concept xy | Person 2 | hours | 60 | 7200 |  | 0 |  | 7200 | investments
P | 3 | Phase 3 |  |  |  | 4400 |  | 9200 |  | 6400
AP | 3.1 | Implementation A | Person 6 | hours | 40 | 3600 | 80 | 7200 |  | 3600 | cost of materials
AP | 3.2 | External power B | Service 1 | lump sum | 50 | 800 |  | 2000 | 43730 | 2800 | travel expenses
1.98
Wählen Sie zunächst in Spalte A aus ob es sich um ein Arbeitspaket, einen Meilenstein oder eine Projektphase handelt
Vermerken in Spalte B das zugehörige PSP-Element
Beschreiben SIe in Spalte C das Arbeitspaket
Ordnen Sie in D die passende Ressource zu
Vermerken Sie in Spalte F die Menge bzw. den Aufwand
In Spalte H können Sie noch zusätzliche Kosten vermerken und
in Spalte J die passende Kostenart zuordnen
Tipp: Am einfachsten funktioniert es, wenn Sie sich eine der darüberligenden Zeilen für einen neuen Eintrag kopieren (entweder Meilenstein, Phase oder Arbeitspaket).
Fill this entire area with your project-specific data.
It is best to copy the appropriate predecessor line (phase or work package) and adapt it.
Check the blue phase totals to make sure that the totals range is correct.
Please enter a date in the "Release on" field if unplanned costs have been approved.

## Analysis
cost summary | P |  |  |  | types of costs | Total costs
[5 empty] | external staff costs | 2160
project stages | Total planned costs | Total change costs | Sum of total costs |  | internal staff costs | 36500
Phase 1 | 18910 | 1400 | 19270 |  | Investments | 2600
Phase 2 | 19800 | 6000 | 25800 |  | Marketing/advertising costs | 2000
Phase 3 | 4400 | 9200 | 6400 |  | material costs | 25000
Total costs | 43110 | 16600 | 51470 |  | travel expenses | 16300
[5 empty] | Grand Total | 84560
Approved Change Requests
| External power B | Status analysis | Licences | Overall result
43728 |  |  | 6000 | 6000
43730 | 2000 | 360 |  | 2360
Overall result | 2000 | 360 | 6000 | 8360