## A3 Verkefni - Sniðmát (2)
Title: Skráning lífsmarka á bráðamóttöku barna | Date: | 2021-01-01 | Project team: Elín Markúsdóttir, Sandra Salvör og Karitas Gunnarsdóttir , Oddný Kristinsdóttir hjúkrunarfræðingar, Ingibjörg Richter kerfisfræðingur
Supervisor: Viðar Örn Eðvarðsson |  |  |  |  | Project lead (resident): | Urður Jónsdóttir og Kristín Júlía Erlingsdóttir
Aim statement (What are we trying to accomplish?) |  |  | 1 | Meaures (How will we know a change is an improvement?) (list measures) |  |  |  |  | 4
Increase the measurement and recording of full vital signs upon presentation to the pediatric emergency department. Full vital signs are defined as heart rate, oxygen saturation, temperature, blood pressure and respiratory rate. |  |  |  | Prepare guidelines to define and standardize which vital signs should be taken at presentation to the PED. To encourage adherence to these guidelines we will be making changes to Heilsugátt so that missing vital signs are flagged and more visible to those working at each time.
What process(es) are we trying to improve? (process map) |  |  | 2 | Action plan |  |  |  |  | 5
|  |  |  | Action |  |  | By whom | Date | Status
|  |  |  | Process map and fishboe analysis |  |  | KJE/UJ | nov.21 | Finished
|  |  |  | Asseble project team |  |  | KJE/UJ/VÖE | nov.21 | Finished
|  |  |  | Start conversation within the ED |  |  | KG/OK | 2021-11-01 | Finished
|  |  |  | Baseline results, set up as run chart |  |  | KJE | 2021-11-01 | Finished
|  |  |  | First results after conversation started |  |  | KJE/UJ | 2021-12-01 | Finished
|  |  |  | Prepare guidlines |  |  | KJE/UJ | 2021-02-01 | Finished
|  |  |  | PDSA #1: Guidlines official and available |  |  | KJE/UJ/KG/OK | 2021-03-10 | Finished
|  |  |  | Guidlines introduced |  |  | KG/OK | 2021-04-12 | Finished
|  |  |  | Second results, set up as run chart |  |  | KJE/UJ | 2021-04-01 | Finished
|  |  |  | PDSA #2: PEWS |  |  | KG/OK | 2021-05-01 | in progress
|  |  |  | Third results, set up as run chart |  |  | KJE/UJ | 2021-05-01 | in progress
|  |  |  | PDSA #3: Visible on heilsugátt % of patients with full vital signs last 24hrs |  |  | IR | 2021-05-01 | in progress
|  |  |  | Fourth results, set up as run chart |  |  | KJE/UJ | 2021-06-01 | in progress
What change can we make that will result in improvement? (5 Why's/Fishbone diagram & change ideas) |  |  | 3 | Results (Run Chart) |  |  |  |  | 6
|  |  |  | Implementation, follow up and lessons learned |  |  |  |  | 7
We are still waiting on the main changes to Heilsugátt and will hopefully see more improvement once they are implemented. Changes take a lot more time than expected. We will analyze further after all changes have been made.