## A3 Verkefni - Sniðmát (2)
Title: Mænuvökvataka á Minnismóttöku Landakot | Date: | 30.maí 2023 | Project team: Læknar og ritarar á Minnismóttöku Landakots
Supervisor: Helga Eyjólfsdóttir |  |  |  |  | Project lead: | Berglind Árnadóttir og Guðbjörg Erla Guðmundsdóttir
Aim statement (What are we trying to accomplish?) |  |  | 1 | Meaures (How will we know a change is an improvement? |  |  |  |  | 4
Biðtími í mænuvökvatöku er langur og talsvert er af endurbókunum. Það tefur fyrir greiningu og leiðir til margra ónýttra tímabókanna. Tilgangur verkefninsins er að fækka endurbókunum og lausum tímabókunum í mænuvökvatöku við uppvinnslu á Minnismóttöku Landakots um 50% yfir 1 árs tímabil. |  |  |  | Í Sögukerfi munum við fara yfir vikulega: 1. Endurbókanir í mænuvökvatöku á Minnismóttöku Landakots (ML) og 2. Lausa tíma í mænuvökvatöku á ML. Eru þessar mælingar svokallaðar outcome measures og hafa áhrif á flæði sjúklinga og styttingu á biðtíma sjúklinga eftir mænuvökvatöku á ML.
What process(es) are we trying to improve? (process map) |  |  | 2 | Action plan |  |  |  |  | 5
|  |  |  | Action |  |  | By whom | Date | Status
|  |  |  | Process map og fishbone analysis |  |  | GEG/BÁ | Okt. 21 | Finished
|  |  |  | Teymisfundur til undirbúnings gæðaverkefnis |  |  | GEG/BÁ/HE | Nóv. 21 | Finished
|  |  |  | Gagnasöfnun fyrir PSDA1 og gögn sett í run chart |  |  | BÁ | Nóv. 21 | Finished
|  |  |  | Undirbúningur á tékklista |  |  | GEG/BÁ | Nóv. 21 | Finished
|  |  |  | PDSA #1: Tékklisti fyrir bókanir í mænuvökvatöku |  |  | GEG/BÁ | 2022-01-01 | Finished
|  |  |  | Kynning á verkefni fyrir lækna sem starfa á minnismóttöku |  |  | GEG/BÁ | 2022-01-01 | Finished
|  |  |  | Talning á lausum tímum í sögu og niðurstöður settar í run chart |  |  | GEG/BÁ | 2022-09-01 | Finished
|  |  |  | Teymisfundur með supervisor |  |  | GEG/BÁ/HE | Nóv. 22 | Finished
|  |  |  | PDSA #2: Fundur með læknum minnismóttöku og frekari kynning á lista |  |  | GEG/BÁ | Nóv. 22 | Finished
|  |  |  | Talning á lausum tímum í Sögu eftir PDSA #2 og niðurstöður settar í run chart |  |  | GEG/BÁ | Mars 23 | Finished
|  |  |  | Results (Run Chart) |  |  |  |  | 6
What change can we make that will result in improvement? (5 Why's/Fishbone diagram & change ideas) |  |  | 3
|  |  |  | Implementation, follow up and lessons learned |  |  |  |  | 7
Breyta 1 fól í sér að aðilar utan teymis þurftu að fylla út tékklista (pappírsbeiðni). Þá hafði breyta 1 áhrif á fish-bone analysis mtt lækna, annað starfsfólk, verkferlar og heilsugátt/saga. Ritarar fóru yfir listann þegar skjólstæðingar voru bókaðir í mænuvökvatöku. Hugmynd að breytu 2 var fræðslubæklingur fyrir sjúklinga annarsvegar eða kynning á verkefninu fyrir starfsfólk Minnismóttökunnar (M) hins vegar. Fallið var frá hugmyndinni um fræðslubækling. Vinnsla verkefnisins tafðist og því talið betra að fjalla um og minna á verkefnið á fundi fyrir lækna og starfsfólk M. Við umræður kom í ljós að starfsfólk var almennt mjög ánægt með verkefnið. Teymið hafði samt sem áður búið til fræðslubækling og var hann afhentur M eftir að verkefnið kláraðist þar sem áhugi var fyrir því, og hafði því ekki áhrif á niðurstöður verkefnisins. Niðurstöður (run-chart) sýna að marktækur munur var á lausum tímum en ekki á endurbókunum. Má draga þá ályktun að aukið skipulag sem myndaðist með innleiðslu á tékklistanum hafa ollið því að lausum tímabókunum fækkaði. Óljóst er afhverju endurbókunum fækkaði ekki, en við úrvinnslu gagna kom í ljós að talsvert var um veikindi lækna á síðara tímabili en því fyrsta og hefur það líklega haft áhrif á niðurstöður. Fróðlegt hefði verið að sjá hvort fræðslubæklingur hefði eitthvað að segja hvað varðar endurbókanir, en sú nálgun snýr að frekari upplýsingagjöf fyrir sjúklinginn og aðstandendur.
Note on K27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The PDSAs should be clearly annotated on the Run Charts.

## EXAMPLE
Title: Communication pathways regarding neonatal | Date: | 2. maí 2022 | Project team: Jóhanna Rut Óskarsdóttir hjúkrunarfræðingur, Ella Björg Rögnvaldsóttir ljósmóðir, Sunna María ljósmóðir
Supervisor: Berglind Jónsdóttir |  |  |  |  | Project lead (resident): | Helga Þórunn og Hrafn Hlíðdal
Aim statement (What are we trying to accomplish?) |  |  | 1 | Measures (How will we know a change is an improvement?) (list measures) |  |  |  |  | 4
We want to decrease non-urgent phone calls from Meðgöngu- og sængurlegudeild 22A and Fæðingarvakt 23B by 30% before 29th of April because it can interrupt urgent care and work on the ward without lengthening the time from contact to residents’ reaction. |  |  |  | Count all phone calls received by the neonatal resident each 24 hours from 08:00 to 08:00 the next day. Then filter out the urgent phone calls.
Measure the time it takes from a phone call or a message to be recieved until the resident reacts on it and starts working on the problem
What process(es) are we trying to improve? (process map) |  |  | 2 | Action plan |  |  |  |  | 5
|  |  |  | Action |  |  | By whom | Date | Status
|  |  |  | Process map and fish analysis |  |  | HÞÓ/HHÞ | 03.11.21 | Finished
|  |  |  | Team meeting for planning the project |  |  | Team | 4.11.21 | Finished
|  |  |  | Start measuring phone calls by including other neonatal residents |  |  | HÞÓ/HHÞ | 22.11.21 | Finished
|  |  |  | Baseline results, set up as a run chart started |  |  | HÞÓ/HHÞ | 25.11.21 | Finished
|  |  |  | First results put in the run chart after outcome measurements |  |  | HÞÓ/HHÞ | 23.12.21 | Finished
|  |  |  | Contact Heilsugátt to get a message board to contact residents in NICU |  |  | HHÞ | 11.01.22 | Finished
|  |  |  | Introduction in the wards of 22A and 23B of PDSA1, with a newfound message board directly to the NICU resident. |  |  | JRÓ/EBR&SMHHÞ/HÞÓ | 24.01.22 | Finished
|  |  |  | Start measuring the effect of PDSA1 |  |  | HÞÓ//HHÞ | 31.1.22 | Finished
|  |  |  | Second results put in the run chart |  |  | HÞÓ//HHÞ | 28.2.22 | Finished
|  |  |  | Introduction of PDSA2, with daily check-ins from the NICU resident to 22A |  |  | HÞÓ//HHÞ | 11.2.22 | Finished
|  |  |  | Start measuring the effect of PDSA#2 |  |  | HÞÓ/HHÞ | 14.3.22 | Finished
|  |  |  | Third results, set up as run chart |  |  | HÞÓ/HHÞ | 14.3.22 | Finished
|  |  |  | Introduction of the outcomes of the quality improvement project |  |  | HÞÓ/HHÞ | 12.5.22 | In progress
What change can we make that will result in improvement? (5 Why's/Fishbone diagram & change ideas) |  |  | 3 | Results (Run Chart) |  |  |  |  | 6
|  |  |  | Implementation, follow up and lessons learned |  |  |  |  | 7
Change to clinical work and work processes takes a lot more time than anticipated. It is important to maintain the progress made by It was difficult to measure the outcomes since it was dependent on residents that are not in the team to do extra work. That resulted in team members receiving data late and having to constantly remind them to measure outcomes. The message board in Heilsugátt has gotten a status in every day work but the regular visits to the ward need further evaluation if they are to be maintained.