## Turnaround Tracker
Week | Listen (but filter) | Find Talent & Drainers | Face into Stakeholders | Be Ruthless (x3 Test) | Plan Backwards | Overall Maturity Score | Guide
Week 1 | [6 empty] | 1. Listen (but filter)
Week 2 | [6 empty] | 1 = Team voices unheard / only hears noise
Week 3 | [6 empty] | 3 = Collected input, but not yet filtered into clear root causes
Week 4 | [6 empty] | 5 = Clear, agreed root causes, team feels heard but not drowned in emotion
Week 5
2. Find the Talent & Drainers
1 = Haven’t identified who really understands the problems / who drains energy
3 = Some talent spotted, but not yet fully empowered; drainers still disruptive
5 = Key fixers engaged in delivery; drainers reassigned/redirected
3. Face into Stakeholders
1 = Stakeholders kept at arm’s length / little honesty
3 = Issues shared, but limited two-way collaboration
5 = Stakeholders fully engaged, providing support on scope, budget, and dates
4. Be Ruthless (x3 Test)
1 = Everything still seen as “must-have”
3 = Some prioritisation, but scope creep still present
5 = Ruthless cuts made; only true launch-critical items remain
5. Plan Backwards
1 = Vague re-plans, unclear end-goal
3 = High-level backwards plan but gaps in detail or commitment
5 = Realistic, detailed backwards plan in place; team aligned on “good enough to go live”