There are a wide range of tasks required to plan and implement work-based learning. This checklist can be used for all work-based learning and includes a high-level overview of tasks that should be considered. Additional tasks may be required while some may be discarded.

## Six Months Prior to Engagement

- Review academy’s Work-Based Learning Plan and Calendar

- Create a list of proposed dates for the activity

- Consider which industry partners, Advisory Board members, and/or local community professionals might be a good fit for the activity

  - Decide whether outreach to new industry partners and/or local community professionals is required

  - Collect outreach information

## Four Months Prior to Engagement

- Meet with the Advisory Board and provide a list of proposed dates. Have them sign up and/or suggest potential industry partners and/or community professionals to participate in the activity

- Send out the Request Email to potential participants and include the Partner Interest Survey

## Two Months Prior to Engagement

- Finalize date and time of activity

- Confirm location of activity

- Assign students any required pre-work. Examples include:

  - Student Timeline for Informational Interviews

  - Phone Etiquette and Scripts for Informational Interviews

  - Resume and Cover Letter for Mock Interviews/Resume Review

## One Month Prior to Engagement

- Send the 4-weeks confirmation email to participants

- Share any required resources with participants

- Send a calendar invite to the participants that reflects date, time, and location of activity

- Complete any required permission forms for your school and district:

  - Photo Release

  - Volunteer Paperwork

  - Parent/Guardian Permission Slips

## One Week Prior to Engagement

- Send the 1-week confirmation email to participants

- Assign students the Research Activity

- Instruct students on dress for success by sharing the Professional Dress Guidelines

## One Day Prior to Engagement

- Add activity to WBL Participation Tracker

  - Ensure students are in NAFTrack to feed into the WBL Participation Tracker

## Day of Engagement

- Add students to the activity in the WBL Participation Tracker

- Assist the industry partner, Advisory Board member, and/or community professional as needed

- Take pictures if allowed

## One Day After Engagement

- Send Thank You Email to participants

- Instruct students to complete the Reflection Form in NAFTrack

- Support students as they complete and send the Student Thank You Note

## One Week After Engagement

- Update the WBL Participation Tracker if you haven’t yet

  - Include full details of the event

  - Update student participation

- Confirm students completed the WBL Reflection Form

- Share photos and 4-sentence summary to NAF Communications, Advisory Board, Administration, School District, and Superintendent to highlight your academy on social media by clicking here.