## CP Data
Site Location Source Reference | Survey Phase/Batch | Installation Batch Number | Street Address | Post Code | Controlled Parking Zone (CPZ) | Link to Map | Charger Install dates | EV Charger Commissioned Y/N
Batch 3.1 | Batch 2.1 | Batch 3 | Churchill Square Shopping Centre, Cannon Place - LC12 | BN1 2ED | Z / PbyP | Map | 2026-04-24
Batch 2 | Batch 2.1 | Batch 3 | 8 Melrose Close - LC01 | BN1 7BP | None | Map | 2026-04-29 | 2026-05-01
Batch 2 | Batch 2.1 | Batch 2 | Opposite Mimosa Court, Brentwood Road | BN1 7HW | None | Map
Program 1 | Program 1.2 | Batch 3 | Flats 27-32 Woburn Place - LC01 | BN1 9GA |  | Map
Batch 1 | MGroup Batch 1 - Post | Batch 3 | 19 St Helens Road | BN2 3EE | S | Map | 2026-05-04
Batch 1 | MGroup Batch 1 - Post | Batch 3 | 4 Beaufort Terrace | BN2 9SU | V | Map | 2026-05-01 | 2026-01-05
Batch 1 | MGroup Batch 1 - Post | Batch 3 | 43 - 45 Lockwood Crescent | BN2 6UH | None | Map | 2026-05-04
Batch 1 | MGroup Batch 1 - Post | Batch 3 | 5 Manor Crescent | BN2 5EJ | n/a | Map | 2026-05-05
Batch 1 | Batch 1 part 2 | Batch 2 | 8 St Cuthmans Close | BN2 5HW | Private | Map | 2026-05-05
Batch 1 | MGroup Batch 1 - Post | Batch 3 | Ardingly Court, High Street | BN2 1RW | C / PbyP | Map | 2026-05-05
Batch 1 | MGroup Batch 1 - Post | Batch 3 | Carlyle Street, adjacent to 138 Elm Grove | BN2 9XU | S | Map | 2026-05-06
Batch 1 | MGroup Batch 1 - Post | Batch1 | Dinapore House, John Street | BN2 9PJ | C / PbyP | Map | 2026-05-01 | 2026-01-05
Batch 1 | MGroup Batch 1 - Post | Batch1 | Grove Bank, Grove Hill | BN2 9NG | C / PbyP | Map | 2026-05-01 | 2026-01-05
Batch 1 | MGroup Batch 1 - Post | Batch 3 | Kemptown Mews, Arundel Place | BN2 1GD | H | Map | 2026-05-06
Batch 1 | MGroup Batch 1 - Post | Batch 3 | Lewes Street, rear of 13 Albion Hill | BN2 9NP | Private | Map | 2026-05-06
Batch 1 | MGroup Batch 1 - Post | Batch1 | Opposite 37 - 42 St Mary's Place | BN2 1LH | C | Map | 2026-05-06
Batch 1 | MGroup Batch 1 - Post | Batch 3 | Phoenix Halls, Newhaven Street | BN2 9WG | V | Map | 2026-05-07
Batch 1 | MGroup Batch 1 - Post | Batch 3 | Windermere Court, North Drive | BN2 0BU | C / PbyP | Map | 2026-05-07 | 2026-01-05
Batch 2 | Batch 2 | Batch 3 | 17 Guildford Road | BN1 3LW | Permit Holders Y | Map | 2026-05-07
Batch 2 | Batch 2.1 | Batch 3 | 19 Alexandra Villas | BN1 3RE | Y | Map | 2026-05-07
Batch 2 | Batch 2.1 | Batch 3 | 27 Upper Lewes Road | BN2 3FD | Permit Holders J | Map | 2026-05-07
Batch 2 | Batch 2.1 | Batch 3 | 69 Princes Road | BN2 3RH | Permit Holders J | Map | 2026-05-08
Batch 2 | Batch 2.1 | Batch 2 | 9 Surrenden Park | BN1 6XA | 10 | Map | 2026-05-08
Batch 2 | Batch 2.1 | Batch 2 | 9a Beaconsfield Villas | BN1 6HA | J | Map | 2026-05-08
Batch 2 | Batch 2.1 | Batch 3 | Opposite 31 Edinburgh Road | BN2 3HY | Permit Holders J | Map | 2026-05-08
Batch 2 | Batch 2.1 | Batch 3 | Opposite 28 Crespin Way | BN1 7FH | None | Map | 2026-05-08
Batch 2 | Batch 2.1 | Batch 3 | Robinia Lodge, Station Road | BN1 6SF | K | Map | 2026-05-08
Batch 2 | Batch 2.1 | Batch 3 | Gerard Street, adjacent to 29 Clyde Road | BN1 4NW | J | Map | 2026-05-11
Batch 3.1 | Batch 2.1 | Batch 3 | 1 Clifton Hill | BN1 3HL | Y | Map | 2026-05-11
Batch 3.1 | Batch 2.1 | Batch 3 | 16 Victoria Road | BN1 3FS |  | Map | 2026-05-11
Program 1 | Program 1.2 | Batch 3 | 70 Beatty Avenue | BN1 9EP |  | Map | 2026-05-11
Program 1 | Program 1.2 | Batch 3 | 85 Chailey Road | BN1 9JG |  | Map | 2026-05-11
Program 1 | Program 1.2 | Batch 4 | 29 Beatty Avenue | BN1 9EE | B (Events) | Map | 2026-05-11
Program 1 | Program 1.2 | Batch 4 | 9 - 10 Bristol Road | BN2 1JX | C / PbyP | Map | 2026-05-12
Program 1 | Program 1.2 | Batch 4 | Seymour Street, adjacent to 140 Marine Parade | BN2 1DF | H | Map | 2026-05-12
Program 1 | Program 1.2 | Batch 4 | Somerset Point Flats, Somerset Street | BN2 1GW | C / PbyP | Map | 2026-05-12
Program 1 | Program 1.3 | Batch 4 | 10 Dover Road | BN1 6LH | F | Map | 2026-05-12
Program 1 | Program 1.3 | Batch 4 | 101 Hythe Road | BN1 6FL | F | Map | 2026-05-12
Program 1 | Program 1.3 | Batch 4 | 112 Bonchurch Road | BN2 3LS | permit holders S | Map | 2026-05-12
Program 1 | Program 1.3 | Batch 4 | 134 Osbourne Road | BN1 6LW | F | Map | 2026-05-12
Program 1 | Program 1.3 | Batch 4 | 136 Balfour Road | BN1 6LW | F | Map | 2026-05-13
Program 1 | Program 1.3 | Batch 4 | 17 Dover Road | BN1 6LP | F | Map | 2026-05-13
Program 1 | Program 1.3 | Batch 4 | 19 Gladstone Place | BN2 3QE | V | Map | 2026-05-13
Program 1 | Program 1.3 | Batch 4 | 20 Bernard Road | BN2 3EP | S | Map | 2026-05-13
Program 1 | Program 1.3 | Batch 4 | 3 Carisbrooke Road | BN2 3EF | S | Map | 2026-05-13
Program 1 | Program 1.3 | Batch 4 | 49 Sherbourne Close | BN3 8BE | None | Map | 2026-05-13
Program 1 | Program 1.3 | Batch 4 | 7 Sandgate Road | BN1 6LG |  | Map | 2026-05-13
Program 1 | Program 1.3 | Batch 4 | Opposite 13 Upper Hollingdean Road | BN1 7GA | None | Map | 2026-05-13