## ExportedData
Site Location Source Reference | Survey Phase/Batch | Installation Batch Number | Street Address | Post Code | Controlled Parking Zone (CPZ) | Link to Map | Charger Install dates | EV Charger Commissioned Y/N
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 1 - 6 Durham Close | BN2 4LY | tbc | Map | 2026-03-25 | Yes
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 10 Walmer Crescent | BN2 4LR | None | Map | 2026-03-25 | Yes
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 160 Milner Road | BN2 4BQ | U | Map | 2026-03-26 | Fault - TBC
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 20 Hornby Road | BN2 4JL | tbc | Map | 2026-03-25 | Yes
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 112 Langley Crescent | BN2 6NQ | None | Map | 2026-03-26 | Yes
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 164 Bexhill Road | BN2 6QA | None | Map | 2026-03-26 | Yes
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 22 Vernon Avenue | BN2 6BF | None | Map | 2026-03-27 | Yes
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 285 Bexhill Road | BN2 6QL | None | Map | 2026-03-26 | Yes
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 2a Briarcroft Road | BN2 6LR | None | Map | 2026-03-27 | Yes
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 40 - 42 Cowley Drive | BN2 6WB | None | Map | 2026-03-30 | Yes
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 43 The Ridgway | BN2 6PD | None | Map | 2026-03-27 | Yes
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 5 Batemans Road | BN2 6RD | None | Map | 2026-03-27 | Yes
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 56 Wanderdown Road | BN2 7BT | None | Map | 2026-03-30
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | Ainsworth Close, adjacent to 23 Ainsworth Avenue | BN2 7BH | None | Map | 2026-03-30
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 44 Wanderdown Road | BN2 7BT | None | Map | 2026-03-30
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 146 Warren Road | BN2 6DD | None | Map | 2026-04-09
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 2 Northgate Close | BN2 7DZ | None | Map | 2026-03-31
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 25 Court Ord Road | BN2 7FD | None | Map | 2026-03-31
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 20 Winton Avenue | BN2 8FN | None | Map | 2026-04-01
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 23 Hawthorn Close | BN2 8HX | None | Map | 2026-04-01
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 37 Ashdown Avenue | BN2 8AH | None | Map | 2026-03-31
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 4 Lustrells Close | BN2 8AS | None | Map | 2026-04-01
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 8 Wanderdown Close | BN2 7BY | None | Map | 2026-04-01
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 8 Wanderdown Drive | BN2 7BZ | None | Map | 2026-04-01
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 134 Coombe Road | BN2 4EE | U | Map | 2026-04-07
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 155 Bear Road | BN2 4DB | U | Map
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | Fitzherbert Drive, adjacent to 16 Borrow King Close | BN2 4BW | None | Map | 2026-04-07
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 291 Bear Road | BN2 4DD | U | Map
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 31 - 33 Bear Road | BN2 4DA | U | Map
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 65 - 79 Fitch Drive | BN2 4HX | tbc | Map | 2026-04-07 | Yes
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | Opposite 9 Milner Road | BN2 4BS | U | Map | 2026-04-07 | Yes
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 10 Pankhurst Avenue | BN2 9YN | S | Map | 2026-04-02
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 2 Burlow Close | BN2 5GU | None | Map | 2026-04-02
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 2 Roedean Path | BN2 5RP | None | Map | 2026-04-02
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 26 St Lukes Road | BN2 9ZD | C | Map | 2026-04-09
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 31 Queens Park Road | BN2 0GJ | C | Map | 2026-04-02
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 9 Finsbury Road | BN2 9UU | V | Map | 2026-04-08
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | Brede Close, adjacent to 14 Hamsey Close | BN2 5GQ | n/a | Map | 2026-04-08
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 16 Wivelsfield Road | BN2 8FQ | None | Map | 2026-04-08
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 2 Shanklin Road | BN2 3LQ | S | Map | 2026-04-09 | Yes
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 31 Brading Road | BN2 3PE | S | Map | 2026-04-08
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 140 Wiston Road South | BN2 5PR | None | Map | 2026-04-10
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 112 Milner Road | BN2 4BQ | U | Map | 2026-04-09 | Yes
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 226 Cowley Drive | BN2 6TH | None | Map | 2026-04-13
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 26 - 48 Kipling Avenue | BN2 6UE | None | Map | 2026-04-13
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 11 Wadhurst Rise | BN2 5PW | None | Map | 2026-04-13
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 20 Bristol Gate | BN2 5BD | H | Map | 2026-04-13
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 37 - 42 Chiddingly Close | BN2 5GE | None | Map | 2026-04-14
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | 93 Brading Road | BN2 3PE | S | Map | 2026-04-14
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | Hornby Place, Hornby Road | BN2 4JT | tbc | Map | 2026-04-14
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | Opposite 38 Connell Drive | BN2 6RT | None | Map | 2026-04-14
Batch 1 | Batch 1 part 2 | Batch 2 | 105 Greenbank Avenue | BN2 8QP | None | Map | 2026-04-15
Batch 2 | Batch 2.1 | Batch 2 | 1c Hertford Road | BN1 7GG | None | Map | 2026-04-15
Batch 2 | Batch 2.1 | Batch 2 | 355 - 368 Highbrook Close | BN2 4HL | D (Event) / Private | Map | 2026-04-15
Batch 2 | Batch 2.1 | Batch 2 | 10 Barrow Close | BN1 7FL | None | Map | 2026-04-15
Batch 2 | Batch 2.1 | Batch 2 | 45 Preston Park Avenue | BN1 6HG | J | Map | 2026-04-16
Batch 2 | Batch 2.1 | Batch 2 | 74 Lynchet Close | BN1 7EY |  | Map | 2026-04-16
Batch 2 | Batch 2.1 | Batch 2 | 75 Preston Drove | BN1 6LD | J | Map | 2026-04-16
Batch 2 | Batch 2.1 | Batch 2 | Opposite Mimosa Court, Brentwood Road | BN1 7HW | None | Map | 2026-04-16
Batch 2 | Batch 2.1 | Batch 2 | St Joseph's, Davey Drive | BN1 7BF | None | Map | 2026-04-17
Batch 1 | Batch 1 part 2 | Batch 2 | 27 Oaklands Avenue | BN2 8LQ | None | Map | 2026-04-17
Batch 1 | Batch 1 part 2 | Batch 2 | 11 Ovingdean Close | BN2 7AD | None | Map | 2026-04-17
Batch 1 | Batch 1 part 2 | Batch 2 | 21 Perry Hill | BN2 8FT | None | Map | 2026-04-17
Batch 1 | Batch 1 part 2 | Batch 2 | 23 Rodmell Avenue | BN2 8LT | None | Map | 2026-04-20
Batch 1 | Batch 1 part 2 | Batch 2 | 40 Oaklands Avenue | BN2 8LQ | None | Map | 2026-04-20
Batch 1 | Batch 1 part 2 | Batch 2 | 56 Moulsecoomb Way | BN2 4PD | D (Events) | Map | 2026-04-20
Batch 1 | Batch 1 part 2 | Batch 2 | 63 Staplefield Drive | BN2 4RH | D (Events) | Map | 2026-04-20
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | Abbey Road, adjacent to 1 Chapel Terrace | BN2 1HS | H / PbyP | Map | 2026-04-21
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | Kingsfold Flats, Findon Road | BN2 5NT | None | Map | 2026-04-21
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | Opposite 57 Queens Park Terrace | BN2 9YB | C / PbyP | Map | 2026-04-21
Batch 1 | Batch 1 part 2 | Batch 2 | Opposite Cedar Flats, Beresford Road | BN2 5DD | H | Map | 2026-04-21
Batch 2 | Batch 2.1 | Batch 2 | 5 Highfields | BN1 9AR | B (Event Only) | Map | 2026-04-22
Batch 2 | Batch 2.1 | Batch 2 | Barrow Hill, adjacent to 53 Crespin Way | BN1 7FG | None | Map | 2026-04-22
Batch 2 | Batch 2.1 | Batch 2 | 1 Inwood Crescent - LC02 | BN1 5AP | A / PbyP | Map | 2026-04-22
Batch 2 | Batch 2.1 | Batch 2 | 46 Stephens Road - LC05 | BN1 7ER | None | Map | 2026-04-22
Batch 2 | Batch 2.1 | Batch 2 | 49 Compton Road - LC05 | BN1 5AL | A / PbyP | Map | 2026-04-23
Batch 2 | Batch 2.1 | Batch 2 | 5 Fairlie Gardens - LC02 | BN1 6PY | 10 | Map | 2026-04-23
Batch 2 | Batch 2 | Batch 3 | 57 Preston Drove - LC38 | BN1 6LA | J | Map | 2026-04-23
Batch 2 | Batch 2.1 | Batch 2 | 83 Millers Road - LC04 | BN1 5NQ | A | Map | 2026-04-23
Batch 2 | Batch 2.1 | Batch 2 | Bavant Road, adjacent to 28 Harrington Road - LC01 | BN1 6RD |  | Map | 2026-04-24
Batch 2 | Batch 2.1 | Batch 2 | Opposite 119 Compton Road - LC11 | BN1 5AN | A | Map | 2026-04-24
Batch 2 | Batch 2.1 | Batch 2 | Opposite 48 Inwood Crescent - LC08 | BN1 5AP | A / PbyP | Map | 2026-04-24
Batch 3.1 | Batch 2.1 | Batch 3 | Churchill Square Shopping Centre, Cannon Place - LC12 | BN1 2ED | Z / PbyP | Map | 2026-04-24
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | Opposite 11 Hawthorn Close - LC02 | BN2 8HX | None | Map | 2026-04-27
Batch 1 | MGroup Batch 1 - Post | Batch1 - Supp post | Buller Road, adjacent to 50 Milner Road - LC02 | BN2 4BH | n/a | Map | 2026-04-27
Batch 2 | Batch 2.1 | Batch 2 | 36 Waverley Crescent - LC03 | BN1 7BG | None | Map | 2026-04-27
Batch 2 | Batch 2.1 | Batch 3 | 1 Loder Road - LC45 | BN1 6PL | F | Map | 2026-04-27
Batch 1 | MGroup Batch 1 - Post | Batch 3 | 28 Heath Hill Avenue - LC33 | BN2 4FH | n/a | Map | 2026-04-28
Batch 2 | Batch 2.1 | Batch 3 | 13 Hollingbury Place - LC05 | BN1 7GE | None | Map | 2026-04-28
Batch 2 | Batch 2.1 | Batch 3 | 13 Isfield Road - LC06 | BN1 7FE | None | Map | 2026-04-28
Batch 2 | Batch 2.1 | Batch 3 | 22 Ditchling Gardens - LC08 | BN1 6JX | G | Map | 2026-04-28
Batch 2 | Batch 2.1 | Batch 2 | 6 Stanford Road - LC01 | BN1 5DJ | DIS (Q / PbyP) | Map | 2026-04-29
Batch 2 | Batch 2.1 | Batch 2 | 61 Chester Terrace - LC06 | BN1 6GB | J | Map | 2026-04-29
Batch 2 | Batch 2.1 | Batch 2 | 68 Beaconsfield Villas - LC14 | BN1 6HE | J | Map | 2026-04-29
Batch 2 | Batch 2.1 | Batch 3 | 8 Melrose Close - LC01 | BN1 7BP | None | Map | 2026-04-29
Batch 2 | Batch 2.1 | Batch 2 | Old Shoreham Road, opposite Buxton Road - LC14 | BN1 5DD | Q / PbyP | Map | 2026-04-30
Batch 2 | Batch 2.1 | Batch 2 | Old Shoreham Road, opposite Lancaster Road - LC12 | BN1 5DD | Q / PbyP | Map | 2026-04-30
Program 1 | Batch 2.1 | Batch 3 | 21 Egginton Road - LC04 | BN2 4PL |  | Map | 2026-04-30
Program 1 | Program 1.2 | Batch 3 | 43 Halland Road - LC09 | BN2 4PG |  | Map | 2026-04-30
Program 1 | Program 1.2 | Batch 3 | 5 Hawkhurst Road - LC21 | BN1 9GF | D (Events) | Map | 2026-05-01
Program 1 | Program 1.2 | Batch 3 | 6 Middleton Rise - LC05 | BN1 9AN |  | Map | 2026-05-01
Program 1 | Program 1.2 | Batch 3 | 8 Standean Close - LC03 | BN1 9EU |  | Map | 2026-05-01
Program 1 | Program 1.2 | Batch 3 | Flats 27-32 Woburn Place - LC01 | BN1 9GA |  | Map | 2026-05-01
Program 1 | Program 1.2 | Batch 3 | Opposite 45 Ashurst Road - LC09 | BN2 4PH | D (Events) | Map | 2026-05-04
Program 1 | Program 1.2 | Batch 3 | Opposite 75 Hawkhurst Road - LC14 | BN1 9EF |  | Map | 2026-05-04