## Sheet1
Parameter | Preference |  |  |  | Big bang | Parallel | Phased | Relative Importance | Big bang | Parallel | Phased
How critical is the cost-effectiveness of ERP implementation for your business? | Medium | Approach | Match score | How critical is cost-effectiveness of ERP implementation for your business? | High | Low | Medium | 4 | 1 | 0 | 1
What is the acceptable speed of deployment for your business? | Medium | Big Bang | 21 | What is the acceptable speed of deployment for your business? | Fast | Medium | Slow | 3 | 0 | 1 | 1
How will you rate your business’ current level of technical expertise? | Medium | Parallel | 15 | How will you rate the current level of technical expertise in your business? | Low | High | Medium | 5 | 1 | 0 | 1
How many business/office locations do you have? | Multiple | Phased | 24 | How many business/office locations do you have in your business? | Single | Single | Multiple | 5 | 0 | 0 | 1
How many of these modules do you want to implement the ERP software in? | 1 to 3 |  |  | How many of these business functions do you want to implement the ERP software in? Finance, Supply Chain, Inventory Management, CRM, HR, Accounting, MRP, Analytics | 1 to 3 | 4 to 5 | More than 5 | 4 | 1 | 1 | 1
What level of ERP implementation risk is acceptable for your business? | High |  |  | What level of risk is acceptable for your business? | High | Low | Medium | 5 | 1 | 1 | 0
Are you willing to conduct frequent training during the implementation process? | Yes |  |  | Are you willing to conduct frequent trainings during the implementation process? | No | Yes | Yes | 3 | 1 | 1 | 1