## Instructions
Marketing Roadmap Template
This marketing roadmap template will help you to lay out an action plan for your marketing strategy. Based on the buying journeys you completed for your Buyer Personas, you should have a list of marketing actions you think will be needed. This template allows you to map those activities (and anything else) and build out an action plan for each. This should be treated as a live document and updated over time, as you add activities and gain more information about your marketing strategy. INSTRUCTIONS Step 1 - Add the marketing activities you intend to complete (ie, digital marketing, trade shows etc) to the Marketing Roadmap tab, including detail of timelines, dates, people involved and costs. You may not have all of this information immediately, particularly costs and time involved. This may come from bringing in a marketing agent, etc. Step 2 - Once you've determined the marketing activities you can then map them onto the timeline tab to show the schedule of those activities and when they will all occur. There is a filled out example on the next tab.

## Marketing Roadmap - Example
YOUR MARKETING ROADMAP
PHASE | INITIATIVE | ACTIVITY | KEY STEPS | WHO | ESTIMATED TIME | ESTIMATED DATES | ESTIMATED COST | NOTES
Phase One (Getting ready) | Digital | Website upgrade | 1. Create content plan and website brief to be sent to digital agencies and research most appropriate agencies. Send brief 2. Review agencies' proposals and select agency to complete the work 3. New website completed 4. Set up email marketing tool and templates and connect to website | 1. CEO & Marketing Manager (MM) 2. CEO & MM 3. Agency 4. MM | 3 months | May - July 2022 | $20,000
|  | Social channels set-up | 1. Define required social channels & their objectives 2. Define social calendar 3. Set up channels 4. Execute and continue to update social calendar | Marketing Manager | 1 month | July - August 2022 | $1,000 - $2,000
| Brand tone | Determine principles for the language and the brand's tone of voice | 1. Research target customers and develop customer personas 2. Audit current content against value proposition and purpose statement 3. Define tone of voice based on what customers respond to and and how we want to sound | Marketing Manager & CEO | 2 months | March - April 2022 | $
$
$
| Total for phase one |  |  |  | X months | Month - Month | $
Phase Two (Localisation) | Influencer strategy | Identify influencers in market who can endorse the product | 1. Identify relevant influencers in the market and create a personalised plan to engage 2. Confirm group of key influencers 3. Provide influencers with early access to product innovations, trend reporting, data and test ideas with this group - ongoing | MM (1, 2, 3, 4) | Ongoing | March 2023 | $10,000
| Content plan | Create a localised content plan | 1. Confirm any amendments needed to brand tone for the target market (taking into account translations, etc) 2. Hire a locally engaged copywriter 3. Build content plan for social channels - ongoing action | MM (1, 2, 3) | Ongoing | April 2023 | $
$
$
$
$
| Total for phase two |  |  |  | X months | Month - Month | $

## Timeline - Example
MARKETING ROADMAP - THE TIMELINE
[7 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024
PHASE | INITIATIVE | ACTIVITY | KEY STEPS | WHO | EST TIME | EST DATES | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A
Phase One (Getting ready) | Brand tone | Principles for tone of voice |  |  | 2 months | March - April | bar: 2022 M to 2022 A
| Digital | Website upgrade |  |  | 3 months | May - July | bar: 2022 M to 2022 J
|  | Social channels set-up |  |  | 1 month | July - August | bar: 2022 J to 2022 A
Phase Two (Localisation) | Influencer strategy | Identify influencers in target market |  |  | Ongoing | March 2023 | bar: 2023 M to 2024 A
| Content plan | Create a localised content plan |  |  | Ongoing | April 2023 | bar: 2023 A to 2024 A

## Marketing Roadmap
YOUR MARKETING ROADMAP
PHASE | INITIATIVE | ACTIVITY | KEY STEPS | WHO | ESTIMATED TIME | ESTIMATED DATES | ESTIMATED COST | NOTES
Phase One (Getting ready) | [6 empty] | $
$
$
$
$
| Total for phase one |  |  |  | X months | Month - Month | $
Phase Two (Localisation) | [6 empty] | $
$
$
$
$
$
| Total for phase two |  |  |  | X months | Month - Month | $

## Timeline
MARKETING ROADMAP - THE TIMELINE
[7 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024
PHASE | INITIATIVE | ACTIVITY | KEY STEPS | WHO | EST TIME | EST DATES | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A
Phase One (Getting ready)
Phase Two (Localisation)