## Instructions
📘 Annex C: Delivery Planning– Quick Guide
Delivery Timetable
This workbook is used to assess whether your project is well planned, realistic, and deliverable.
👉 Focus on clarity and practicality, not volume of detail.
🧭 1. Delivery Timetable
What to include
A typical response will have:
8–15 key activities
8–10 milestones (e.g. permissions secured, contractor appointed, works completed)
Activities in a clear, logical order
👉 Example sequence:
Design → Permissions → Procurement → Delivery → Monitoring
Example activities
Complete surveys
Secure permissions
Procure contractor
Deliver works
Install monitoring
Show dependencies and constraints
For each activity, include:
What must happen first (e.g. consents before works)
Any constraints, such as:
land access
planning approval
Accessibility and inclusion
Include specific actions where relevant, especially in:
design
delivery
engagement
Only complete where the activity includes a specific accessibility, inclusion or targeted engagement action.
👉 For example: |  | step-free access or improved surfacing
accessible information
targeted community engagement
Procurement and timing
Show how you have planned:
procurement timelines
delivery around seasonal constraints
Avoid
Too many small or repetitive tasks
Missing key steps (e.g. permissions, procurement)
Vague descriptions (“works delivered”, “project managed”)
✅ Final check
✔ Activities are clear and in order
✔ Key milestones are included
✔ Dependencies and constraints are explained
✅ Key message |  | You will be assessed on how clear, realistic and deliverable your plan is — not how much detail you include.

## Delivery Planning
What a proportionate response looks like....
For Delivery: You do not need to list every task in detail.
Focus on: Key activities (8-15 rows typical); Major milestones; Critical dependencies (e.g. permissions, procurement)
Good applications will show how procurement has been planned to align with seasonal and environmental constraints to ensure timely and compliant delivery
Activity Planning | [6 empty] | Delivery Logic | [5 empty] | Management & outcomes
Workstream (Select from dropdown) | Activity (What are you delivering? Be Specific) | Start Month | End Month | Milestone (Y/N) Dropdown | Milestone Description | Deliverable / Result (What will be completed?) | Owner (Role) | Key Dependencies (What must happen first?) | Permissions / External constraints (Planning, permissions, land access) | Procurement Required (Y/N) Dropdown | Seasonal constraint (if applicable) | Accessibility & inclusion action (Describe specific actions to improve accessibility and inclusion (step-free access, inclusive signage, targeted engagement with underrepresented groups) | How progress will be tracked (monthly reports. Site visits, footfall monitoring, etc) | Notes / Assumptions | Workstream List
Consents | Secure land access and agreements | 2026-12-01 | 2027-01-01 | Yes | Land access agreements signed | Signed agreements in place | Project manager | Initial landowner engagement completed | Landowner agreement required | No |  |  |  |  | Mobilisation
Procurements | Procure contractor for path works (timed to avoid nesting season) | 2027-01-01 | 2027-03-01 | No | Contractor appointed ahead of April mobilisation window | Contractor ready to start on site in April 2027 | Commercial lead | Completion of ecological surveys & design | Work must avoid bird nesting season (April-Aug); planning consent required. | Yes | Apr-Aug |  |  |  | Design & Surveys
Consents
Procurements
Delivery
Engagement
Monitoring
Communications