## Instructions
📘 Annex D: Risk Management – Quick Guide
Risk Management Plan
This workbook is used to assess whether your project is well planned, realistic, and deliverable.
👉 Focus on clarity and practicality, not volume of detail.
🧠 2. Risk Management Plan
What to include
Focus on your main risks (around 8–12).
Write each risk clearly using:
Cause → Event → Impact
👉 Example: |  | Delay in land agreements → works cannot start → project delays
For each risk include:
Likelihood and impact score
Mitigation / controls (how you reduce the risk)
Contingency (what you will do if it happens)
Risk owner (responsible role)
Link risks to delivery
Your risks should relate to your plan, for example:
permissions and consents
procurement
delivery works
environmental constraints
Avoid
Generic risks or repeated answers
Overly long lists of minor risks
Vague actions (“monitor regularly”)
✅ Final check
✔ Responsibilities are assigned
✔ Risks are specific and realistic
✅ Key message |  | You will be assessed on how clear, realistic and deliverable your plan is — not how much detail you include.

## Risk Management
You are not expected to provide a detailed operational risk management framework at this stage.
Focus on your key delivery risks, how you will manage them, and what you will do if they occur
The risk category should broadly reflect the stage or area of delivery that the risk relates to (for example: procurement, consents, delivery). It does not need to map directly to each activity in your delivery timetable
|  | 1=Rare | 1- Low impact
|  | 5=Almost certain | 5= Severe impact
Risk description (cause> event> impact) | Project Phase / area | Likelihood 1-5 (dropdown) | Impact 1-5 (dropdown) | Score (Likelihood x Impact) | Mitigations / controls (how will you manage this risk) | Contingency (What will you do if it happens?) | Risk owner (role) | Monitoring trigger (optional - what would indicate this risk is increasing)
Delay in securing land agreements > work cannot start. project delays | Consents | 3 | 4 | 12 | Early engagement with landowners; use of standard agreements; legal support in place | Resequence delivery to prioritise accessible sections; escalate to senior stakeholders | Project manager | Lack of agreement progress by Feb 2027
|  |  |  | 0 |  |  |  |  | Categories List
|  |  |  | 0 |  |  |  |  | Mobilisation / governance
|  |  |  | 0 |  |  |  |  | Design & Surveys
|  |  |  | 0 |  |  |  |  | Permissions & Consents
|  |  |  | 0 |  |  |  |  | Procurements
|  |  |  | 0 |  |  |  |  | Delivery / Construction
|  |  |  | 0 |  |  |  |  | Environmental / seasonal
|  |  |  | 0 |  |  |  |  | Stakeholder / engagement
|  |  |  | 0 |  |  |  |  | Monitoring / reporting
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0