## Lessons Learned Template
Lessons Learned Template
Today's Date: | 2021-01-02
Project Name:
Project Manager:
Notes: | (add any extra info here)
Date | WIN or ISSUE | Describe What Happened | What Was the Impact? | How Does This Change Future Projects? | Action Items
| WIN | We implemented a new time tracking system with the team to test whether or not productivity would improve | We saved 200 hours of time and delivered the work 2 weeks early | We will roll out time tracking to all teams in the company | 1. Purchase software licenses for all employees 2. Send email explaining why time tracking is necessary
| ISSUE | Our IT manager for the project was out sick for 2 weeks and there was no available replacement, so we had to wait for her return | The project was delayed 4 weeks and the client was upset. A $25,000 credit was issued to the client | We need to have redundancy in the IT department to ensure there is always someone available | Chat with CEO and HR about hiring additional IT help
| WIN | The client was so happy with the final presentation that she offered us a 2 year exclusive contract! | This contract is going to double our revenue growth over the next 2 years | The new style of in-person client presentation should be used on more projects, when possible. | Share the new client presentation format with other teams

## How to Use This Template
How to Use Our Lessons Learned Template
The lessons learned template is a tool to note what worked and what didn't in our project, so we can repeat the positive and avoid the negative.
WIN or ISSUE: Choose either WIN or ISSUE to classify the lesson. A win is something positive that happened, and an issue is something negative that happened
Describe What Happened: Use this field to give a detailed description of the lesson you learned
What Was the Impact?: Here, you’ll describe the positive or negative result, and the impact there may have been. For a win, write about the positive outcome that occurred. For an issue, write about the negative consequences you experienced due to the problem
How Does This Change Future Projects?: In this field, record your thoughts on how this lesson might impact future work. Think about how other people in your organization might benefit from learning this lesson
Action Items: Add the actionable steps that will be taken to address your win or issue. Every row should have an action item, even if it is as simple as “monitor to see if it happens again.” This is the most important part of the template, because you are outlining the steps you will take to improve