## 1 GIA
Gender impact assessments
Table 1 - Gender impact assessments progress
Required | Required | Required | Required | Required | Required | Recommended | Recommended
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
Uniform Policy | Policy | This policy guides the ordering and use of all GMCT's unfiorms for employees across all 21 sites. The policy outlines the process of ordering uniforms and guidelines that staff must adhere to particularly as front facing staff members. | For Review | Yes | Gendered language has now been removed from policy and ordering forms. | Yes | This policy in particular seemed to not include an intersectional lens when it came to people of all genders intersected with sexuality and cultural or religious requirements.
History and Heritage AR app | Program | This app was designed for community members to design and learn about the heritage and history of the various cemeteries that form part of the Greater Metropolitan Cemetries Trust. Part of this includes stories of people buried and their contribution they made to society. | For Review | Yes | We have consulted with a number of different people/groups regarding the history and heritage projects – notably, interviews with a small group of professional and amateur historians for the website content, and a diverse group of stakeholders from different cultural contexts for the app | Yes | Examining possible additional needs led the group into ‘solution mode’ but pointed to the importance of producing content that is accurate, representative and culturally aware, and a user experience that is device agnostic, accessible and considers UX. The need for LOTE versions of the app was also raised, as were cultural barriers to participation beyond language.
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.
Example(s)
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review | Yes | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated womens and all-gender secured changerooms and facilities for all womens and gender-diverse teams who hire Council sportsgrounds. | Yes | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are percieved as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.

## 2.1 Strategies and measures
Strategies and measures
Table 2.1 - Strategies and measures progress
Required | Required | Required | Recommended | Recommended | Recommended | Recommended
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | Relevant indicator(s)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Indicators key
List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. | [6 empty] | 1. 2. 3. 4. 5. 6. 7. | Gender composition of all levels of the workforce. Gender composition of governing bodies. Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender. Sexual harassment in the workplace Recruitment and promotion practices in the workplace. Availability and utilisation of terms, conditions and pratices relating to: - family violence leave - flexible working arrangements - working arrangements supporting employees with family or caring responsibilities Gendered segregation within the workplace
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | 1 | 2 | 3 | 4 | 5 | 6 | 7
1.1 Governance: Regular reporting of progress on GEAP to executive team | Complete | Reporting every 6 months. This is now BAU for our Executive Team and Board to be aware of the our progress on all active GEAP items | This can be considered successful. This reporting cycle provides our ET the opportunity to have oversight over the progress to key actions to promote further gender equality at GMCT | 2025-12-01 | Manager Organisational Development and Inclusion | X |  | X | X | X | X | X
1.2 Governance: Develop a Cemetery Industry diversity and inclusion (D&I) committee to meet regularly and collaborate to achieve a more inclusive industry | Complete | We have commenced monthly meetings in April 2023 with senior stakeholders at both GMCT and SMCT, however we are wanting to build upon this foundation before expanding to include other Class A and Class B Cemetery Trusts. | This can be considered successful, with further opportunity existing to include stakeholders from more Trusts across Victoria. | 2023-12-01 | Manager Organisational Development and Inclusion | X |  | X | X | X | X | X
1.3 Governance: Launch the D&I working group,with an executive sponsor, to track progress on actions and results | Complete | We launched the D&I Network in June 2023 and currently have a group of 16 participants from across the business that attend the monthly meetings. These meetings have been very effective in sharing key D&I learnings, promoting upcoming D&I events and training, and discussing improvements that can be made to our ways of working to ensure a more inclusive working environment at GMCT | This can be considered successful. Since commencing, the D&I network have met every 4-6 weeks and have provided very positive feedback as to the sense of belonging within the group and the clear purpose to promote inclusivity at our organisation. Further opportunity exists to encourage greater participation from all regions. | 2022-12-30 | Manager Organisational Development and Inclusion | X |  | X | X | X | X | X
2.1 Inclusive Culture: Finalise the D&I strategy | Complete | Completed - launched as of June 2023 and communicated to all staff including our Diversity and Inclusion Nedtwork and our Community Advisory Committee and Board | This can be considered very successful. The DISAP has been completed and shared with our workforce, and has received positive feedback from a variety of stakeholders including our Board, our Community Advisory Committee and our Diversity and Inclusion Network. | 2023-12-31 | Manager Organisational Development and Inclusion | X |  | X | X | X | X | X
2.2 Inclusive Culture: Develop a communications and education plan that outlines why gender equality is important and steps everyone can take to support D&I. This will also include understanding more about intersectional gender inequality and inclusive language | Complete | We have co-designed a communications plan with our internal SMEs and we utilise key dates such as International Women's Day to inform and educate our workforce on key matters relating to gender equality. We have also incorporated references to intersectional gender inequality through our Occupational Violence program which was delivered to all of our employees, specifically discussing groups that might be at a higher level of risk than others when considering intersectionality | This has been carried out successfully, and has been built into our annual diversity and inclusion events calendar and our ongoing occupational violence training program. | 2022-12-31 | Manager Organisational Development and Inclusion | X |  | X | X | X | X | X
2.3 Inclusive Culture: Continue with awareness raising events to celebrate key dates on the diversity calendar such as International Women’s Day, International Day of People with Disabilities, NAIDOC Week, Harmony Day, Wear it Purple Day, Pride Week, Equal Pay Day | Complete | We commenced our D&I events in December with International Day of People's with a disability, and have events that will be taking place across the remainder of the year including Pride March in February, International Women's Day in March, and National Reconciliation Week in May / June. This has been marked as complete as they are now built into our regular staff events and wellbeing calendar | This has been very successful and has been well received by our employees. This work will be continued now that we have an active D&I network and we are resourced with a dedicated D&I advisor position | 2023-12-31 | Manager Organisational Development and Inclusion | X |  | X | X | X | X | X
2.4 Inclusive Culture: As part of the communications plan, 2024 consider ways to mark events and create symbols that indicate strong support for diversity with particular focus on: o Aboriginal and/or Torres Strait Islander employees o Gender diverse and LGBTIQ+ employees o Employees who are carers o Employees from diverse cultural identities o Employees who speak different languages | In progress | We have commenced looking at the most suitable options for symbols to support all community groups and look to launch various options to employees aligned to culturally significant dates across 2024 and 2025. | This is at early stages and is not yet due. | 2024-12-31 | Manager Organisational Development and Inclusion | X |  | X | X | X | X | X
3.1 Inclusive People Policies and Practices: Improve gender equality audit data collection, including reporting of people of self-described gender and intersectional experiences through employee survey data | Complete | Whilst this is an ongoing piece of work to continuously improve, this action has been completed as following the gender audit conducted in 2021. We also include reference to self-reporting of self-described gender and intersectional experiences every two years as part of our employee engagement survey process. | This has been completed to a satisfactory standard, and we hope to continue to receive more data and insights over coming surveys. | 2025-12-31 | Manager Organisational Development and Inclusion |  |  | X | X | X | X
3.2 Inclusive People Policies and Practices: To ensure consistency across the cemetery industry, collaborate with SMCT to align our ANZSCO codes for our positions which are the same across both organisations | In progress | Awaiting ANZSCO codes as part of GEAP progress reporting to compare notes with SMCT. To ensure a consistent and thorough analysis across the industry, it requires collaboration with SMCT and therefore we have not met the deadline. This is an activity we would like to invest the right amount of time into and get meaningful results and insights for the sector. This will take place in FY25Q4. | This action is still pending and therefore success cannot be measured. | 2023-12-31 | Manager Organisational Development and Inclusion |  |  | X | X | X | X
3.3 Inclusive People Policies and Practices: Refresh recruitment and promotion processes with a D&I lens | In progress | New employees to be asked for feedback on the recruitment process as well as a Gender Impact Assessment to be completed in FY25. This will be launched in conjunction with our D&I induction module. To review the promotion practices we will require support and assistance from HR as we don't have access to this data | This action is still pending and therefore success cannot be measured. | 2023-12-31 | Manager Organisational Development and Inclusion |  |  | X | X | X | X
3.4 Inclusive People Policies and Practices: Educate people leaders on ways to challenge unconscious biases, particularly relating to gender, age, cultural background, disability and Aboriginal and/or Torres Strait Islander background | In progress | To be included in FY25 leadership development program | This action is still pending and therefore success cannot be measured. | 2025-12-31 | Manager Organisational Development and Inclusion |  |  | X | X | X | X
3.5: Inclusive People Policies and Practices: Build a D&I induction module for new employees | In progress | Draft induction pack has been designed, but is not yet completed and rolled out to new employees. | This action is still pending and therefore success cannot be measured. | 2023-12-31 | Manager Organisational Development and Inclusion |  |  | X | X | X | X
3.6 Inclusive People Policies and Practices: Review talent identification, performance evaluation and succession planning data to identify if any biases are slowing the progression of women through GMCT | Complete | Analysis conducted in April 2023 across data extracted from succession planning for our SLT, criticial role identification and newly development senior leadership matrix by the executive team which allowed peer review across directorate to remove unconscious biases, these results are also reported to EPRC as part of the annual workplan reporting in November each year. Next report is due in November 2024. Gender split for succession planning is 1 female and 1 male identified as ‘Star’, 4 males identified as ‘Rising Star’ and 2 females and 6 males identified ‘High Contributors’. | Whilst we are capturing the data annually, the level of analysis into any gender biases that might exist is low. It is to be expected that the gender split percentage per talent and succession planning category is similar to our workforce composition gender split (62% men, 38% women). Our talent percentage per gender split is 79% men to 21% women which indicates we can do more to encourage the development of women to ensure a gender split which is reflective of our entire workforce gender split. | 2025-12-31 | Manager Workforce Development |  |  | X | X | X | X
3.7 Inclusive People Policies and Practices: Educate leaders on the importance of career-focused learning and development programs reflecting as close as possible to a 40/40/20 gender split | Not started | Not yet due to be commenced - to be reviewed following February GEAP progress reporting based on fresh learning data | This action is still pending and therefore success cannot be measured. | 2024-12-31 | Manager Organisational Development and Inclusion |  |  | X | X | X | X
3.8 Inclusive People Policies and Practices: Explore a leadership development and/or mentoring program which can support women to gain further leadership and career-planning skills | Not started | Not yet due to be commenced | This action is still pending and therefore success cannot be measured. | 2024-12-31 | Manager Organisational Development and Inclusion |  |  | X | X | X | X
3.9 Inclusive People Policies and Practices: Undertake further exploration with people leaders to ensure higher duties are offered across all genders equally, particularly at Level -2 | Complete | Over the reporting period, 26 (29%) women performed in higher duties as opposed to 63 men. Men had more opportunities at all levels except for level -1 where 67% of higher duties were offered to women. The largest variances of higher duties were at level -2 (only 25% of higher duties for women) and level -4 (29%). Level -3 was 41% of women in higher duties roles. | The data shows that more effort can be made to ensure women at level -2 are offered more opportunities for higher duties opportunities that their men counterparts. This is slightly under the percentage of women relating to gender composition of the workforce. | 2023-12-31 | Manager Workforce Development |  |  | X | X | X | X
3.10 Inclusive People Policies and Practices: Develop a Reconciliation Action Plan | Complete | A Reflect Reconciliation Action Plan was endorsed by Reconciliation Australia in December 2023. This was delayed from the intial due date due to an organisational restructure, difficulty in finding a Wurrundjeri artist to complete RAP artwork, and a delay in endorsement from Reconciliation Australia. This is our first ever RAP for our organisation. Our workforce will be notified of our RAP early 2024 and the document will also be available on our intranet for community and customers to access. | This can be considered a success. The Reflect RAP lays a foundation for policies, procedures, and ways of working that support our journey to reconciliation. We have seen our workforce feel a higher level of comfort in having discussions relating to the RAP, and we expect this to continue to develop and grow as we continue with our RAP actions and prepare for the next phase, the Innovate stage. | 2022-12-31 | Manager Organisational Development and Inclusion |  |  | X | X | X | X
3.11 Inclusive People Policies and Practices: Continue progressing with our five-year Disability Access and Inclusion Plan (DAIP) to support people with disability | In progress | Our 5-year DAIP is in its final year and we are on schedule to complete all actions within the committed timeframe. Only two items are outstanding but are on track to be completed as detailed in the DAIP. | This can be considered to be successful. All DAIP actions are completed except for two that are on track, and we are starting to consider how GMCT best incorporates principles of disability access and inclusion into our ongoing ways of working. | 2025-12-31 | Various owners, reporting by Corporate Planning and Reporting Lead |  |  | X | X | X | X
3.12 Inclusive People Policies and Practices: Develop a plan to support our ageing workforce, including items such as options of reduction of hours, a transition to retirement program, superannuation, time off work to manage caring and other needs | Complete | Plans are based on an employee's specific needs rather than across our entire workforce. Employees have contacted HR to discuss their individual needs, and our Leadership Team within the Operations and People directorate discuss the ageing workforce as a standing agenda item in their regular team meetings. Recurring Superannuation workshops have also been delivered by Vision Super annually across all regions with the next session scheduled for May 2024. Employees also have access to Clause 12.4 - Flexible working arrangements (specific circumstances) is available to EBA staff and used as a practice for non-EBA staff. In addition clause 44 Phased Retirement is also available for employees over 55 years of age. Superannuation session are included in the annual Wellbeing Calendar of events and offered to the workforce periodically over a 12 months period. | This can be considered successful. | 2025-12-31 | Manager Workforce Development |  |  | X | X | X | X
3.13 Inclusive People Policies and Practices: Improve pay equity o Upskill our human resources (HR) team to undertake annual gender pay parity assessments across all levels of our organisation | Complete | Manager Workforce Development is trained in analysing Korn Ferry Hay Remuneration and Job Evaluation methodology and in 2022 was trained in the Public Entity Classification Framework | This can be considered successful. | 2022-12-31 | Manager Workforce Development |  |  | X | X | X | X
3.14 Inclusive People Policies and Practices: Improve pay equity o Review positions in our payroll system to ensure positions reflect the salaries of other roles at the same level away from the CEO | Complete | A pay equity review was conducted in FY22 and FY23 to ensure alignment of roles and remuneration across all Non-EBA, Non-Exec roles consistent with responsibilities. Salary adjustments were approved and processed. | This can be considered successful. In 2021 there was a 6.1% pay gap which, as of 2023, is now a -0.9% pay gap in favour of women. Refer to indicator 3 of this report to see more detail relating to this. | 2022-12-31 | Manager Workforce Development |  |  | X | X | X | X
3.15 Inclusive People Policies and Practices: Provide annual education and/or communication to ensure that everyone is fully aware of GMCT’s sexual harassment, discrimination and harassment policy and processes that are in place | Complete | Sexual harassment and discrimination was included within the Occupational Violence training program for all staff over September-November 2023. The policy will be renewed as part of our annual work plan within FY25 and will be considered as part of our annual training priorities within that year. | This can be considered a success. Further opportunities exist to utilise a learning management system to have a tailored learning module available for employees to complete annually as a standalone module. | 2022-12-31 | Manager Workforce Development |  |  | X | X | X | X
3.16 Inclusive People Policies and Practices: Research reasons why women are departing the business through a review of exit questionnaires with departing employees, applying a gender equality lens to our departures, and conducting ‘stay’ interviews with employees to gain insight as to the varying challenges faced by women and men | Complete | Exit Interviews are offered to all exiting employees however, it is not a mandatory requirement. In the GEAP reporting period from July 1 2021 to June 30 2023, there were 94 leavers. Of these, 41 (43.6%) were women. Of the 41 females that exited, 36 were voluntary departures and 5 was an involuntary departures. Of the 36 voluntary women departing, only 3 completed exit interviews. An analysis of exit interviews conducted for this period showed that they were leaving for better career opportunities or family / personal reasons. Within FY25, further work to gain insights on employees exiting the business will be conducted by the line manager plus the introduction of stay interviews. | This can be considered successful with further improvements as outlined in the status description. | 2023-12-31 | Manager Workforce Development |  |  | X | X | X | X
3.17 Inclusive People Policies and Practices: Continue to promote flexible working at GMCT (from induction onwards) | Complete | Flexible hybrid roles are advertised at recruitment (if applicable). Hybrid agreement is reached between successful candidate and relevant executive, and if an employee seeks to alter this arrangement, they are to discuss with their manager in the first instance. If the manager approves the request, they will then seek further guidance from HR to formalise the change. | This can be considered a success. Hybrid working arrangements are available for all employees to access should their personal circumstances change in accordance with the guiding principles available on our intranet. | 2025-12-31 | Manager Workforce Development |  |  | X | X | X | X
3.18 Inclusive People Policies and Practices: Create a campaign to encourage the continued use of carer's leave entitlements to support the high percentage of employees who have caring responsibilities | Complete | This action has been sufficiently completed, and is now an ongoing annual reminder that we provide our employees with every year as part of National Carer's Week. | This can be considered successful. | 2023-12-31 | Manager Workforce Development |  |  | X | X | X | X
3.19 Inclusive People Policies and Practices: Review and communicate family violence leave policies to ensure they are in line with best practice | Complete | This action has been sufficiently completed, and is now an ongoing annual reminder that we provide our employees with every year as part of National Carer's Week. Employees are aware that they have access to Clause 45 - Family Violence is available to EBA staff and used as a practice for non-EBA staff for employees. To-date one female employee has accessed this entitlement. Our Family Leave Policy is guided by the Vic Govt Wage Policy and is benchmarked on the VPS Agreement as it is more beneficial than the NES conditions | This can be considered successful. | 2023-12-31 | Manager Workforce Development |  |  | X | X | X | X
3.20 Inclusive People Policies and Practices: Increase awareness of the prevention of occupational violence | Complete | All training was delivered from September-November 2023 and was delivered to cohorts based on their level of exposure to OV situations (high risk and low risk). 87% of our workforce attended one of these sessions and the post-training evaluation forms found that 96% of the high risk group were favourable to the outcomes being suitable for their roles, and 69% of the low risk cohort was favourable. Follow up training will be implemented in 2024 every 6 months to catch new staff and those who missed training, and refresher training will be delivered every 3 years. | This action is considered to have been delivered successfully. Based on the post-survey evaluation surveys, we have determined the high risk training to be a huge success in achieving the desired outcomes. The low risk group survey results have identified some improvements could be made to future programs of a similar nature, with some considerations being in-person training and more interactive training. | 2023-12-31 | Workplace Health and Safety Manager (in consultation with General Manager Service and Delivery) |  |  | X | X | X | X
3.21 Inclusive People Policies and Practices: Continue to refresh parental leave and supporting processes to encourage access by different genders | Complete | Refreshed as part of our most recent enterprise agreement to remove reference to maternity / paternity and rename to parental leave, which is open to any parents regardless of gender. As per action 3.19, our Parental Leave Policy is guided by the Vic Govt Wage Policy and is benchmarked on the VPS Agreement as it is more beneficial than the NES conditions | This can be considered successful. Further opportunities could exist by having a regular communications campaign. | 2024-12-31 | Manager Workforce Development |  |  | X | X | X | X
4.1 Inclusive Partnerships: Explore opportunities to partner with the Southern Metropolitan Cemeteries Trust (SMCT) on a graduate program | Complete | GMCT graduate program runs from Sept 2023 to September 2025. GMCT explored an opportunity to partner with SMCT however they do not intend to have a graduate program in the near future. GMCT will again reach out to SMCT forwards the end of the current graduate program to invite them to participate. | Having developed strong relationships with SMCT, we are confident that this opportunity will be discussed when they decide to commence a graduate program in future. | 2023-12-31 | Manager Workforce Development | X |  | X |  | X |  | X
4.2 Inclusive Partnerships: Create a campaign to attract women school leavers and those studying at Technical and Further Education (TAFE) to consider GMCT as an employer | In progress | Discussions have commenced with the communications department on an attraction campaign | No evaluation required as action is not yet due | 2024-12-31 | Manager Workforce Development | X |  | X |  | X |  | X
4.3 Inclusive Partnerships: Consider partnerships with women in trade organisations to increase awareness of GMCT as a potential employer | Not started | Not yet due to be commenced | No evaluation required as action is not yet due | 2024-12-31 | Manager Workforce Development | X |  | X |  | X |  | X
Select one
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.

## 2.2 Resourcing your GEAP
Resourcing your GEAP
Table 2.2 - Allocation of resources to implement the strategies and measures in your GEAP
Recommended
You might consider some or all of the following, in addition to any other aspects you consider relevant: • Who implements the strategies and measures in your GEAP? What role do they perform at what level in your defined entity? • How many staff members/FTE are allocated to implementing the strategies and measures? • Was enough resourcing allocated to successfully implement your strategies and measures? If not, how will this be addressed?
Your Comments
Our organisation has implemented a restructure to consolidate all of our diversity and inclusion scope into one team under the newly formed Governance directorate, and is the responsibility of the Manager Organisational Development and Inclusion. This allows for clear and consisten governance, management and reporting across all of this portfolio. GMCT has also created a new FTE position of Organisational Development and Inclusion Advisor to support the Manager to execute actions outlined in all of our D&I strategies and action plans. This role commenced on 27 September 2023. The actions detailed in the GEAP are owned by key Managers in the organisation, namely the Manager Organisational Development and Inclusion, Manager Workforce Development and Manager Workplace Health and Safety. Whilst these three managers are accountable for the satisfactory acquittal of each of their assigned actions, they have been supported by their team members to complete these required tasks. The number of staff involved in completing these actions total 11 employees across the three teams. Resourcing is sufficient to carry out the required tasks at this stage, however the reporting requirements every two years are difficult from a resourcing perspective given the level of detail required by the Commission.

## 3 Indicators
Workplace Gender Equality Indicators
Table 3 - Workplace gender equality indicators progress
Required | Required | Required | Recommended | [6 empty] | Recommended | Factors key:
|  |  | Factors | [7 empty] | a. b. c. d. e. f. g. | The size of the defined entity, including the defined entity's number of employees. The nature and circumstances of the defined entity, including any barriers to making progress. Requirements that apply to the defined entity under any other Act, including an Act of the Commonwealth. The defined entity's resources. The defined entity's operational priorities and competing operational obligations. The practicability and cost to the defined entity of making progress. Genuine attempts made by the defined entity to make progress.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
Gender composition of all levels of the workforce | Yes | Whilst our workforce has grown since 2021 by 28 employees (11.3% increase), we have also seen an increase of the percentage of women in our workforce from 34% to 38%. This increase has been evident at Levels -3 (+11%) and -4 (+3.5%) levels of the organisation. An 11% decrease of women at -2 level shows that there is more to be done at senior leadership level. There has been no change at Executive level (change of gender for CEO however we have gained one more woman executive).
Gender composition of governing bodies | No | The composition of our governing body remains similar to that of 2021.
Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender | Yes | In 2021 there were pay gaps at all levels away from CEO, however after a lot of work to reduce these pay gapsand conducting a pay parity review against the new Public Entity Executive Classification Framework (PEECF) and the Korn Ferry Hay Remuneration Framework, we have found that in 2023 that there is now a pay gap in favour of women across annualised base and total remuneration for mean and median calculations. There is no pay gap existing at level -3, whereas larger discrepancies exist at our non-enterprise agreement levels: Level -1 (in favour of women) and -2 (in favour of men). The largest variance for pay gaps in 2023 are for part-time contract positions which is due to one man at level -1 (Executive) on a part-term fixed term contract compared to 1 and 4 women at levels -3 and -4 respectively. As at June 2023, Level -2 includes 20 men and 8 women. Thnese 8 women consist of 4 senior leader positions and 4 support / assistant positions.
Sexual harassment in the workplace | Yes | There have been no sexual harassment claims within the reporting period.
Recruitment and promotion practices in the workplace | Yes | Recruitment: Our overall results for recruitment across genders for 2023 shows an even 50/50 split which is an improvement on the 2021 results (35% women, 65% men). We gained one woman at Level -1, one man at Level -2, and had an even gender split at Levels -3 (2 women and 2 men) and -4 (19 women and 19 men). Permanent Promotions: A variance of permanent promotions across genders exists which is to be expected given the current composition of our workforce is only 35% women. Whilst the gender split of permanent promotions dropped from 33% women in 2021 to 25% women in 2023, the total number of permanent promotions within the reporting periods was vastly different - only 9 promotions in 2021 compared to 34 promotions in 2023 (+278% increase). This is a result of our focus on offering career development opportunities with an increase of total promotions at levels -2, -3 and -4. In particular, Level -4 had no permanent promotions in 2021, whereas in 2023 we had 17 promotions. Only men have been promoted at Level -2 in both 2021 (2 men employees) and 2023 (4 men employees). Career Development Training Opportunities: Whilst career development training has slightly decreased for women at levels -1 and -2 since 2021 (-10% in 2021 and -9% in 2023 respectively), this aligns to the workforce composition of women at these levels in 2023. Women at levels -3 and -4 went from undertaking 32% of overall career development training for both levels in 2021 to 57% and 55% respectively. Higher duties: In 2021, more higher duties were undertaken by women than men (54%). This has decreased in 2023 to 32% women. While Level -3 has a minimal variance across genders (47% women), the variance was more considerable at levels -2 and -4. Only men at level -2 have carried out higher duties during both 2021 (2 in total) and 2023 (3 in total). A larger variance existed at level -4 whereby, despite an almost even split in 2021 (47% women), men had 78% of the higher duty opportunities. This is, again, reflective of the much higher representation of men at this level given the nature of our operations and industry. Internal Secondments: Secondments across all levels showed a 50/50 split of men and women at levels -3 (4 in total) and -4 (2 in total). Exits: the exits in 2023 were an even gender split, improving slightly from 2021 where the exits were 45% women. There were slightly fewer numbers of exits overall for both levels -2 and -3 in 2023, with an even split across genders at level -2 and 38% of women at level -3 compared to 20% women exits in 2021. Level -4 had a much larger number of exits than in 2021, however the gender split of these exits was almost equal across genders (52% women).
Availability and utilisation of terms, conditions and practices relating to: - family violence leave; and - flexible working arrangements; and - working arrangements supporting employees with family or caring responsibilities | Yes | Composition of workforce by Level on formal flexible working arrangement: The total gender split of employees on formal flexible working arrangements is 53% women across the workforce. Whilst formal flexible working arrangements were evenly split across both genders for formal flexible working arrangements at level -1 and -3. Of our women employees at level -2, 87.5% are on formal flexible working arrangements. Composition of senior leaders by Flexible working arrangement type and Gender: Due to formal hybrid work arrangements being implemented since 2021, 91% of our senior leaders are working on a flexible work arrangement. The total number of senior leaders taking other types of flexible working arrangements reduced in 2023, the main variance relating to more instances of purchased leave (75% of all formal flexible working arrangements) in 2021. Only three men in senior leader roles had formal flexible working arrangements and no women partaking in these arrangements in 2023 outside of a hybrid working arrangement. Composition of people who took parental leave, average length of paid leave and average length of unpaid leave by Level to CEO, Employment basis and Gender: Only 7 employees took parental leave in 2023. One of these was a woman who extended her unpaid leave for another 52 weeks, the remaining 6 men took 5.7 weeks of paid parental leave and 3.6 weeks of unpaid parental leave in total. Spread across organisational levels, one man was at Level -2, all other employees were at level -4. Parental leave exits: No employees exited the organisation while on parental leave. Family violence leave was accessed by one employee in the 2023 reporting period. Composition of people who accessed carers leave by Gender: the 2023 gender split of 33% women remained very similar to the 2021 split of 35%. The total number of employees accessing carer's leave increased by 52% with an extra 18 employees accessing leave in 2023.
Gendered segregation within the workplace | Yes | Key roles that have seen a variance from 2021: 139999 Specialist Managers: have increased since 2021 for both genders with women remaining around 27% of these roles. 362211 Gardener (general): An increase of 8 employees in total gardener roles saw an increase of the percentage of women in these roles from 21% to 24%. 451399 Funeral Workers: There was a 3% decrease of women in funeral worker roles in 2023. 511112 Program or Project Administrators: Program or project administrators increased from 20% women to 37.5%. 512111 Office Manager, 521211 Secretary (general), 542111 Receptionist (general) - 100% of the employees in these roles are women. 531111 General Clerk: 90% of women in general clerk positions are women. 561999 Clerical and Office Support Workers: A slight shift in clerical and office support roles have seen more men in these positions than women in 2023 (56%) when compared with 2021 (40%). 821113 Earthmoving Labourer: While the large majority of earthmoving labourers remain men, there was an increase of women in these roles from 4% to 9%

## Examples (hidden)
1 Gender impact assessments
| Title | Subject | Description | Status |  |  | Confirm if actions taken |  |  |  | Describe actions taken |  | Confirm intersectionality considered |  | Explain intersectional lens applied
| What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. |  |  | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. |  |  |  | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. |  | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. |  | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
| Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review |  |  | Yes |  |  |  | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated womens and all-gender secured changerooms and facilities for all womens and gender-diverse teams who hire Council sportsgrounds. |  | Yes |  | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are percieved as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.
2.1 Strategies and measures
| Strategies and measures | Status | Status description | Evaluation of success | [6 empty] | Timeline | Responsible | Relevant indicator(s)
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
| List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | [6 empty] | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator.
| Example: Address gaps identified in collecting intersectional data as part of employee and payroll systems | Complete | This strategy was implemented in March 2023. A payroll systems firm was engaged to upgrade our systems to support the collection of intersectional data in relation to sexual orientation, race, Aboriginality, religion, ethnicity, disability and gender identity. We have now begun collecting intersectional data and addressing the gaps identified in our 2021 audit. | Although originally anticipated for implementation in 2022, delays meant this strategy was implemented in March 2023. Intersectional data is being collected as part of new recruitments and promotions, and voluntary updates by existing staff. New intersectional data as part of our 2023 progress audit and future GEAPs will enable us to better understand intersectional gender equality in our organisation and areas for improvement. | [6 empty] | 2022 | People and Culture Corporate Support | X | X | X |  | X | X | X
3 Workplace Gender Equality Indicators
| Indicator | Confirm if progress made | Progress description | Factors | [6 empty] | Factors discussion
|  |  |  | a | b | c | d | e | f | g
| This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
| Example 1: Recruitment and promotion practices in the workplace | Yes | Recruitment In our 2021 audit, women represented only 35% of new recruits in the year to 30 June 2021. In our 2023 progress audit, this rose 6% to 41%. In 2021, of the women we recruited, 17% were employed on a full-time permanent basis, 14% on a part-time permanent basis and 69% on fixed-term contracts. In 2023, 22% of women recruited were employed on a full-time permanent basis, 20% on a part-time permanent basis and 58% on fixed-term contracts. We were not able to collect non-binary or gender diverse data in 2021. Our employee and payroll systems have since been updated to collect improved gender-diverse data. This has been achieved through the implementation of strategy 5.2 under our 2021 Gender Equality Action Plan (GEAP): ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. As such, in 2023, our data showed that 2% of new recruits identified as non-binary or gender diverse. Our organisation argues that these figures, in conjunction with successful implementation of relevant GEAP strategies, contribute to progress against Indicator 5. Not only have we been able to notably increase our recruitment of women and gender diverse employees, but we have also been able to offer these new recruits more attractive contract conditions. Stable contracts will also support us to retain employees of all genders and move towards a more gender-balanced workforce in the future. Promotions Our 2021 audit showed that 25% of promotions in the 12 months to 30 June 2021 were awarded to women. These promotions occurred in the lower and middle levels of the organisation only, and not within the executive leadership team. Our 2023 progress audit showed that 30% of all promotions were awarded to women, an increase of 5%. Of these, 10% occurred in the higher levels of the organisation and were ongoing permanent roles. Our organisation historically has a very stable executive leadership team where roles tend to be longer-term contracts or ongoing positions, with few exits. We are pleased to see promotion at the higher level of our organisation into ongoing positions for women. In 2021, we were not able to collect promotion data for non-binary or gender-diverse employees. In 2023, our updated systems allowed us to collect this data. However, there were no promotions awarded to this staff cohort. We believe that a significant aspect of our success in increasing the proportion of promotions awarded to women has been our focus on improving secondment and higher duties opportunities for women and gender-diverse employees. The proportion of secondments awarded to women increased by 5% and the proportion of higher duties by 6% between our 2021 workplace gender audit and our 2023 progress audit. Data on higher duties opportunities for gender diverse and non-binary employees was not collected in 2021, therefore there is no measured change in the data. We consider these improvements, while small, to demonstrate measurable progress against the workplace gender equality indicator ‘recruitment and promotion practices in the workplace’. We also believe the uptick in career development opportunities for women and resulting increase in women’s share of promotions demonstrates that our strategic approach is effective. We hope to see similar improvements for gender diverse employees reflected in our 2025 data. | No | Yes | No | No | No | No | Yes | As a largely male-dominated industry we recognise we have started from a lower baseline for this indicator and there is further to go. Despite this, we have made genuine efforts to attract and recruit a more gender diverse workforce by implementing the strategies identified in our GEAP, in particular: strategy 5.2 ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. We note that we are two years into the four-year GEAP implementation period, and as such have not fully implemented all GEAP strategies. The majority of our strategies against this indicator remain in early implementation stage. We believe our genuine efforts to implement strategies against this indicator and measurable progress arising from the data, demonstrate progress against indicator 5.
| Example 2: Sexual harassment in the workplace | No | Our 2021 Employee Experience Survey data showed that 7% of women and 4% of men who responded to the survey had experienced sexual harassment in the workplace, and of those 5% of women and 6% of men made a formal complaint. In 2023, our Employee Experience Survey data showed that 9% of women and 6% of men who responded to the survey reported having experienced sexual harassment in the workplace, an increase of 2% from 2021 for both cohorts. Of those, 9% of women and 10% of men indicated that they had made a formal complaint. Our 2023 Employee Experience Survey also indicated that women with disability were overrepresented among those who reported experiencing sexual harassment. We have initiated a review process to consider how we might address this between now and the 2025 reporting cycle. No respondents in our 2021 Employee Experience Survey identified as gender diverse. We also didn’t record any formal sexual harassment complaints in our 2021 workforce reporting data from employees of self-described gender. In our 2023 employee experience survey, 2% of respondents identified as non-binary or gender diverse. Of this cohort, 10% indicated experience of sexual harassment, with 50% of this group indicating that they had made a formal complaint. We note that these figures represent an increase in anonymous self-reporting of sexual harassment. This is concerning, as anonymous reporting tends to be more accurate than formal incident reporting processes. In analysing our 2021 and 2023 audit data, we found that our workforce reporting shows minimal change in terms of outcomes for formal complaints of sexual harassment. In 2021, our audit data showed that no outcome was reached for 70% of matters where the complainant was a woman, and 50% of matters where the complainant was a man. In 2023, our progress audit showed that of the incidents of sexual harassment reported by women, no outcome was reached for 65% of matters. This figure was 40% for men. We did not collect data on gender diverse and non-binary employees in 2021, nor their experience of sexual harassment. Our 2023 progress audit showed that of the incidents of sexual harassment reported by gender diverse and non-binary employees, no outcome was reached for 67% of matters. The enduring high levels of formal complaints with no outcome across our 2021 and 2023 audit data suggests that we have work to do in effectively and efficiently resolving sexual harassment complaints. The lack of outcomes for incidents of this type may contribute to our lack of progress in reducing sexual harassment. As a result of this analysis, we are reviewing our GEAP strategies and measures to consider how we might better respond to, and therefore hopefully reduce, sexual harassment in our organisation. We consider that the anonymous nature of the Employee Experience Survey data provides an accurate representation of sexual harassment. The increased sexual harassment reported via the Employee Experience Survey data indicates ‘no progress’ was made by our organisation against this indicator. | No | No | No | Yes | Yes | No | No | (e) Competing priorities and operational obligations Our organisation is a metro health service. During the recent covid-19 pandemic, Victoria’s public health system experienced unprecedented demand. In particular, rates of access to ICU and ventilation increased dramatically. As such, our organisation prioritised its public-facing service delivery. We directed the majority of our stretched resources externally to enable high-quality public health care. Demand outstripped supply, and already-stretched resources were directed to keeping ICU and general wards staffed. As a result, we were not able to deliver comprehensive in-person bespoke staff training in relation to sexual harassment, so instead delivered a low-cost e-learning module. We also lacked the resources to comprehensively review our internal sexual harassment processes. (d) Resources As described cell D9, our resources were significantly stretched due to an increase in demand for ICU services during the covid-19 pandemic. Competing priorities reduced the resources available for internal-facing programs, such as comprehensive sexual harassment training delivery and process review. For this reason, we focussed on low-cost strategies and measures in our GEAP, including delivering a sexual harassment e-learning module, circulating internal communications campaigns and encouraging staff to undertake the Employee Experience Survey. Our communications campaign focussed on drawing attention to existing sexual harassment policies including how the organisation will respond.

## (Hidden) REF (hidden)
Policy | New | Yes | Select one | Yes
Program | For Review | No | Complete | No action taken
Service |  |  | In progress
Ongoing
Not started
Void/cancelled